INVITATION TO BID FOR CONSULTANCY

| 1 | Title of Consultancy | ADVERTISEMENT: TERMS OF REFERENCE FOR CHASP III MID-TERM EVALUATION |  |
| --- | --- | --- | --- |
| 2 | SCI Contracting Office | Save the Children Somalia/land Country Office |  |
| 3 | Period of Consultancy | The duration of the assignment will be 60 calendar days, inclusive of travel days and weekends |  |
| 4 | Consultant type required | Consultancy Firm |  |
| 5 | Responsibility for Logistics arrangements and Costs | Save the children will pay the consultant fee in a lump sum and will not reimburse any incurred costs during the assignment. The consultant will cover their own Logistical arrangements including food, accommodation, tickets and any other related expenses. Save the Children will cover the costs associated with data collection and its related costs. |  |
| 6 | Taxation Provisions | The consultancy firm shall be responsible for all taxes arising from the consultancy in line with the local Tax regulations applicable at the SCI contracting office. |  |
| 7 | Travel requirements | The consultancy firm will cover their travel costs (tickets) and arrange local travel to field sites and accommodation. |  |
| 8 | Security requirements | The consultancy firm will comply with standard of Save the Children Security procedures, including the completion of SCI online security training (applicable to international consultants) prior to travel to Somalia in case needed. |  |
| 9 | Professional quality and Expertise | The following are the minimum requirements for the Consultant Firm/individual to be considered for carrying out the assignment. - The evaluation firm must demonstrate gender balance and should include at least one woman with proven expertise and experience in women’s health and sexual and reproductive health (SRH) and SGBV in fragile or humanitarian contexts, serving as a lead or co-lead evaluator. Given the strong gendered dimensions of health outcomes, and the influence of unequal power dynamics within communities and health systems, it is essential that the evaluation be designed and led through a gender-responsive and intersectional lens to ensure findings and recommendations reflect women’s and girls’ lived realities. - At least 7 years’ experience and knowledge in designing and conducting gender-responsive, child-rights-sensitive program evaluations, including health programs that target SGBV, SRHR, and adolescent empowerment. Minimum 2 years of experience in SGBV programming to ensure appropriate expertise and a do no harm approach. - At least a master’s degree in public health or others relevant discipline. - Undertaken similar assignments of large multi area, multi-interventions health programs review in Somalia or a similar context. - Share evidence of similar prior assignments. - Having exceptional ability in critical and strategical thinking and drawing practicable recommendations and policy briefs from program reviews. - Fluency in English (verbal and written), Somali is an added value. |  |
|  | 10 EVALUATION CRITERIA The proposals submitted by consulting companies will be evaluated based on the following criteria: |  |  |
|  | Essential Criteria |  | Pass/Fail |
| 1 | The Bidder and its staff agree and Sign to comply with SCI policies embedded below at this ITB. The Bidder is to download below listed items, read, understand and sign off appropriate section in below. a) Terms & Conditions of Bidding b) Supplier Sustainability Policy and the included mandatory policies |  | Pass/Fail |
| 3 | A valid Certificate of Registration from the relevant Ministry of Commerce in Somalia. |  | Pass/Fail |
| 4 | A valid Tax Compliance Certificate the relevant ministry of Finance/Revenue Authority in Somalia. |  | Pass/Fail |
|  | Capability Criteria (Technical Evaluation): |  |  |
| 5 | Detailed technical proposal with clear understanding of the TOR and Methodology of how the consultant intends to conduct assignment with detailed work plan, clear milestones, methodologies, data analyses plan including any software to be used for analysis. This to be evaluated based on: - Overall quality, clarity, organization and relevance of the technical proposal document - The level of work plan detail and how it is related to the proposed methodology |  |  |
| 6 | Submit two Copies of the previous contracts or LPOs for similar assignment |  |  |
| 7 | Submit official and genuine signed official bank statement from 1st Nov 2024 to 30th Oct 2025. |  |  |
| 8 | Experience in conducting similar assignments related to the subject matter as proven experience. This to be evaluated based on: - Prior experience in conducting qualitative and quantitative research/ evaluation studies in developmental health & nutrition programs with strong SRH/ gender component. Working experience in the Somalia context is desirable. Provide two previous similar evaluation reports? - Submit CVs for the proposed technical team detailing qualifications and experience - Cover letter introducing the company, outlining their technical expertise and interest in the assignment including their technical suitability. - Updated Company Profile (Optional) |  |  |
|  | Commercial Criteria (Financial Evaluation): |  |  |
| 9 | Detailed financial proposal with budget breakdown including all expenses, fees, and taxes. 100% x Lowest bid valueCurrent value bid x X% |  |  |
| Note: For the technical analysis, a company must pass the essential criteria and score 70% and above on the capability to be considered in the next evaluation process and the ultimate decision will be based on interview performance. s |  |  |  |
| 11 | Application Procedure | - Interested consultant (s) who meet the consultancy requirements are requested to submit their bid and each application package should include the above required minimum requirements. Applications can be submitted by: Protected Email box below - Email should be addressed to Somalia.Tenders@savethechildren.org - Should you need any clarifications please direct your queries to Somalia.procurement@savethechildren.org and expect responses within maximum of two working days. - Note – this is a sealed tender box which will not be opened until the tender has closed. Therefore, do not send tender related questions to this email address as they will not be answered. The subject of the email should be TERMS OF REFERENCE FOR CHASP III MID TERM EVALUATION - All attached documents should be clearly labelled so it is clear to understand what each file relates to. - Emails should not exceed 15mb – if the file sizes are large, please split the submission into two emails. - Do not copy other SCI email addresses into the email when you submit it as this will invalidate your bid. All applications MUST be submitted on or before the closing date below to be considered for the assignment. Only shortlisted Candidates will be contacted. |  |
| 12 | Closing date for Applications | Interested consultants shall submit their applications through the above procedures on or before 10th January 2026, EAT at 11:59 PM. |  |

| We, the Bidder, hereby confirm we compliance with the following policies and requirements: |  |  |
| --- | --- | --- |
| Policy | Policy / Document | Signature |
| Terms & Conditions of Bidding |  |  |
| Supplier Sustainability Policy and the included mandatory policies | Click Here to Access |  |

| We confirm that Save the Children may in its consideration of our offer, and subsequently, rely on the statements made herein. |  |
| --- | --- |
| Signature: | ………………………………………………….. |
| Name: | ………………………………………………….. |
| Title: | ………………………………………………….. |
| Company: | ………………………………………………….. |
| Date: | ………………………………………………….. |

Terms of Reference for CHASP III Mid-term Evaluation

Introduction

Save the Children International (SCI), in partnership with the Ministries of Health of Puntland, Jubaland, and Galmudug, with funding support from the Swedish International Development Cooperation Agency (Sida) and the Swiss Agency for Development and Cooperation (SDC), has been implementing the Community Health and Social Accountability Programme (CHASP) since 2017. CHASP aims to reduce health disparities and advance universal health coverage in conflict-affected and underserved areas, with particular attention to the specific needs of women, adolescent girls, and marginalized populations, ensuring gender-responsive and transformative approaches are embedded across all interventions. A central priority of CHASP III, the third three-year phase of the programme, is to strengthen governance and accountability within federal and state Ministries of Health, supporting Somalia’s transition from donor-funded humanitarian services to government-led, sustainable systems.

Background of the program

The current phase, CHASP III, running from 2024 to 2027, builds on the achievements and lessons learned from its earlier phases. The program is designed to expand access to high-quality, gender-responsive reproductive, maternal, newborn, child, and adolescent health (RMNCAH) services, guided by the Essential Package of Health Services (EPHS) framework. CHASP III targets over 1.1 million people in Bari, Lower Juba, and Galgaduud, integrating previous investments in community health and social accountability. These include strengthening regional and district health management teams (RHMTs and DHMTs) and supporting community structures such as Community Health Committees (CHCs) and Child Welfare Committees, ensuring inclusive participation of women, adolescents, internally displaced persons (IDPs), minority clans, and persons with disabilities. The programme runs Father to Father (F2F) groups in certain clinics which aim to shift male attitudes and practices, foster shared caregiving, and support women’s and children’s health and wellbeing, including the reduction of sexual and gender-based violence (SGBV) and promotion of women’s and girls’ agency in household decisions. The program promotes a decentralized health system and scales up innovative, high-impact models like ICCM+, Family MUAC, and other community-led health and nutrition interventions. It prioritizes climate resilience by investing in eco-friendly health facilities and establishing preparedness mechanisms such as the crisis modifier fund for anticipatory action and rapid response. The scale up of SGBV prevention and response mechanisms including clinical management of rape, establishment of SGBV service points and a strengthened SRH package are also key in CHASP III to further enhance equitable access for adolescent girls and vulnerable women and ensure gender-responsive service delivery. The program centers on three outcome areas below:

1. Continued provision of the EPHS, including nutrition, ICCM, and with increased investment in SGBV prevention, family planning and other reproductive health services, and strengthened SGBV case management delivered to women and children.

2. Enhanced governance capacity of MoH to sustain equitable and climate-resilient health systems

3. Strengthened community structures to ensure ownership, inclusive participation, equitable access, and service utilization.

Overall Aim of the assignment

The assignment is two-fold: firstly, to identify areas for improvement and adaptation for sustainability in the day-to-day running of the programme. Secondly, the aim is to investigate CHASP’s long-term impact including improvements in vaccination coverage and mortality and morbidity rates related to preventable diseases, in CHASP districts over the 2017-2025 period of its implementation. The evaluation should apply a strong gender-responsive and intersectional lens, ensuring women’s and adolescent girls’ perspectives and experiences are meaningfully reflected throughout data collection, analysis, and interpretation.

Specific Objectives

- To assess how the planned outcomes and impacts of the program have been realized, including intended and unintended consequences and identify success and hindering factors (both internal/external factors) that positively or negatively influenced implementation.

- To conduct theory of change critical analysis to assess causality, assess whether activities logically led to outputs, outcomes, and impacts as envisioned in the Theory of Change (ToC), and identify synergistic effects of CHASP III interventions and integrated program components.

- To evaluate how program innovations strengthened existing health systems, focusing on health system building blocks along with community contribution and ownership in the decentralized health system.

- To assess how the project implementation adapted across the three member states (Jubaland, Galmudug and Puntland) in terms of governance and response to shocks (droughts, conflicts, and other emergencies).

- To evaluate the progress of the CHASP III transition strategy, assess how well each state aligns with the transition strategy and identify the main barriers and enabling factors affecting its implementation.

- To assess to what extent SGBV services are integrated with health, legal, and social protection systems to provide gender-sensitive, adolescent- and women-centered comprehensive support, and how accessible, coordinated, and survivor-centered are SGBV case management and referral services.

- To identify scalable, gender-transformative practices aligned with the Theory of Change (e.g., male caregiving, joint decision-making, youth-led advocacy or youth-centered empowerment such as girl’s shine model). This includes evaluation of Father-to-Father (F2F) support groups, with a focus on changes in men’s attitudes, caregiving practices, and the resulting impact on women’s wellbeing and decision-making power.

- To examine social inclusion in representation (gender, age, disability, location/migration status, clan minorities) in social accountability mechanisms (CHC, community outreach etc).

- To examine how the project upholds to the principle of do no harm, centrality of protection and conflict sensitivity.

- To assess trends in child and maternal morbidity and mortality in CHASP districts over the 2017–2025 programme period, using available HMIS, survey, and program data, triangulated with qualitative community feedback. Where data are limited or inconsistent, document gaps and propose strategies to strengthen monitoring for long-term impact assessment.

Methodology of the review

This review will use mixed methods, both quantitative and qualitative approaches to gather data. Quantitative data will be from health service catchment population level survey, triangulated with program indicator performance, HMIS and nutrition data from the MoH. While for qualitative data, individual and group in-depth interviews will be conducted with relevant stakeholders including Ministry of Health directors at federal level, three-member states, beneficiaries, district health management board member, donors, SCI field staff and other authorities in the project area.

Strategies to be used to collect relevant information include:

- Conduct Interviews with a representative range of samples of beneficiaries to capture information related to the relevance and appropriateness of the program innovation strategies utilized. (Ensure children, adolescent girls, IDP women and women with disabilities alongside male respondents to assess gender-differentiated experiences and outcomes).

- Conduct In-depth interviews with MoH directors and SCI field staff and other key stakeholders including key district level authorities and community leaders.

- Document success stories, case Studies, lessons learned, provide recommendation and policy implications/briefs.

An in-depth approach to data analysis is required. The statistical analysis of the quantitative component is expected to identify factors influencing program outcomes, thus establishing relationships between different variables and the outcomes of interest, as well as validating or challenging assumptions about the status of access and children affected by the crisis. It is expected that qualitative data will be analyzed using emerging codes, thus allowing for the identification of unanticipated factors/patterns. Extensive triangulation of qualitative and quantitative data will be required for validation of results and in-depth understanding of the effects observed. Findings should be disaggregated at multiple levels, including sex, disability, location, rural, urban, type of health facility, IDP/non-IDP condition, and where relevant, most prevalent community livelihood (such as pastoralism, agro-pastoralism, agriculture).

Output And Midterm Evaluation Criteria

In assessing project interventions, the midterm evaluation must follow The Organization for Economic Co-operation and Development (OECD) six evaluation criteria: relevance, coherence, effectiveness, efficiency, impact and sustainability plus health system resilience.

Relevance:

- Was the program design relevant to identified needs.

- To what extent was the program design adaptive to evolving needs and changing program implementation environment?

- Is there compelling evidence that points to the need for adjustment of the theory of change and the underlying assumptions that informed the program design?

Efficiency

- Are the financial resources, human resources and other inputs being used efficiently to achieve program progress?

- What specific measures can be taken to enhance value for money, and cost sharing in delivering program outputs?

Coherence

- To what extent has there been cooperation with other organizations/actors working on the same thematic components (in terms of complementarity, harmonization, and coordination with others)? Including other SCI projects)

- To what extent are the objectives aligned to the national priorities and strategies?

- To what extent were the program design and implementation aligned to community needs?

- To what extent is there complementarity between the CHASP program with integrated disease surveillance and response in the program target districts?

Effectiveness:

- To what extent are the planned program outputs delivered, and how are they contributing to the attainment of program objectives within the required timeframe?

- What has worked/not worked well in terms of activity implementation and the processes/systems deployed to facilitate the same?

- What are the barriers to immunization for zero-dose and under-vaccinated children in program target districts/health catchment populations?

Impact:

- Have key program results and lessons learned been incorporated into advocacy and training work?

- The program intervention contribution to the outcome of IPC (infection, prevention, and control) and net impact of nutrition intervention.

- What has changed in child vaccination coverage and maternal and child mortality and morbidity rates in CHASP program areas since the program started?

Sustainability:

- What has the program done to ensure sustainability of the health systems supported/developed in the first half of the project?

- What needs to be done to strengthen the sustainability of the program deliverables in the second half of implementation

Review team

Save the Children (SC) will oversee the review exercise and periodically update the donors of the evaluation progress. Furthermore, SC field and project team will provide necessary support at the field level.

Timeframe

The projected timeline of this review is about 9 weeks, including fieldwork and drafting and submitting the final report after feedback is incorporated and validation of the report.

Data Sources and Data Collection Methods/Tools

All primary data collected during the study must facilitate disaggregation by gender, age, and disability, location or remoteness, vulnerability status. Save the Children will provide guidance on tools and classification schemes for this minimum dataset.

Quantitative methods using structured questionnaires will be used to establish quantitative benchmarks in the Phase 1 log frame. Focus Group Discussions, Individual questioning with a scientific representation of all the stakeholders, will be used to collect detailed qualitative information.  It is expected that the consultant will come up with innovative ways of combining the various research tools and methodologies to get the right and accurate information.

During the MTR, the consultant will interview selected stakeholders including targeted beneficiary communities, Ministry of health of federal/member state authorities, Community Health Committees, Facility in charge and staff of implementing, men/women groups, religious leaders, opinion leaders, women leaders and WROs who provide critical SGBV&SRHR services in the case management system. Related to the Father to Father (F2F) groups, interview separately men and women from the same households in beneficiary data collection to assess shifts in attitudes, caregiving practices, and household gender dynamics.

A range of project documentation will be made available to the study team that provides information about the design, implementation and operation of the Program. Documents include: project progress report, Log frame and other previous evaluation reports.

The study team is required to adhere to the Save the Children Child Safeguarding; Protection from Sexual Exploitation and Abuse; Anti-Harassment, Intimidation and Bullying; and Data Protection and Privacy policies throughout all project activities.

Data collection the instruments include semi-structured interview questionnaires; one- on-one personalized in-depth interview questionnaires for key informants; focus group discussions (FGDs) with discussion guidelines; institutional fact establishment sheets. The questionnaires will be administered to the respondents, while Institutional fact establishment sheets will be used to collect specific quantitative and qualitative facts at the sampled institutions, including physical and non-physical facilities, enrolment, teacher establishment, etc.

Ethical clearance and considerations:

This will be a routine program evaluation and will not require ethical clearance.

Work Plan

| Activity | Feb |  |  |  | March |  |  |  | April |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity description | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | Wk4 |
| Kick off meeting and preparation of inception report |  |  |  |  |  |  |  |  |  |  |  |  |
| Review & approval of inception report by SC/ donors |  |  |  |  |  |  |  |  |  |  |  |  |
| Data collection, analysis & data cleaning |  |  |  |  |  |  |  |  |  |  |  |  |
| Preparation of preliminary/ 1st draft report |  |  |  |  |  |  |  |  |  |  |  |  |
| Review of 1st draft report by SC/ donors |  |  |  |  |  |  |  |  |  |  |  |  |
| Incorporate comments/ feedback into final report and submission to SC. |  |  |  |  |  |  |  |  |  |  |  |  |

The detailed work plan for the midterm evaluation is attached below. The roles and responsibilities to execute the process will be determined based on consultation with SC-Sweden/Switzerland and Save the Children Somalia Country Office.

Scope of the review

The scope of this assignment will be based on assessing outcomes, impacts, innovative interventions, objectives and key deliverables as stated in this Term of Reference.

Key deliverables

- A detailed proposal outlining the methodology and instruments of the review, including review guiding questions – Inception Report/Proposal.

- Clear plan of the key roles and responsibilities of the proposed team, the plan should contain short background of the person, how his/her experience fits well with proposed activities, time frame for each activity, etc.

- A debriefing presentation for donor and Save the Children International, to talk over the proposed approaches and methods in conducting the review and combine the feedback from the team.

- Shared the final detailed proposal with detailed implementation plan

- Shared the draft review report with the Donor and SC team for inputs

- Present the results from the review to Donor, SC and MoH and other stakeholders

- Submit the final draft of the report

- Draft evidence dissemination plan

Outline of the report

The proposed report format will encompass the following headings and subheadings:

- Title Page

- Table of Contents

- Executive Summary

- Preface the Report

- Introduction and Background description

- Scope and purpose of review

- Methodology (detailed)

- Results and Findings (detailed)

- Discussions

- Conclusion and recommendations

- Case studies, success stories, lessons learned, policy implications

- List of references

- Annexes

Expected Qualification and Experience of the review team

- The evaluation team must demonstrate gender balance and should include at least one woman with proven expertise and experience in women’s health and sexual and reproductive health (SRH) and SGBV in fragile or humanitarian contexts, serving as a lead or co-lead evaluator.
Rationale: Given the strong gendered dimensions of health outcomes, and the influence of unequal power dynamics within communities and health systems, it is essential that the evaluation be designed and led through a gender-responsive and intersectional lens to ensure findings and recommendations reflect women’s and girls’ lived realities.

- At least 7 years’ experience and knowledge in designing and conducting gender-responsive, child-rights-sensitive program evaluations, including health programmes that target SGBV, SRHR, and adolescent empowerment. Minimum 2 years of experience in SGBV programming to ensure appropriate expertise and a do no harm approach.

- At least a master’s degree in public health or others relevant discipline.

- Undertaken similar assignments of large multi area, multi-interventions health programs review in Somalia or a similar context.

- Share evidence of similar prior assignments.

- Having exceptional ability in critical and strategical thinking and drawing practicable recommendations and policy briefs from program reviews.

- Fluency in English (verbal and written), Somali is an added value.

Obligations Of the Parties

- The Consultant

- The lead consultant will assume overall responsibility for the deliverables.

- The Client

- SCI will support all stages of the evaluation process, including providing relevant documentation, assisting in the organization of data collection (giving contact details, ensuring the availability of interviewees and relevant data, providing feedback on drafts of all agreed outputs, including methodology).

The SCI MEAL advisor and research/ evaluation manager (child survival) will guide the evaluation, and they will:

- Provide input into the proposed methodology and tools

- Sign off final deliverables (inception report, final report)