## BH Latrine Construction
Technical Annex A1: Construction of Sand Cement block Shelters in Burao IDPs |  |  | ITB: Reference Number: SOM-HGA-24-ITB-002
DRC to complete |  |  |  |  | Bidder to complete
| Item/Milestone Required | Delivery Location | Unit | Quantity required | Item/Milestone offered | Quantity Offered
A | Construction of Sand Cement block Shelters in Burao IDPs | Site | Unit | Quantity
1 | Site clearing and removing all existing depris materails from the site and relocate them properly to other safe spaces. | Burao IDPs | LM | 1
2 | Excavate trench of 400mm widh with premeter of 42m lenth, and the maximum depth is 400mm until reaches to hard ground. | Burao IDPs | M3 | 3.2
3 | Construct a masonary foundation wall reaching upto 400mm above the ground level, using cement sand ratio of 1:4. | Burao IDPs | M3 | 5.6
4 | Construct hollow block wall jointed with cement sand mortar of 1:4 . Ensure proper blumbness and straightness of laying bricks, | Burao IDPs | m2 | 70
5 | Construct 200mm thick RCC lentel beam above windows and doors by using steel bars @dia12mm and Y6-Stirrups of 20mm C/C with a cement sand ratio of 1:2:4. | Burao IDPs | m3 | 0.8
6 | Prepare well compacted surface by using compacted soils and hardcore at the top, construct 10mm plain concrete slab and apply cement sand screed well leveled and smooth. | Burao IDPs | m2 | 6
7 | Prepare the screeding surface using a cement sand ratio of 1:3.5 to ensure proper slope of smooth follow of liquids during cleaning, make sure that skirting is also well labelled. | Burao IDPs | M3 | 1.66
8 | Construct a gauge #28 pox profile sheet for roofing using 2x3" timber framework gable trusses of 1000mm C/C and 800mm fully recessed purlines and an overhung of 400mm with the Guidance of the DRC Field Area Engineer. | Burao IDPs | m3 | 22.04
9 | Plastering with suitable 25mm thick cement sand mix (1:4) well bonded to existing joints . The area to be plastered is 128m2 | Burao IDPs | m2 | 128
10 | Prepare interior/Exterior walls for painting by applying one coat of whitewashing and one sky blue interior acrylic PVA paint using a roller. Ensure the floor is protected with a suitable splash sheet. | Burao IDPs | m2 | 128
11 | Supply and install steel framed banneled door of 2200mm high and 900 wide with a complete frame of having hinges and latches. | Burao IDPs | no | 2
12 | Supply and install two bannaled steel framed with security 1mm wire mesh fixing windows measuring 1000mm high and 1200mm wide, | Burao IDPs | no | 1
DRC to complete |  |  | Bidder to complete
Delivery time required (days after PO signature) |  | 60 days | Delivery time offered (days after PO signature):
Delivery Terms required (Add Incoterm if necessary) |  | DDP | Delivery Terms offered (must include incoterm):
Delivery Destination required |  | Burao | Delivery Destination offered:
Minimum bid validity period required after the closure date of the bid |  | 90 Days | Bid validity period offered:
Additional comments to bidders: |  |  |  |  | Company Name:
1 - Please, read all the documents carefully, then price it. 2 - The contractor must ensure full compliance with all applicable local regulations, building codes, and industry standards related to the distribution site and the work being carried out. This includes obtaining any necessary permits or licenses required for the project. 3 -The contractor should adhere to the agreed-upon delivery schedule to ensure that materials are delivered to the distribution site in a timely manner. Any delays or changes in delivery should be promptly communicated and approved by the appropriate parties. 4- The contractor is responsible for ensuring that all materials supplied meet the specified quality standards. This includes conducting quality checks, inspections, and tests on the materials to verify their compliance before delivery. 5-The contractor must prioritize occupational safety during the distribution process. This involves ensuring that all work teams or subcontractors adhere to proper safety procedures, including the use of personal protective equipment (PPE) and following safety guidelines specific to the site. Additionally, strict adherence to guidelines and protocols that are essential to protect the health and well-being of all involved. 6- Supplier will take all responsibilities of delivery facilitation including access and transportation 7-All items should be with in the standard specifications and not from sanctioned countries as Annex G clarifying |  |  |  |  | Contact Person:
Address:
Phone number:
Email Address:
Date:
Do you agree on all additional comment to bidder ?
Signed by a duly authorized company representative:
Title:
Print Name:
Stamp of company