JAMHUURIYADDA FEDERAALKA SOOMAALIYA

WASAARADDA BEERAHA & WARAABKA

جـمـهــو رية الصـومـال الفيدراليه

وزارة الزراعه والري

Federal Republic of Somalia

Ministry of Agriculture & Irrigation

Rural Livelihoods Resilience Program (RLRP)

Expression of Interest

(By the consulting firm in response to the REOI issued by the procuring entity)

For

Capacity Building on Nutrition-Sensitive Post-Harvest Practices

Ref No: SOM-2000004325-0145-CS-QCBS

Issue Date: 29/06/2026

Instructions to Consultants

Assignment Title: Capacity Building on Nutrition-Sensitive Post-Harvest Practices

Ref No: SOM-2000004325-0145-CS-QCBS

The Ministry of Agriculture and Irrigation of Federal Government of Somalia has received financing from the International Fund for Agricultural Development (IFAD) towards the cost of Rural Livelihoods Resilience Program (RLRP) and intends to apply part of the proceeds for the recruitment of consulting services.

The use of any IFAD financing shall be subject to IFAD’s approval, pursuant to the terms and conditions of the financing agreement, as well as IFAD’s rules, policies and procedures. IFAD and its officials, agents and employees shall be held harmless from and against all suits, proceedings, claims, demands, losses and liability of any kind or nature brought by any party in connection with Rural Livelihoods Resilience Program (RLRP).

The consulting services (the "Services") comprise the provision of Capacity Building on Nutrition-Sensitive Post-Harvest Practices.

This request for expressions of interest (REOI) follows the general procurement notice that appeared on the IFAD website on November 2nd, 2024, on UNDB on November 2nd, 2024 and on the ministry of agriculture and irrigation’s Website on November 2nd, 2024.

The Ministry of Agriculture and Irrigation of Federal Government of Somalia (“the client”) now invites eligible consulting firms (“consultants”) to indicate their interest in providing the services. Interested consultants should provide information demonstrating that they have the required qualifications and relevant experience to perform the services. Interested firms should fill the template for expressions of interest and submit found at https://somalijobs.com/ and send it to the address indicated below.

The attention of interested consultants is drawn to IFAD’s Anti-Money Laundering and Countering the Financing of Terrorism Policy and the Revised IFAD Policy on Preventing Fraud and Corruption its Activities and Operations. The latter sets forth IFAD’s provisions on prohibited practices. IFAD further strives to ensure a safe working environment free of harassment, including sexual harassment, and free of sexual exploitation and abuse (SEA) in its activities and operations as detailed in its IFAD Policy to Preventing and Responding to Sexual Harassment, Sexual Exploitation and Abuse. By entering in this document, you certify to have read, understood, and agreed to be bound by the Privacy Policy of IFAD.

The consultant shall not have any actual, potential or reasonably perceived conflict of interest. A consultant with an actual, potential or reasonably perceived conflict of interest shall be disqualified unless otherwise explicitly approved by the Fund. A consultant including their respective personnel and affiliates are considered to have a conflict of interest if they a) have a relationship that provides them with undue or undisclosed information about or influence over the selection process and the execution of the contract, b) participate in more than one EOI under this procurement action, c) have a business or family relationship with a member of the Purchaser’s board of directors or its personnel, the Fund or its personnel, or any other individual that was, has been or might reasonably be directly or indirectly involved in any part of (i) the preparation of this REOI, (ii) the shortlisting or selection process for this procurement, or (iii) execution of the contract. The consultant has an ongoing obligation to disclose any situation of actual, potential or reasonably perceived conflict of interest during preparation of the EOI, the selection process or the contract execution. Failure to properly disclose any of said situations may lead to appropriate actions, including the disqualification of the consultant, the termination of the contract and any other as appropriate under the IFAD Policy on Preventing Fraud and Corruption in its Projects and Operations.

The following conflict of interest rules shall apply with respect to recruitment of government/client staff within the consultant’s proposed team:

(a)	No member of the client’s board of directors or current employees of the client (whether part time, or full time, paid or unpaid, in leave status, etc.) shall be proposed or work as, or on behalf of, any consultant.

(b)	No current employees of the government shall work as consultants or as personnel under their own ministries, departments or agencies.

(c)	Recruiting former client or government employees to perform services for their former ministries, departments or agencies is acceptable provided no conflict of interest exists.

(d)	If a consultant proposes any government employee as personnel in their technical proposal, such personnel must have written certification from the government confirming that: (i) they will be on leave without pay from the time of their official proposal submission and will remain on leave without pay until the end of their assignment with the consultant and they are allowed to work full-time outside of their previous official position; or (ii) they will resign or retire from government employment on or prior to the contract award date. Under no circumstances shall any individuals described in (i) and (ii) be responsible for approving the implementation of this contract. Such certification shall be provided to the client by the consultant as part of its technical proposal.

(e)    In the case where a consultant seeks to engage the services of any person, who may have left the client within a period of less than twelve (12) months of the date of this RFP, it must obtain a written “no-objection” from the client for the inclusion of such a person, prior to the consultant’s submission of its proposal.

A consultant will be selected in accordance with the based on Quality- and Cost-Based Selection (QCBS) set out in IFAD’ project procurement handbook that can be accessed via the IFAD website at www.ifad.org/project-procurement. The client will evaluate the EOIs using the criteria provided in Annex 2. The shortlisted consultant(s) will be provided with the detailed TORs and asked to submit a detailed technical and financial offer. The evaluation will include a review and verification of qualifications and past performance, including a reference check, prior to the contract award.

Consultants may associate with other firms to enhance their qualifications but should indicate clearly whether the association is in the form of a joint venture and/or a sub-consultancy. In the case of a joint venture, all the partners in the joint venture shall be jointly and severally liable for the entire contract, if selected.

The shortlisting criteria are

| Item | Criteria | Points |
| --- | --- | --- |
| i | Minimum five (5) years of professional experience in nutrition-sensitive agriculture orpost-harvest management orfood systems ornutrition education, or related community-based development programmes. | 30 |
| ii | Proven technical expertise in food handling, storage, processing, preservation, food safety, and nutrition-sensitive utilization of agricultural products. | 25 |
| iii | Experience working with rural communities in Somalia or similar fragile and conflict-affected contexts, including community mobilization and behavior change communication (BCC) approaches. | 25 |
| IV | Proven capacity to develop and deliver high-quality training curricula, facilitator manuals, participant guides, visual learning materials, and awareness materials in Somali and English | 20 |
|  | Total Points | 100 |
|  | Minimum points required to pass | 70 points |

Any request for clarification on this REOI should be sent via e-mail to the address below no later than 10:00 AM 09/07/2026 Somalia local time. The client will provide responses to all clarification requests by 12:00 PM 11/07/2026 Somalia local time.

Expressions of Interest, along with all supporting and requested documents (to demonstrate experience in line with the criteria outlined above), must be submitted in written form using the designated forms provided for this purpose.

EOIs shall be submitted to the address below no later than 10:00 AM 14/07/2026 Somalia local time.

Expressions of Interest that will be delivered via email the packages should be clearly marked: REF: SOM-2000004325-0145-CS-QCBS: Capacity Building on Nutrition-Sensitive Post-Harvest Practices.  Consultants must submit all documents in PDF format, compressed into a single password-protected ZIP or RAR file. password should be sent no later than 10:00 AM 14/07/2026 Somalia local time in a separate email to aabyan@rlrp.gov.so  and cc: amuhumad@rlrp.gov.so Submissions received after the deadline or without secure password transmission will be deemed non-compliant and rejected.

# Form EOI-1

# EOI Submission Form

To: Rural Livelihoods Resilience Program (RLRP)

Ministry of Agriculture and Irrigation MOAI

Federal Government of Somalia

Re: Capacity Building on Nutrition-Sensitive Post-Harvest Practices

Ref No: SOM-2000004325-0145-CS-QCBS

We, the undersigned, declare that:

- We are expressing our interest in providing the consulting services for the above-mentioned assignment and have no reservations to the REOI, the instructions to the consultants and any addenda thereto.

- Our expression of interest is open for acceptance for a period of ninety (90) days.

- Our firm, its associates, including any subcontractors or suppliers for any part of the contract, have not been declared ineligible by the Fund and have not been subject to sanctions or debarments under the laws or official regulations of the client’s country or not been subject to a debarment recognized under the Agreement for Mutual Enforcement of Debarment Decisions (the "Cross-Debarment Agreement"), beyond those declared in paragraph 9 of this EOI submission form.

- We acknowledge and accept the IFAD Revised Policy on Preventing Fraud and Corruption in its Activities and Operations. We certify that neither our firm nor any person acting for us or on our behalf has engaged in any prohibited practices as provided in ITC Clause 6. Further, we acknowledge and understand our obligation to report to anticorruption@ifad.org any allegation of prohibited practice that comes to our attention during the selection process or the contract execution.

- No attempt has been made or will be made by us to induce any other consultant to submit or not to submit an EOI for the purpose of restricting competition.

- We acknowledge and accept the IFAD Policy on Preventing and Responding to Sexual Harassment, Sexual Exploitation and Abuse. We certify that neither our firm nor any person acting for us or on our behalf has engaged in any sexual harassment, sexual exploitation or abuse. Further, we acknowledge and understand our obligation to report to ethicsoffice@ifad.org any allegation of sexual harassment, sexual exploitation and abuse that comes to our attention during the selection process or the contract execution.

- The following commissions, gratuities, or fees have been paid or are to be paid with respect to the selection process: [Insert complete name of each recipient, its full address, the reason for which each commission or gratuity was paid and the amount and currency of each such commission or gratuity.]

| Name of Recipient | Address | Reason | Amount | Currency |
| --- | --- | --- | --- | --- |

(If none has been paid or is to be paid, indicate “none.”)

- We declare that neither our consulting firm nor any of its directors, partners, proprietors, key personnel, agents, sub-consultants, sub-contractors, consortium and joint venture partners have any actual, potential or perceived conflict of interest as defined in ITC Clause 5 regarding this selection process or the execution of the contract. [insert if needed: “other than the following:” and provide a detailed account of the actual, potential or perceived conflict]. We understand that we have an ongoing disclosure obligation on such actual, potential or perceived conflicts of interest and shall promptly inform the client and the Fund, should any such actual, potential or perceived conflicts of interest arise at any stage of the procurement process or contract execution.

- The following criminal convictions, administrative sanctions (including debarments) and/or temporary suspensions have been imposed on our consulting firm and/or any of its directors, partners, proprietors, key personnel, agents, sub-consultants, sub-contractors, consortium and joint venture partners:

| Nature of the measure (i.e., criminal conviction, administrative sanction or temporary suspension) | Imposed by | Name of party convicted, sanctioned or suspended (and relationship to the consultant) | Grounds for the measure (i.e., fraud in procurement or corruption in contract execution) | Date and time (duration) of measure |
| --- | --- | --- | --- | --- |

If no criminal convictions, administrative sanctions or temporary suspensions have been imposed, indicate “none”.

- We acknowledge and understand that we shall promptly inform the client about any material change regarding the information provided in this EOI submission form.

- We further understand that the failure to properly disclose any of information in connection with this EOI submission form may lead to appropriate actions, including our disqualification as consultant, the termination of the contract and any other as appropriate under the IFAD Policy on Preventing Fraud and Corruption in its Projects and Operations.

- We understand that you are not bound to accept any EOI that you may receive.

| [Authorized signatory] |  |
| --- | --- |
| [Name and title of signatory] |  |
| [Name and address of firm] |  |

## Form EOI-2 
Organization of the Consultant

Re: Capacity Building on Nutrition-Sensitive Post-Harvest Practices

Ref No: SOM-2000004325-0145-CS-QCBS

[Provide a brief description of the background and organization of your firm/entity and of each associated firm for this assignment. Include the organization chart of your firm/entity. The EOI must demonstrate that the consultant has the organizational capability and to carry out the assignment. The qualifications document shall further demonstrate that the consultant has the capacity to field and provide experienced replacement personnel on short notice. Key staff CVs are not required at the shortlisting stage.]

| Name of the firm |  |
| --- | --- |
| Date of establishment |  |
| Country of registration |  |
| Full address of the firm |  |
| Focal point: name, position, contact information (telephone, email): | Name: |
|  | Tel: |
|  | Email: |
| Number of branches in the country |  |
| Country(ies) of operations with number of branches in each country |  |
| Number of full-time employees |  |
| Number of part-time employees |  |
| Field(s)of expertise of the firm |  |
| Number of professional staff with experience related directly to the assignment |  |
| Subsidiary and associated companies (wherever applicable): (details in the following format to be provided for all associates) – - Name of the company - Nature of business - Address of the company - Website of the company - Brief description of company (maximum of 120 words) |  |
| Any other information that the consultant would like to add: |  |

Maximum 10 pages

## Form EOI-3

## Experience of the Consultant

Re: Capacity Building on Nutrition-Sensitive Post-Harvest Practices

Ref No: SOM-2000004325-0145-CS-QCBS

[Using the format below, provide information on each relevant assignment for which your firm, and each associate for this assignment, was legally contracted either individually as a corporate entity or as one of the major companies within an association, for carrying out consulting services similar to the ones requested under the preliminary terms of reference included in this EOI. The EOI must demonstrate that the consultant has a proven track record of successful experience in executing projects similar in substance, complexity, value, duration, and volume of services sought in this procurement.

Maximum 20 pages]

| Assignment name: | Approx. value of the contract (in current US$): |
| --- | --- |
| Country: Location within country: | Duration of assignment (months): |
| Name of client: | Total No. of staff-months of the assignment: |
| Address, and contact details (including email address(es)): | Approx. value of the services provided by your firm under the contract (in current US$): |
| Start date (month/year): Completion date (month/year): | No. of professional staff-months provided by associated consultants: |
| Name of associated consultants, if any: | Name of proposed senior professional staff of your firm involved and functions performed (indicate most significant profiles such as project director/coordinator, team leader): |
| Narrative description of project: |  |
| Description of actual services provided by your staff within the assignment: |  |

Name of Firm: _________________________________

ANNEX 1

جـمـهــو رية الصـومـال الفيدراليه

وزارة الزراعه والري

JAMHUURIYADDA FEDERAALKA SOOMAALIYA

WASAARADDA BEERAHA & WARAABKA

Federal Republic of Somalia

Ministry of Agriculture & Irrigation

Rural Livelihoods Resilience Program (RLRP)

Terms of Reference for Consulting Services

For

Capacity Building on Nutrition-Sensitive Post-Harvest Practices

Ref No: SOM-2000004325-0145-CS-QCBS

- Background

# Somalia, situated in the Horn of Africa, is highly susceptible to the adverse impacts of climate change. The nation experiences recurrent and severe climate-related disasters, including prolonged droughts, devastating floods, and extreme temperature variations. These events have far-reaching consequences, affecting agricultural productivity, water availability, food security, and the overall livelihoods of millions of Somalis. Given the country's dependency on natural resources, the effects of climate change exacerbate existing vulnerabilities, making it imperative to build resilience across all sectors.

Despite gradual improvements in agricultural production across RLRP target areas, malnutrition and food insecurity remain persistent challenges, particularly among vulnerable rural households. A major contributing factor is not only limited access to food, but also significant post-harvest losses, poor food handling practices, and limited knowledge on nutrition-sensitive utilization of available produce. These challenges undermine household food availability, dietary diversity, and the nutritional status of women and children.

In Somalia, post-harvest losses of staple and nutrient-rich crops are exacerbated by inadequate storage facilities, unhygienic drying and processing methods, aflatoxin contamination risks, and weak household-level preservation practices. At the same time, limited awareness of balanced diets and appropriate food preparation methods reduces the nutritional benefits of food that is produced and consumed at household level.

The RLRP Nutrition Baseline Assessment (July 2025) provides the foundational evidence for this assignment. Conducted across the five target districts, the assessment established a comprehensive baseline of community knowledge, attitudes, and practices (KAP) related to nutrition. The findings reveal critical gaps across multiple domains and wide disparities between districts. District-specific KAP scores range from 65% in Afgoye, 56.12% in Bardere, 54.6% in Kismayo, and 44.4% in Baydhaba, to a critically low 15.29% in El Barde—far below the minimum acceptable threshold of 60%.

The assessment identified six critical gap areas that directly inform this assignment. In Infant and Young Child Feeding (IYCF), there is limited awareness of exclusive breastfeeding and appropriate complementary feeding practices, compounded by structural barriers including food insecurity and maternal workload. Micronutrient deficiencies are widespread, particularly in Iron, Vitamin A, and Iodine, with limited community understanding of deficiency symptoms and prevention. Food safety and hygiene practices are inadequate, characterised by poor food storage, limited awareness of aflatoxin risks, and unsafe food handling during preparation. Deeply entrenched cultural beliefs and taboos restrict consumption of nutrient-rich foods during pregnancy and lactation, while stigma against affordable nutritious foods—such as sorghum and beans being labeled as "poor man's food"—further constrains dietary diversity. Water, sanitation and hygiene (WASH) conditions are characterised by unsafe water sources, poor food hygiene, inadequate sanitation infrastructure, and systemic seasonal vulnerabilities. Gender dimensions are particularly pronounced, with women experiencing severe time poverty—spending 5.5 to 7 hours daily on farming and an additional 6 to 7 hours on domestic tasks—while being systematically excluded from decision-making regarding farm production, food purchases, and budget allocation.

The assessment concluded that nutrition interventions must be multi-sectoral, community-led, and context-specific, targeting the most vulnerable households with a package of complementary support. The wide disparity in KAP scores—from 65% in Afgoye to just 15.29% in El Barde—underscores the need for district-specific module prioritisation, with the most intensive interventions directed to the lowest-performing districts.

The RLRP recognizes that nutrition-sensitive agriculture must extend beyond production to include post-harvest handling, storage, processing, and utilization. This ToR therefore provides the framework for implementing Nutrition-Sensitive Post-Harvest Practices Training as a practical, community-based intervention that contributes directly to improved household nutrition, food safety, and resilience.

This activity directly contributes to RLRP logframe indicators:

- C.I. 1.1.8: Households provided with targeted support to improve their nutrition (target: 27,000 households)

- CI 1.2.9: Households with improved nutrition Knowledge Attitudes and Practices (KAP) (target: 10,500 households)

- 1.2.8: Women reporting minimum dietary diversity (MDDW) (target: 63,000 women)

- The Rural Livelihoods Resilience Programme

Rural Livelihoods Resilience Program is an 8-year program (March 2024 – March 2032). (RLRP)’s development objective is to sustainably increase productivity, incomes and nutrition security and enhance resilience of rural smallholder families in Somalia. It aims to address the challenges underlying the fragility of the agricultural sector in Somalia, e.g. vulnerability to climate change, perpetuating severe water scarcity, violent conflicts leading to displacement of farmers and inadequate access to food, poor access to rural and agricultural production infrastructure and services, limited access to skills training.

RLRP has three main components:

Component 1: Support to Community Resilience. Its expected outcomes are: Strengthened and inclusive communities with enhanced social cohesion so that they can define their livelihood development pathways and manage conflict.

Component 2: Support to Smallholder Livelihoods Enhancement. Its expected outcomes are: increased production and productivity of priority crops and animals for resilience, dietary diversity and food security; and improved incomes.

Component 3: Programme Coordination and Capacity Building. Its expected outcomes are an efficiently and effectively managed programme that integrates gender, youth, environment, climate change, monitoring and evaluation (M&E), knowledge management, and communication (KMC) considerations in all aspects of the programme.

- Objective of the Assignment:

To strengthen the capacity of RLRP beneficiaries and 50 vulnerable households per community across the five RLRP districts, particularly women, youth, community leaders, female members of producer groups and VSLAs, extension workers, and agrodealers/traders by enhancing their knowledge and skills in nutrition‑sensitive post‑harvest management, including food handling, storage, processing, preservation, and safe utilization, thereby improving household dietary diversity, reducing post‑harvest losses, and enhancing nutrition outcomes for women and children,

Specific Objectives

•	Conduct a Training Needs Assessment (TNA) for community and household level training.

•	Review existing curricula and tools from MoAI (Federal), Jubaland, and Southwest States as well as available and relevant FAO, WFP and UNICEF material.

•	Develop a comprehensive curriculum on Nutrition Sensitive Post Harvest Practices.

•	Prepare Facilitator Manuals and Participant Guides tailored to local contexts.

•	Deliver training in five RLRP districts to establish a pool of Master Trainers.

•	Build awareness on dietary diversity, food safety, and nutrition sensitive agriculture.

•	Reduce household level post-harvest losses through improved practices.

•	Promote gender responsive and child sensitive approaches to food utilization.

- Scope of work

Using the July 2025 RLRP Nutrition Baseline Assessment Report as the primary data source, and FAO/WFP/UNICEF's existing training modules :

- Adapt existing FAO/WFP/UNICEF and MoAI training materials for nutrition-specific BCC targeting vulnerable non-farmer households.

- Develop district-specific module prioritisation matrices based on baseline KAP scores:

- El Barde (15.29%): IYCF, WASH, basic dietary diversity

- Baydhaba (44.4%): IYCF, micronutrients, de-stigmatising nutritious foods

- Kismayo (54.6%): Iron and Vitamin A education, WASH

- Bardere (56.12%): Addressing food taboos, gender-responsive planning

- Afgoye (65%): Advanced topics only where CDPs indicate readiness

- Prepare Facilitator Manuals and Participant Guides in Somali and English, including visual aids, job aids, and pre-/post-assessment tools.

- Deliver Training of Trainers (ToT) for 120 community nutrition volunteers – 20-25 per district, prioritising women (minimum 70%), youth, IDPs, and PwD representatives.

- Deliver – through the community nutrition volunteers - community-based nutrition BCC sessions reaching 6,000 vulnerable individuals through the trained community nutrition volunteers. Each Master Trainer will train approximately 50 vulnerable individuals.

- Build awareness on dietary diversity, food safety, and nutrition-sensitive utilisation of available foods, using culturally appropriate messaging strategies from the baseline report.

- Promote gender-responsive and child-sensitive approaches to food utilization, directly addressing cultural taboos and gendered time-use gaps documented in the baseline report.

- Establish referral linkages between trained households and existing health/nutrition services and WFP's school feeding programme.

The consultant will not develop new post-harvest or storage training materials and will not conduct any new primary data collection. Instead, they will:

- Receive existing training modules from FAO/WFP/UNICEF and MoAI via RLRP NPCU.

- Review of the July 2025 RLRP Nutrition Baseline Assessment Report as the primary data source.

- Review relevant sections of validated CDPs for the 34 target communities.

- Conduct a participatory workshop with RLRP nutrition staff, WFP nutrition focal points, and CDP ICDC representatives to adapt existing materials.

Development of Adapted Training Materials

| Activity | Description |
| --- | --- |
| Review of Existing Materials | Assess FAO/WFP/UNICEF and MoAI materials for relevance to BCC for vulnerable non-farmer households |
| Materials Adaptation | Adapt existing materials to cover nutrition-specific modules; do not include post-harvest content |
| Materials Production | Develop Facilitator Manual, Participant Handbook, Visual Aids, Job Aids, Pre/Post Assessment Tools, and Cooking Demonstration Guides |

Nutrition-Specific Modules

| Module | Topic | Priority Districts |
| --- | --- | --- |
| 1 | Nutrition & Dietary Diversity | All districts |
| 2 | Infant and Young Child Feeding (IYCF) | All districts (critical for El Barde, Baydhaba) |
| 3 | Micronutrient Deficiencies | Kismayo, Baydhaba, El Barde |
| 4 | Water Safety and Hygiene (WASH) for Nutrition | All districts (critical for El Barde, Baydhaba) |
| 5 | Household Food Fortification | Afgoye, Bardere |
| 6 | Addressing Cultural Food Taboos | All districts (critical for Bardere, Kismayo, El Barde) |
| 7 | Gender-Responsive Meal Planning | All districts (critical for Kismayo, Bardere) |
| 8 | Utilisation of Biofortified Crops | Afgoye, Bardere |

Training Delivery

- Training of Trainers (ToT): Deliver ToT for 120 community nutrition volunteers (25 per district). Trainees selected from CDP ICDC nominations, prioritising women (minimum 70%), youth, IDPs, and PwDs.

- Community BCC Sessions: Trained volunteers deliver BCC sessions to 6,000 vulnerable individuals – approximately 50 individuals per trained volunteer.

- Use participatory methods – cooking demonstrations, role play, group discussions, visual aids.

- Do not deliver any post-harvest handling or storage training – this is WFP's responsibility.

Referral Linkages

Establish simple referral pathways between trained households and:

- Existing health/nutrition services (MCH posts, health facilities)

- WFP's school feeding programme for complementary food support

Reporting and Follow-Up

- Submit progress and final reports as per deliverables table.

- Include a 3-month post-training verification (phone-based or spot checks with 10% of trained individuals) to assess practice adoption.

- Document referral linkages.

Training Methodology

Training uses a participatory, gender-responsive, behaviour-change approach. Core methods include group discussions, practical cooking demonstrations, visual aids, role play, and case studies. Pre- and post-assessments measure learning progress.

Target Participants

| Training Level | Number | Selection Criteria |
| --- | --- | --- |
| Master Trainers (ToT for community nutrition volunteers) | 120 | CDP ICDC nominations; minimum 70% women; inclusion of youth, IDPs, PwDs; not farmers |
| End Beneficiaries | 6,000 | PLW, caregivers of under-2s, IDPs, PwDs; |
| Total direct beneficiaries | 6,120 |  |

Breakdown by District

| District | KAP Score | Master Trainers (ToT) | End Beneficiaries |
| --- | --- | --- | --- |
| El Barde | 15.29% | 25 | 1,250 |
| Baydhaba | 44.4% | 25 | 1,250 |
| Kismayo | 54.6% | 24 | 1,200 |
| Bardere | 56.12% | 24 | 1,200 |
| Afgoye | 65% | 22 | 1,100 |
| Total |  | 120 | 6,000 |

Reporting Training Conducted

- Work closely with the SPCU during field implementation and adhere to NPCU technical guidance, quality standards, and reporting requirements.

- Submitting timely and high-quality progress and final reports, documenting activities, outputs, challenges, and lessons learned.

- Summary of activities and methodologies used..

- Recommendations for follow-up actions and scaling of training initiatives.

Training Methodology

- Training uses a participatory, gender‑responsive, behaviour‑change approach.

- Core methods include group discussions, practical demonstrations, visual aids, and cooking demonstrations.

- Pre‑ and post‑assessments measure learning progress.

- Q&A and observation help explore causes, solutions, and shared understanding.

- Hands‑on group work includes demonstrations of fuel‑efficient stoves and recording key discussion points.

- Group presentations reinforce learning and encourage active participation.

- Brainstorming strengthens dialogue and idea generation.

- Case studies build real‑life problem‑solving skills.

- Role play helps participants understand household roles, decision‑making, and practical scenarios.

Target Participants

- Vulnerable rural households, with priority to women-headed households

- Youth involved in household food handling and processing

- Female members of producer groups and VSLAs

- Extension workers and agro-dealers/traders

- Community nutrition volunteers (where available)

Schedule of Deliverables

The activity will be implemented over 60 days, starting immediately after the signature of the contract in 5 RLRP districts. The implementation will follow a phased approach, including preparatory activities, community‑level awareness and training, supervision, and reporting. The sequencing of activities will be coordinated by the NPCU in collaboration with the SPCUs and relevant state ministries to ensure timely delivery and quality assurance.

| # | Deliverable | Timeline |
| --- | --- | --- |
| 1 | Inception report with a detailed work plan. | 10 days after contract signing |
| 2 | Training needs assessment and curriculum approved by RLRP | 15 days |
| 3 | Training materials with handouts, PPT and training facilitation | 10 days |
| 4 | Training report with attendance lists disaggregated by gender and age, detailed training sessions, outcomes and lessons learned, plus photographs | 25 days |
|  | Total | 60 Days |

F. Support from the MoAI and RLRP

Ministry of Agriculture and Irrigation (MoAI)

The Ministry of Agriculture and Irrigation (MoAI) shall provide overall policy guidance and technical oversight for the activity to ensure alignment with national priorities and standards. Specifically, MoAI will:

- Provide policy directions to ensure the training is consistent with national nutrition, food safety, and post-harvest management guidelines.

- Offer technical oversight to ensure the content and delivery of the training reflects nutrition-sensitive agriculture principles.

- Support identification of target sites and communities in coordination with state- and district-level authorities.

- Facilitate community mobilization through existing agricultural extension and nutrition structures.

- Provide ongoing technical backstopping during implementation, including participation in selected training sessions and review of technical materials.

Rural Livelihoods Resilient Programme (RLRP)

#### RLRP shall be responsible for overall management, supervision, and quality assurance of the assignment.

#### Key responsibilities include:

- Leading the procurement and contracting process for the consulting firm in accordance with RLRP and IFAD procedures.

- Ensure technical quality and consistency of the training with RLRP standards.

- Review and approve training materials, progress reports, and final deliverables.

- Monitor results and outputs to ensure the activity meets programme objectives and performance indicators.

- Consolidate lessons learned and ensure integration into broader RLRP nutrition-sensitive interventions

- Provide day-to-day supervision of field-level implementation.

- Coordinate with local authorities, extension staff, and community structures.

- Monitor training delivery, participation, and adherence to agreed schedules.

- Support resolution of operational and logistical issues during implementation.

G. Required Qualifications

The selected firm shall possess the following qualifications:

 Minimum five (5) years of professional experience in nutrition-sensitive agriculture, post-harvest management, food systems, nutrition education, or related community-based development programmes.

 Proven technical expertise in food handling, storage, processing, preservation, food safety, and nutrition-sensitive utilization of agricultural products.

 Experience working with rural communities in Somalia or similar fragile and conflict-affected contexts, including community mobilization and behavior change communication (BCC) approaches.

 Proven capacity to develop and deliver high-quality training curricula, facilitator manuals, participant guides, visual learning materials, and awareness materials in Somali and English

Key Personnel

#### 1. Team Leader / Nutrition and Post-Harvest Specialist (Key Expert 1)

Qualifications and Experience

- Bachelor's degree in Nutrition, Food Science, Post-Harvest Technology, Agriculture, Public Health, or a related field.

- Minimum seven (7) years of professional experience in nutrition-sensitive agriculture, food systems, post-harvest management, nutrition education, or related fields.

Responsibilities

- Lead and coordinate overall implementation of the assignment.

- Supervise the Training Needs Assessment (TNA) and curriculum development process.

- Ensure technical quality of all training materials and deliverables.

- Lead stakeholder consultations and coordinate with MoAI and RLRP.

- Prepare inception, progress, and final reports.

#### 2. Training and Community Mobilization Specialist (Key Expert 2)

Qualifications and Experience

- Bachelor's degree in Agricultural Extension, Rural Development, Community Development, Education, or a related field.

- Minimum five (5) years of experience in adult learning, community mobilization, and training delivery.

Responsibilities

- Support the Training Needs Assessment and community consultations.

- Facilitate training sessions and practical demonstrations.

- Coordinate participant mobilization and stakeholder engagement.

- Support development of training manuals, visual aids, and awareness materials.

- Ensure inclusive participation of women, youth, and vulnerable households.

#### 3. Nutrition and Behaviour Change Communication (BCC) Specialist (Key Expert 3)

Qualifications and Experience

- Bachelor's degree in Nutrition, Public Health, Social Sciences, Behaviour Change Communication, or a related field.

- Minimum five (5) years of experience in nutrition education, dietary diversity promotion, food safety, and community awareness programmes.

Responsibilities

- Lead development of nutrition education content and behaviour change messages.

- Provide technical input on dietary diversity, food safety, IYCF, micronutrient deficiencies, and food utilization modules.

- Support training delivery and participant assessments.

- Contribute to monitoring learning outcomes and documenting lessons learned.

- Ensure nutrition and gender considerations are integrated throughout the assignment.

H. Reporting and Coordination

The consultant shall report to the National Program Coordinator/Nutrition and Social Inclusion Specialist  and work closely with RLRP State Coordinators and District Officers.

The SP will be responsible for providing their own office space, transport, equipment, and training materials and logistics. This includes, meeting venues in the communities, notebooks, pens, flipcharts and marker pens for the group work.

They will be expected to deploy a technically competent team with the required expertise and ensure that all tools, software, and resources for data collection, analysis, and reporting are available. It is expected that the SP already possesses this equipment and software and therefore it should not be included in the proposal cost.

I. Payment Schedule

Payment shall be issued only after the assignment has been completed and the deliverables have been reviewed and accepted by the RLRP Coordinator.

ANNEX 2

Qualification and Evaluation Criteria

| Item | Criteria | Points |
| --- | --- | --- |
| i | Minimum five (5) years of professional experience in nutrition-sensitive agriculture or post-harvest management orfood systems or nutrition education, or related community-based development programmes. | 30 |
| ii | Proven technical expertise in food handling, storage, processing, preservation, food safety, and nutrition-sensitive utilization of agricultural products. | 25 |
| iii | Experience working with rural communities in Somalia or similar fragile and conflict-affected contexts, including community mobilization and behavior change communication (BCC) approaches. | 25 |
| IV | Proven capacity to develop and deliver high-quality training curricula, facilitator manuals, participant guides, visual learning materials, and awareness materials in Somali and English | 20 |
|  | Total Points | 100 |
|  | Minimum points required to pass | 70 points |

This document refers to legally constituted consulting firms as “consultant”.

The policy is accessible at https://www.ifad.org/en/document-detail/asset/41942012.

The policy is accessible at www.ifad.org/anticorruption_policy.

The policy is accessible at https://www.ifad.org/en/document-detail/asset/40738506.

The policy is accessible at https://www.ifad.org/en/privacy.

The Cross-Debarment Agreement was entered into by the World Bank Group, the Inter-American Development Bank, the African Development Bank, the Asian Development Bank and the European Bank for Reconstruction and Development, additional information may be located at: http://crossdebarment.org/.