Request for Proposal

[REQUIREMENT DESCRIPTION]

Third-party Evaluation TOR - GAC 5 Project (Banadir  Galgaduud)

RFP DOCUMENT # [__38730____]____]

RFP Issue Date:  22-02-2026]

Proposal submission Deadline :  [07-03-2026]

CARE USA

151 Ellis Street NE

Atlanta, GA 30303-2440

Confidential Document

Prepared by

CARE ®

Table of Contents

1.	ABOUT CARE	2

2.	GENERAL CONDITIONS and CLAUSES	2

2.1.    	CARE’s GENERAL CONDITIONS	2

2.2.	CONFIDENTIALITY/ NON-DISCLOSURE	3

2.3.	PUBLICITY	3

2.4.	LIABILITY	3

2.5.	FORCE MAJEURE	3

2.6.	ERRORS AND OMISSIONS	4

2.7.	OWNERSHIP OF WORK	4

2.8.	CONFLICT OF INTEREST	4

3.	COMPANY PROFILE & BIDDER’S DECLARATION	5

3.1.	COMPANY PROFILE	5

3.2.	BIDDER’S DECLARATION	6

4.	CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL	7

4.1.	PROPOSOSAL GUIDELINES	7

4.2.	PROJECT PURPOSE AND DESCRIPTION	7

4.3.	PROJECT OVERVIEW	8

4.4.	PROJECT REQUIREMENTS	9

4.5.	PROJECT TIMELINE	11

4.6.	EVALUATION CRITERIA	11

# ABOUT CARE

At CARE, we seek a world of hope, inclusion, and social justice, where poverty has been overcome and people live with dignity and security.

This has been our vision since 1945, when we were founded to send lifesaving CARE Packages® to survivors of World War II. Today, CARE is a leader in the global movement to end poverty. We put women and girls in the center because we know we cannot overcome poverty until all people have equal rights and opportunities. In 2019, CARE worked in 100 countries and reached 70 million people with an incredible range of life-saving programs.

To know more about CARE, visit: https://www.care.org/our-work/

# GENERAL CONDITIONS and CLAUSES

# CARE’s GENERAL CONDITIONS

The enclosed document is not an offer to contract, but a solicitation of a vendor’s proposed intent.  Acceptance of a proposal in no way commits CARE to award a contract for any or all products and services to any vendor.

CARE reserves the right to make the following decisions and actions based on its business interests and for reasons known only to CARE:

- To determine whether the information provided does or does not substantially comply with the requirements of the RFP

- To contact any bidder after proposal submittal for clarification of any information provided.

- To waive any or all formalities of bidding

- To accept or reject a proposal in whole or part without justification to the bidder

- To not accept the lowest bid

- To negotiate with one or more bidders in respect to any aspect of submitted proposal

- To award another type of contract other than that described herein, or to award no contract;

- To enter into a contract or agreement for purchase with parties not responding to this RFP

- To request, at its sole discretion, selected Vendors to provide a more detailed presentation of the proposal

- To not share the results of the bids with other bidders and to award contracts based on whatever is in the best interest of CARE.

Any material statements made orally or in writing in response to this RFP or in response to requests for additional information will be considered offers to contract and should be included by vendor in any final contract.

# CONFIDENTIALITY/ NON-DISCLOSURE

All information gained by any vendor concerning CARE work practices is not to be disclosed to anyone outside those responsible for the preparation of this proposal.  Any discussion by the vendor of CARE’s business practices could be reason for disqualification.  CARE, at their discretion, reserves the right to require a non-disclosure agreement.

Reciprocally, CARE commits that information received in response to this RFP will be held in strict confidence and not disclosed to any party, other than those persons directly responsible for the evaluation of the responses, without the express consent of the responding vendor.

Finally, the information contained within this RFP is confidential and is not to be disclosed or used for any other purpose by the vendor.

# PUBLICITY

Any publicity referring to this project, whether in the form of press releases, brochures, or photographic coverage will not be permitted without prior written approval from CARE.

# LIABILITY

The selected vendor(s) will be required to show proof of adequate insurance at such time as CARE is prepared to procure the services.  The participating vendor will also be required to indemnify and hold harmless CARE for, among other things, any third-party claims arising from the selected vendor’s acts or omissions, and will be liable for any damage caused by its employees, agents or subcontractors.

# FORCE MAJEURE

- Neither Party shall be responsible for a performance that is delayed, hindered, or is rendered inadvisable, commercially impracticable, illegal, or impossible by a “Force Majeure Event.” A Force Majeure event includes, without limitation, an act of nature, a pandemic, emergency, civil unrest or disorder, actual or threatened terrorism, war, fire, governmental action or interference of any kind, power or utility failures, strikes or other labor disturbances, a health warning issued by the Center for Disease Control (or similar agency), any other civil or governmental emergency and/or any other similar event beyond a Party’s reasonable control.

- The Party that seeks to invoke this Force Majeure provision (the “Affected Party”) shall provide the other Party (the “Unaffected Party”) with a written notice within ten (10) days of the date the Affected Party determines a Force Majeure Event has occurred.

# ERRORS AND OMISSIONS

CARE expects the vendor will provide all labor, coordination, support, and resources required based on the vendor’s proposal and corresponding final SOW.  No additional compensation will be available to the vendor for any error or omission from the proposal made to CARE.  The only exclusions are add-ons, deletions, and/or optional services for which the vendor has received written authorization from CARE.

# OWNERSHIP OF WORK

All work created during this evaluation must be original work, and no third party should hold any rights in or to the work.  All rights, title and interest in the work shall be vested in CARE.

# CONFLICT OF INTEREST

CARE encourages every prospective Supplier to avoid and prevent conflicts of interest, by disclosing to CARE if you, or any of your affiliates or personnel, were involved in the preparation of the requirements, design, specifications, cost estimates, and other information used in this RFP.

# COMPANY PROFILE & BIDDER’S DECLARATION

Bidders are requested to complete this form, including the Company Profile and Bidder’s Declaration, sign it and return it as part of your proposal. No alterations to its format shall be permitted and no substitutions shall be accepted.

# COMPANY PROFILE

Table 4.1.A Previous Work with CARE

| Have you already had previous transactions with CARE? | Yes | No |
| --- | --- | --- |
| If marked “Yes”, please provide the year of the latest transaction with CARE and the requirement that was delivered. (This is to inform everyone that this information is for system checking only. This will not be part of any evaluation process.) |  |  |
| If you marked, “No” on the table above, please answer the Table 4.1.A. below: |  |  |

Table 4.1.B Other Information

| Item Description | Detail(s) |
| --- | --- |
| Legal name of bidder |  |
| Legal Address, City, Country |  |
| Website |  |
| Year of Registration |  |
| Company Expertise |  |
| Bank Information (Please answer below) |  |
| Bank Name: |  |
| Bank Address: |  |
| IBAN: |  |
| SWIFT/BIC: |  |
| Account Currency: |  |
| Bank Account Number: |  |

| Previous relevant experience: 3 contracts |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name of previous contracts | Client & Reference Contact Details | Contract Value | Period of activity | Types of activities undertaken |

# BIDDER’S DECLARATION

| Yes | No |  |
| --- | --- | --- |
|  |  | Ethics: By submitting this Proposal/Quote, I/we guarantee that the bidder has not engaged in any improper, illegal, collusive, or anti-competitive arrangements with any competitors; has not directly or indirectly contacted any buyer representative (aside from the point of contact) or gather information regarding the RFP; and has not attempted to influence or offer any type of personal inducement, reward, or benefit to any buyer representative. |
|  |  | I/We affirm that we will not engage in prohibited behavior or any other unethical behavior with CARE or any other party. We also affirm that we have read the general clause and conditions included in this RFP and that we will conduct business in a way that avoids any financial, operational, reputational, or other undue risk to CARE. |
|  |  | Conflict of interest: I/We warrant that the bidder has no actual, potential or perceived Conflict of Interest in submitting this Proposal/Quote; or entering into a Contract to deliver the Requirements. CARE Procurement's Point of Contact will be notified right away by the bidder if a conflict of interest occurs during the RFP process. |
|  |  | Bankruptcy: l/We have not declared bankruptcy, are not involved in bankruptcy or receivership proceedings, and there is no judgment or pending legal issues that could hinder the ability to conduct business. |
|  |  | Offer Validity Period: I/We confirm that this Proposal/Quote, including the price, remains open for acceptance for the Offer Validity. |
|  |  | I/We understand and recognize that you are not bound to accept any proposal you receive, and we certify that the goods offered in our Quotation are new and unused. |
|  |  | By signing this declaration, the signatory below represents, warrants and agrees that he/she has been authorized by the Organization/s to make this declaration on its/their behalf |

| Supplier Name: |  |
| --- | --- |
| Title/Designation: |  |
| Company Name: |  |
| Date: |  |
| Signature |  |

# CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL

# PROPOSOSAL GUIDELINES

This Request for Proposal represents the requirements for an open and competitive process.

All vendors must provide written notification via email to (som.consultant@care.org) of their intent to participate, or not to participate in the bidding process by [07-march-2026

.

Proposals will be accepted until 07-Marhc-2026 delivered via email solely to som.consultant@care.org, no later than the above specified date.

Any proposals received after this date and time will not be accepted.  All proposals must be signed by an official agent or representative of the company submitting the proposal.

If the organization submitting a proposal must outsource or contract any work to meet the requirements contained herein, this must be clearly stated in the proposal.  Additionally, all costs included in proposals must be all-inclusive to include any outsourced or contracted work.  Any proposals which call for outsourcing or contracting work must include a name and description of the organizations being contracted.

All costs must be itemized to include an explanation of all fees and costs.

Contract terms and conditions will be negotiated upon selection of the winning bidder for this RFP.  All contractual terms and conditions will be subject to review by the CARE legal department, and will include scope, budget, schedule, and other necessary items pertaining to the project.

You must respond to every subsection including statement, question, and/or instruction without exception.

Any verbal information obtained from, or statements made by representatives of CARE shall not be construed as in any way amending this RFP.  Only such corrections or addenda as are issued in writing by CARE to all RFP participants shall be official.  CARE will not be responsible for verbal instructions.

# PROJECT PURPOSE AND DESCRIPTION

CARE is issuing this RFP (Request for Proposal) soliciting qualified bidders to submit proposals intended for the [ToThird-party Evaluation TOR - GAC 5 Project (Banadir  Galgaduud)].

This RFP is an invitation to bid, not an offer of contract.  Bidders must submit a response that complies with the minimum requirements contained herein.

# PROJECT OVERVIEW

CARE is seeking a provider to submit proposals intended for the [provide requirement description]

Terms of Reference (TOR) for third-party Monitoring of the Multi-Sectoral Humanitarian Response Targeting IDPs, Returnees and Host Communities in Somalia (2024-2026) - CARE Somalia, GAC Project

## 1. Background

Somalia remains entrenched in one of the world's most severe and protracted humanitarian crises, now significantly exacerbated by compounding and under-resourced shocks. Unrelenting cycles of extreme flooding, escalating localized conflict, and severe environmental shocks (including the long-term impact of past locust infestations and persistent, intensifying drought conditions) continue to destroy livelihoods and overwhelm local response capacity.

Humanitarian estimates indicate that nearly 6 million people require urgent assistance. This pressure is accelerating displacement, adding to the estimated 4 million people already living in a state of protracted internal displacement (IDPs), many of whom reside in overcrowded camps with insufficient basic services.

Critical Humanitarian Indicators

The cumulative impact of this crisis has led to severe deterioration across critical sectors:

- Nutrition: The country is on the brink of a nutrition catastrophe. An estimated 1.85 million children under five are projected to suffer from acute malnutrition, including approximately 421,000 cases of Severe Acute Malnutrition (SAM), the most life-threatening form. This worsening crisis is concentrated in rural areas and IDP sites and is being compounded by cuts to vital humanitarian funding for therapeutic services.

- Health: Somalia’s already fragile health system is struggling to cope with the high prevalence of malnutrition and a constant cycle of infectious disease outbreaks, including recurrent cholera, measles, and diphtheria. Climatic shocks, especially flooding and water scarcity, fuel the transmission of these diseases, leading to a critical malnutrition-disease feedback loop that disproportionately impacts children and contributes to one of the world's highest maternal mortality rates. Access to essential health services is extremely limited, particularly for IDPs and those in remote, conflict-affected areas.

- Protection: The crisis has severely exacerbated the pre-existing vulnerabilities of women and girls, leading to heightened risks of Gender-Based Violence (GBV), including sexual violence and exploitation, particularly in congested IDP settlements. Children are at the epicentre of the protection crisis, facing risks of family separation, recruitment by armed groups, psychosocial trauma, and the erosion of community-based protection mechanisms due to funding shortfalls. Tenure insecurity for IDPs also remains a major protection concern, with evictions increasing the vulnerability of already displaced families.

CARE is a humanitarian non-governmental organization committed to working with poor women, men, boys, girls, communities, and institutions to have a significant impact on the underlying causes of poverty. CARE seeks to contribute to economic and social transformation, unleashing the power of the most vulnerable women and girls.

  - Project Overview

CARE, in partnership with SSWC, is implementing a multi-country, multi-sectoral initiative that will reach 90,459 individuals, including IDPs, returnees, and host communities, in the Galgaduud and Banadir regions of Somalia. The project aligns with Canada’s Feminist International Assistance Policy (FIAP) through its strong focus on gender equality, human dignity and the protection of vulnerable populations.

The response employs a gender-responsive, survivor-cantered approach to mitigate acute threats to life and health, prioritizing the needs of women, girls, and vulnerable groups (including PWD and adolescents). Key interventions include:

- Health: Rehabilitating facilities, training gender-balanced teams, and providing essential services, including Reproductive Maternal and Newborn Child Health (RMNCH) and the Minimum Initial Service Package (MISP), with a focus on SRHR integration and Clinical Management of Rape (CMR).

- Nutrition: Implementing Outpatient Therapeutic Feeding (OTP) and Targeted Supplementary Feeding Programs (TSFP) for acute malnutrition, alongside community-based Maternal, Infant, and Young Child Feeding in Emergencies (MIYCN-E) support.

- Protection (SGBV): Establishing Women and Girls’ Safe Spaces (WGSS) informed by risk analysis, offering MHPSS, case management, referrals for CMR and other essential services. . The project also i engages men and boys in GBV prevention and provides Multi-Purpose Cash Transfers (MPCT) in Somalia to meet acute needs.

Project Outcomes expected results:

| Level | Outcome Title | Description | Target Groups & Locations |
| --- | --- | --- | --- |
| Ultimate Outcome | Increased Equitable Use of Services | Increased equitable use of gender-sensitive primary healthcare, especially Sexual Reproductive Health and Nutrition (iSRHN), as well as protection/SGBViE services. | Women and girls, Persons with Disabilities (PWD), host communities, Internally Displaced Persons (IDPs) and returnees in Somalia (Galgaduud and Banadir Regions). |
| Immediate Outcome 1 | Health | Enhanced, timely and equitable access to lifesaving health services, including SRH. This includes training health providers to offer gender-sensitive & inclusive services. | Vulnerable women, girls, boys, men, and PWD. |
| Immediate Outcome 2 | Nutrition | Increased and more equitable access to gender-sensitive nutrition services, including diagnosis, treatment and prevention. | Children under 5 (U5) and Pregnant and Lactating Women and Girls (PLWG). |
| Immediate Outcome 3 | Protection | Enhanced, timely, and equitable access to survivor-centred Sexual and Gender-Based Violence (SGBV) response services and SGBV risk mitigation. | Vulnerable women, girls, boys, men and PWD in Galgaduud and Banadir regions. |

# 3. Objectives of the Third-Party Monitoring (TPM)

The primary objective of this Third-Party Monitoring (TPM) assignment is to independently verify reported project implementation progress and service delivery quality from October 2024 to present. The TPM will provide objective, evidence-based verification of activities, outputs, and early results while the project is under implementation.

Drawing on independent field monitoring, document review, and stakeholder validation. TPM will assess whether project activities are being implemented as planned and in line with agreed standards, with particular attention to equitable access, service quality, and adherence to gender-sensitive and survivor-centered approaches across Health, Nutrition, and Protection interventions.

This Third-Party Monitoring (TPM) assignment serves as an independent accountability and verification mechanism for the project. The purpose of the TPM is to:

- Independently verify reported implementation progress by triangulating internal project reporting with third-party field monitoring, document review, and stakeholder validation, to strengthen the accuracy, credibility, and transparency of reported outputs and activities.

- Confirm implementation quality and adherence to agreed standards by assessing whether project activities are being implemented as planned, in line with agreed technical approaches, targeting criteria, coordination arrangements, and gender-sensitive and survivor-centered principles, informed by relevant OECD-DAC concepts - relevance, effectiveness, coherence, and equity/gender equality applied strictly from an implementation monitoring and verification perspective.

- Support implementation oversight and adaptive management by providing practical, evidence-based observations and recommendations to address identified gaps, risks, or implementation bottlenecks and to improve service delivery during ongoing implementation.

The TPM will result in a verification-focused report presenting validated findings on implementation status, service delivery quality, and compliance with agreed project approaches. Findings will be shared with Global Affairs Canada (GAC), relevant coordination structures, and CARE teams for accountability purposes and to inform ongoing project management and decision-making.

# 4. Key Monitoring and Verification Questions

The Third Part Monitoring will be guided by the following questions

| Category | TPM Questions |
| --- | --- |
| Performance & Achievement | - Progress Verification: Based on current output data, what is the variance between actual reach and planned targets for October 2024 to the present? - Quality of Services and Beneficiary Satisfaction: To what extent do beneficiaries report satisfaction with the safety, adequacy, accessibility, and inclusiveness of the services provided, and how is beneficiary feedback systematically used to inform adaptive management and final-phase project implementation? |
| Relevance & Effectiveness (Health & Nutrition) | - To what extent did the project increasing the equitable use of integrated Sexual Reproductive Health and Nutrition (SRHN) services among target populations (women, girls, IDPs, PWD)? - What implementation evidence is available regarding uptake of key health services include antenatal care (ANC), facility delivery, family planning, and management of common illnesses) based on routine service data and verification findings? - To what extent is the nutrition component (OTP/TSFP/MIYCN-E) contributing to early detection and treatment of acute malnutrition in children under five (U5) and PLWG? - What are the operational and access barriers (as identified in the baseline, gender analysis and other studies) remain evident during implementation, and how are these being addressed within current project modalities? |
| Food Security & Basic Needs | - Progress toward Food Security: To what extent is the project delivering planned food security and Multi-Purpose Cash Assistance (MPCA) support in line with targeting and implementation plans? - Protection-Integrated Support: How effectively has the project targeted protection-supported beneficiaries to ensure they have the financial means to access food and essential services without resorting to negative coping mechanisms? |
| Protection & Inclusion | - Access and coverage: to what extent the project delivering timely and equitable access to SGBViE response service for vulnerable population (women, girls, men, boys and PWDs) - Service Quality & Survivor-Centred Approach: To what extent were protection and SGBV services being delivered in line with survivor-centred, confidential, and culturally appropriate manner, as perceived by service providers and community stakeholders? - Risk Mitigation: To what extent did the project’s protection and risk mitigation measures contribute to reducing safety and protection risks associated with accessing services (including health, nutrition, and cash assistance)? - Inclusion: how effectively did the project identify and address barriers to access for persons with disabilities, IDPs, returnees, adolescents, and other at-risk groups? - Integrated approach: To what extent did integration across sectors (health, nutrition, protection) contribute to reducing protection risks and barriers to access, particularly for women, girls, IDPs, and persons with disabilities? - Accessibility and safety: To what extent do the WGSS function as intended, providing safe, accessible and appropriate entry points for GBV and protection response services? |
| Implementation Observations & Practical Considerations | - What key implementation observations emerge from the third-party monitoring related to service delivery, access, coordination, and inclusion across sectors? - What practical considerations and good practices can be identified to support ongoing project implementation and management, including addressing observed gaps or risks? |

# 5. Approach and Methodology

Third Part Monitoring (TPM) assignment will verify reported implementation progress and service delivery using a mixed-methods approach, informed by available baseline information and routine monitoring data (including joint supervisions, project progress reports and PDM reports) where applicable to support verification of reported results and implementation status over the project period.

- The TPM will draw on both quantitative and qualitative data, collected through beneficiary/household surveys, document and secondary data reviews, FGDs, and KII with project staff, implementing partners, service providers and relevant community and coordination  stakeholders.

- A verification-focused analysis will be employed to compare reported outputs and activities against available monitoring data and selected indicator values with the aim of validating consistency, coverage, and service delivery quality.

The technical support team is expected to propose an appropriate and comprehensive monitoring and verification methodology, detailing the proposed approach, sampling strategy, data analysis methods, presentation and reporting framework, and ethical considerations.

Primary data collection related to SGBV will not involve direct interviews with survivors. Analysis will rely on anonymized service data, key informant interviews, and community-level perspectives, in line with ethical guidelines for GBV-sensitive monitoring and research.

# 6. Scope of Monitoring

The TPM will be conducted in the Adaado and Banadir districts of Galgaduud and Banadir regions, specifically focusing on locations where project activities were implemented. Participants will include Project supported IDPs, returnees, host communities, PWDs, as well as relevant government authorities and partner (SSWC) engaged in project implementation and coordination.

# 7. Responsibilities

a) Responsibilities of CARE

CARE will be responsible for the overall coordination and facilitation of the Third-Party Monitoring (TPM) assignment. Specifically, CARE will:

- Provide overall guidance to the TPM service provider, including the approved Terms of Reference (ToR), reporting templates, and relevant technical guidance.

- Provide the CARE-approved data collection system/platform to be used for TPM data collection.

- Review and approve the TPM methodology, data collection instruments, and digitized tools prior to deployment.

- Provide access to relevant project documentation, routine monitoring data, indicator reference sheets, and reporting requirements necessary for verification purposes.

- Facilitate access to project locations, implementing partners, service providers, and relevant government and coordination stakeholders, as appropriate.

- Support the TPM team during field data collection through coordination and facilitation, while maintaining the independence of the monitoring and verification process.

- Review and provide input on the draft TPM report, and review and approve the final TPM verification report.

- Lead dissemination of TPM findings to GAC and other relevant stakeholders.

b) Responsibilities of the PM Service Provider / Consultant

The TPM service provider will be responsible for the overall planning, implementation, and delivery of the Third-Party Monitoring (TPM) assignment, in line with this ToR and agreed timelines. The TPM service provider will independently verify project implementation progress, service delivery quality, and reported results through systematic data collection, analysis, and triangulation.

Specifically, the TPM service provider will:

- Develop a TPM-focused methodology and verification work plan, including sampling, data quality assurance, and ethical safeguards, for CARE’s review and approval.

- Design, digitize, and finalize data collection tools using the CARE-provided data collection system/platform, in line with approved indicators and methodology.

- Undertake a desk-based review of relevant project documentation and routine monitoring data, and lead field-level data collection in line with the approved TPM methodology.

- Recruit, train, deploy, and manage enumerators responsible for primary data collection, ensuring adherence to approved tools, protocols, and ethical standards.

- Conduct primary data collection, including surveys, key informant interviews, focus group discussions, and field verification visits, as appropriate.

- Analyze collected data alongside secondary data and project documentation to validate reported outputs, coverage, and service delivery quality.

- Ensure strict compliance with safeguarding, protection, and GBV-sensitive monitoring standards, including the exclusion of direct interviews with SGBV survivors.

- Conduct debriefings with CARE to validate preliminary findings prior to final reporting.

- Prepare and submit draft and final TPM verification reports in accordance with agreed timelines, formats, and reporting requirements.

# 8. Key Deliverables

The TPM deliverables are:

- TPM Inception Note:

- Detailed Monitoring and verification methodology.

- Sampling approach and work plan.

- Data collection methodology and tools.

- Draft TPM Report:

- A draft report addressing the monitoring and verification questions identified in the ToR.

- CARE will provide comments within 2 working days, and the consultant will submit a revised final draft within 2 working days of receiving feedback from CARE.

- Final TPM Report:

- Final TPM verification report incorporating CARE’s comments.

- A short presentation summarizing key findings.

- Submission of Dataset(s) to the Development Data Library:

- Submission of the report in a machine-readable, non-proprietary format.

- Submission of all data collection tools, raw and cleaned data sets (Qualitative and Quantitative), generated codebooks and syntaxes (SPSS/STATA), qualitative codebook, audio types, transcriptions and translations, photos, and GPS Coordinates for all sampled locations.

# 9. Duration of the Assignment

The duration of the assignment is 20 working days after the signing of the contract (including weekends). This is inclusive of traveling, fieldwork, and reporting. The assignment is expected to take place from 1st – 20th March , 2026.

| Activity | Time Frame |
| --- | --- |
| Inception Meetings | 1 |
| Inception note and development of data collection tools | 2 |
| Review and finalization of Inception note | 2 |
| Field Data collection/monitoring including enumerator training | 6 |
| Data analysis and draft report preparation | 4 |
| Review of TPM report | 2 |
| Final report submission and presentation of findings | 3 |
|  | 20 |

# 10. Qualification of the Consultant

The TPM will be conducted by an external consultant/s (team or individual) with vast experience in performing third-party monitoring, verification, or monitoring assignments for similar GAC-funded projects and a strong understanding of the Somalia/Somaliland context. The consultant/s must demonstrate expertise and experience directly relevant to the core sectors of this project: Health, Nutrition, and Protection (SGBViE), in addition to general humanitarian and monitoring qualifications.

Key Qualifications:

- Humanitarian Experience: 10 years’ international humanitarian and development experience, particularly in the Somalia context.

- Proven humanitarian monitoring and evaluation experience, demonstrating the ability to see the big picture and make practical recommendations.

- Standards: Strong experience and knowledge in the application of humanitarian standards like SPHERE and Core Humanitarian Standards (CHS).

- Demonstrated understanding of gender, protection, and gender-based violence (GBV) considerations in humanitarian monitoring, including adherence to ethical, survivor-centred principles and established guidance for GBV-sensitive research, without direct engagement with survivors.

- Methodology: Good understanding of integrated approaches to programming.

- Contextual Knowledge: Strong knowledge and experience in the Somalia context (teams including Somali speakers are desirable).

- Data Skills: Ability to absorb, consolidate, analyze, and communicate large amounts of data and information simply and concisely.

- Logistics & Security: Experience and ability to operate in security volatile environments. Willingness to travel to Somalia under the CARE international security framework.

Essential Sector-Specific Expertise

| Sector | Required Expertise |
| --- | --- |
| Health | - Strong knowledge of the drivers of poor health in the Somalia context. - Proven experience in monitoring, verification, or assessment health programs, particularly those including Sexual and Reproductive Health and Rights (SRHR), Reproductive Maternal and Newborn Child Health (RMNCH), and Clinical Management of Rape (CMR) components. |
| Nutrition | - Strong knowledge of the drivers of malnutrition in the Somalia context. - Proven experience in monitoring, verification, or assessment of nutrition programs nutrition programs, including Outpatient Therapeutic Feeding (OTP), Targeted Supplementary Feeding Programs (TSFP), and Maternal, Infant, and Young Child Feeding in Emergencies (MIYCN-E). |
| Protection (SGBViE) | - Demonstrated experience in monitoring or assessing Gender-Based Violence (GBV) and SGBV programming, including survivor-centered approaches, case management system, and the establishment and functioning of Women and Girls’ Safe Spaces (WGSS). - Experience assessing the implementation and functionality of SGBV risk mitigation measures, referral pathway and service integration, using ethical, non-intrusive monitoring approaches that do not involve direct interviews with survivors.• |
| Cross-Cutting (CVA) | - Solid experience and understanding of Cash and Voucher Assistance (CVA) and its inter-connectedness to other sectors, especially food security, nutrition, and protection |

# 11. Consultant Hiring – Award Criteria

Consultants will be evaluated based on key qualifications, relevant experience, and technical capability and will be considered the Best Price Quality Ratio approach. The award will balance technical quality and cost to ensure the most advantageous overall value.

Evaluation Components

- Technical Proposal (Quality) – Assesses experience, methodology, team expertise, and work plan (typically the highest weight).

- Financial Proposal (Cost) – Reviews total fees and cost realism; important but not the sole deciding factor.

Scoring Categories

- Firm Experience – Relevant past projects and organizational capacity.

- Methodology & Work Plan – Technical approach, understanding of scope, and timeline.

- Key Personnel – Qualifications and direct experience of assigned experts.

- Local Knowledge – Familiarity with local regulations and context.

- Fees & Expenses – Overall cost and budget suitability.

Scoring Matrix

| Category | Key Evaluation Factors | Weight (%) |
| --- | --- | --- |
| Firm Experience | Track record in similar sectors; years in operation; references. | 30% |
| Methodology | Understanding of ToR; innovation in approach; realistic timeline. | 25% |
| Key Personnel | CVs of lead experts; academic background; specific project roles. | 20% |
| Local Knowledge | Regional presence; understanding of local laws/stakeholders. | 5% |
| Financial | Total cost; fee transparency; alignment with market rates. | 20% |
| Total Score |  | 100% |

Selection Methods

- QCBS (Quality- and Cost-Based Selection) – Weighted technical and financial scores (standard method).

- QBS (Quality-Based Selection) – Highest technical score selected, then fee negotiated.

- LCS (Least-Cost Selection) – Lowest price among technically compliant proposals with required qualification.

- FBS (Fixed-Budget Selection) – Best technical proposal within a predefined budget.

Administrative Requirements

Consultants must meet minimum eligibility criteria, including legal registration, tax compliance, required insurance, absence of conflicts of interest, and minimum years of operation. Failure to comply may result in disqualification.

# How to apply:

All applications MUST be accompanied by a technical and financial proposal including a brief outline of the proposed TPM methodology and approach, 3 references with contacts and a tentative work plan as well as the candidate’s availability during the months of March 2026. The proposals shouldn’t exceed 5 pages. Deadline for submission of technical and financial proposals is 07th March2026.

Interested consultants or firms are expected to conduct their own security and accessibility of the target project locations before application. Updated CVs of individuals or profile of applying company expressing interest to conduct the assessment should be sent to Mark. Som.consultant@care.org

Please indicate “Third-Party Monitoring (TPM) GAC Project’’.

[Provide additional requirements]

| Item # | Other Requirements |  |
| --- | --- | --- |
| 1 | Delivery Date & Time | Bidder shall deliver the goods at least ____ weeks after Contract signature. |
| 2 | Delivery Terms (incoterms) | EXW [Ex-works (Place)] |
|  |  | FCA [Free Carrier (Port)] |
|  |  | FAS [Free Along-Side Ship (Port)] |
|  |  | FOB [Free On-Board (Port)] |
|  |  | CFR [Cost, & Freight (Port)] |
|  |  | CIF [Cost, Insurance & Freight (Port)] |
|  |  | CPT [Carriage Paid-To (Place)] |
|  |  | CIP [Carriage & Insurance Paid-To (Place)] |
|  |  | DAP [Delivered at Place (Place)] |
|  |  | DPU [Delivered at Place Unloaded (Place)] |
|  |  | DDP [Delivered Duty Paid (Place)] |
| 3 | Custom Clearance (Must be linked to Incoterms at origin) | Not Applicable. Shall be done by _______________ |
|  |  | Shouldered by CARE |
|  |  | Supplier/ Bidder |
|  |  | Freight Forwarder |
| 4 | Exact Address(es) of Delivery Location | Banadir and Galmudug |
| 5 | Warranty Period | Standard Manufacturer’s Warranty (if applicable) |
| 6 | Payment Terms | 30 Days upon Receipt of items |
| 7 | Quotation Validity | The quote needs to be valid for 90 days to cover all the days from bidding up to the award process. However, once the contract has been released, it shall be valid for the same coverage as reflected in the requirement above. |

[Provide additional requirements]

# PROJECT TIMELINE

All bidders are advised to strictly follow the below timeline as noted.

Any technical questions arising during the preparation of your response to this RFP should be submitted in writing via email to AhmedAli.Mohamed@care.org no later than [05-03-2026.

| Schedule of Activities/ To-do | Date of the Activity/ Deadline of Submission | Responsible | Remarks |
| --- | --- | --- | --- |
| RFP Issued | 07-03-2026 | CARE |  |
| Supplier to notify CARE of intention to participate in bidding |  | Supplier | Deadlines must be strictly observed. |
| Deadline for submission of clarification questions to CARE | 01-03-2026 | Supplier | Deadlines must be strictly observed. |
| CARE to answer all clarifications | 05-03-2026 | CARE |  |
| Supplier’s Deadline of Submission of Proposal | 07-03-2026 | Supplier | Deadlines must be strictly observed. |
| Evaluation of Proposal |  | CARE |  |
| Vendor presentation (if required) |  | Supplier |  |
| Finalists selected |  | CARE | Upon notification, the contract negotiation with the winning bidder will begin immediately. |

# PROJECT REQUIREMENTS

- Technical Requirements

a.1 Technical Proposal of the Product

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Overall Proposal Suitability |  |  |
| 1 | Please see the Scope of Work and any other required specifications for this project. |  |
| 2 | Provide Delivery Lead Time |  |
| 3 | Provide after-sales service (if applicable) |  |
|  | (Any additional requirement that is deemed necessary for “Previous Works & Awards” Category |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Previous Works and Awards |  |  |
| 1 | Provide 3 or more client experiences or testimonials (References whose environment, size, and scope are most similar to CARE. Include a summary of the work completed for each account. Include reference contact names, with telephone numbers and email addresses.) |  |
| 2 | Provide previous records of performance and service. |  |
| 3 | Provide citations and awards. This encompasses reviewing the citations and awards a vendor has received from other customers and award-giving bodies. |  |
| 4 | Provide any testimonials, survey response/s from previous buyers and/or partners. |  |
| 5 | (Any additional requirement that is deemed necessary for “Previous Works & Awards” Category. |  |

| EQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Technical Expertise and Organizational Experience |  |  |
| 1 | Provide 5 Availability of vendor’s representatives to call upon and consult with. |  |
| 2 | Any proof that the vendor has the Ability to render satisfactory service in this instance. |  |
| 3 | Provide Years of experience in providing the same requirement to other companies. |  |
| 4 | Provide the latest report alight with TOR assigment |  |
| 5 | (Any additional requirement that is deemed necessary for “Technical Expertise and Organizational Experience. |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Others |  |  |
| 1 | Provide any relative requirements which were not mentioned above. (delete if not applicable) |  |

- VALUE & COST (Financial Requirements)

(Provide below requirements, payment terms, etc., if there’s any)

See attached template (in Excel File) to be used for your financial bid.

Compliance with Requirements

|  | Yes, we will comply | No, we cannot comply | If marked as “No”, please provide counter proposal |
| --- | --- | --- | --- |
| Minimum Technical Specifications |  |  |  |
| Delivery Lead Time |  |  |  |
| Delivery Term (INCOTERMS) |  |  |  |
| Warranty Period (if applicable) |  |  |  |
| Validity of Quotation |  |  |  |
| Payment Terms (30 Days) |  |  |  |
| Other Requirements (Please specify) |  |  |  |

Scoring Categories

- Firm Experience – Relevant past projects and organizational capacity.

- Methodology & Work Plan – Technical approach, understanding of scope, and timeline.

- Key Personnel – Qualifications and direct experience of assigned experts.

- Local Knowledge – Familiarity with local regulations and context.

- Fees & Expenses – Overall cost and budget suitability.

Scoring Matrix

| Category | Key Evaluation Factors | Weight (%) |
| --- | --- | --- |
| Firm Experience | Track record in similar sectors; years in operation; references. | 30% |
| Methodology | Understanding of ToR; innovation in approach; realistic timeline. | 25% |
| Key Personnel | CVs of lead experts; academic background; specific project roles. | 20% |
| Local Knowledge | Regional presence; understanding of local laws/stakeholders. | 5% |
| Financial | Total cost; fee transparency; alignment with market rates. | 20% |
| Total Score |  | 100% |

Note for Country Offices (CO): The specific criteria must closely represent the objective and scope given the nature of the procurement required. Evaluation criteria reflected above can be added and or adjusted depending on the requirement and the type of purchase. The final evaluation criteria must be reflected above prior to releasing of this RFP.

CARE will review proposed budgets and pricing after the initial review of the criteria above.*