TERMS OF REFERENCE (TOR)

Menstrual Health and Hygiene (MHH) Education and Awareness Sessions for Adolescent Girls and Teaching Staff:

Background:

The project aims to improve the well-being, participation, confidence, and agency of adolescent girls by addressing barriers related to Menstrual Health and Hygiene (MHH). Limited access to accurate menstrual health information, appropriate menstrual hygiene knowledge, and supportive school environments can negatively affect girls’ attendance, participation, confidence, and overall learning experience.

As part of the project, MHH education and awareness activities will be implemented in selected project-supported schools to strengthen adolescent girls’ knowledge, confidence, and ability to manage menstruation safely and with dignity. The intervention will also strengthen the capacity of teaching staff to provide accurate, supportive, and age-appropriate information and to create a safe and non-judgmental environment for adolescent girls.

The intervention will target 400 adolescent girls, particularly girls in the relevant upper primary grades, and will include structured MHH education sessions for adolescent girls and orientation sessions for selected teaching staff.

This assignment is strictly limited to the preparation and delivery of MHH education and orientation sessions. It does not include the procurement, provision, establishment, stocking, or distribution of dignity kits, menstrual hygiene materials, or MHH kits.

Purpose of the Assignment:

The purpose of this assignment is to engage a qualified service provider/consultant to design and facilitate effective, participatory, age-appropriate, and culturally appropriate MHH education sessions for adolescent girls and orientation sessions for selected teaching staff.

The assignment will support the project by:

- Increasing adolescent girls’ knowledge and understanding of menstruation and menstrual hygiene.

- Strengthening girls’ confidence and ability to manage menstruation safely, hygienically, and with dignity.

- Improving girls’ understanding of puberty, personal hygiene, menstrual health, and available sources of support.

- Addressing common myths, misconceptions, stigma, and harmful practices related to menstruation.

- Improving teachers’ knowledge and capacity to provide accurate, supportive, and age-appropriate MHH information.

- Promoting a safe and supportive school environment where menstruation can be discussed without stigma or discrimination.

- Measuring changes in participants’ knowledge and confidence through appropriate pre- and post-session assessments.

Specific objectives:

The assignment will aim to:

- Deliver comprehensive, age-appropriate, and participatory MHH education sessions to 400 adolescent girls in selected project-supported schools (Mjeex &Sanaag).

- Conduct orientation sessions for selected teaching staff on MHH and appropriate support for adolescent girls.

- Strengthen girls’ knowledge of menstruation, puberty, menstrual hygiene, personal hygiene, and available support services.

- Address myths, misconceptions, stigma, and harmful practices related to menstruation.

- Strengthen girls’ confidence and ability to manage menstruation safely and with dignity.

- Provide girls with safe opportunities to ask questions and discuss MHH-related concerns.

- Strengthen teachers’ capacity to respond appropriately to girls’ questions and concerns.

- Promote gender-sensitive, inclusive, culturally appropriate, and safeguarding-compliant approaches to MHH education.

- Conduct pre- and post-session assessments to measure changes in knowledge and confidence.

- Document the sessions, participation, key findings, challenges, lessons learned, and recommendations.

Scope of Work:

The selected service provider/consultant will be responsible for the preparation and delivery of MHH education and orientation sessions.

- Preparation and Planning

The service provider/consultant will:

- Develop an inception/work plan outlining the proposed methodology, session schedule, target schools, participant groups, and implementation approach.

- Review and adapt MHH education materials to ensure that they are age-appropriate, culturally appropriate, gender-sensitive, inclusive, and suitable for the target context.

- Develop or finalize appropriate facilitation materials and session plans.

- Coordinate with the Project Manager/Project Team and participating schools to agree on the implementation schedule.

- Ensure that all facilitators involved in the sessions understand safeguarding, confidentiality, child protection, and appropriate engagement with adolescent girls.

B. MHH Education Sessions for Adolescent Girls

The service provider/consultant will conduct structured and participatory MHH education sessions for 400 adolescent girls.

Sessions should cover, as appropriate:

- Understanding menstruation and the menstrual cycle.

- Puberty and the physical and emotional changes associated with adolescence.

- Menstrual hygiene and personal hygiene.

- Safe and hygienic menstrual management practices.

- Common menstrual concerns and appropriate responses.

- Myths and misconceptions related to menstruation.

- Menstrual stigma and ways to address it.

- Confidence, dignity, and positive attitudes towards menstruation.

- When and where to seek support for menstrual health concerns.

- Available support mechanisms within the school and community.

- Questions and concerns commonly experienced by adolescent girls.

The sessions should use participatory approaches, including:

- Interactive discussions.

- Question-and-answer sessions.

- Small-group activities.

- Practical demonstrations where appropriate.

- Visual and age-appropriate learning materials.

- Scenario-based discussions and exercises.

- Confidential opportunities for questions and feedback.

C. Orientation Sessions for Teaching Staff

The service provider/consultant will conduct orientation/training sessions for selected teaching staff and relevant school personnel.

The sessions will strengthen teachers’ capacity to:

- Understand MHH and the common challenges faced by adolescent girls.

- Understand puberty and menstruation from an age-appropriate and supportive perspective.

- Provide accurate and appropriate MHH information.

- Respond appropriately to girls’ questions and concerns.

- Provide a supportive, respectful, and non-judgmental environment.

- Identify girls who may require additional support and refer them through appropriate channels where relevant.

- Maintain confidentiality and respect for girls’ privacy.

- Address stigma, misconceptions, teasing, and discrimination related to menstruation.

- Promote a safe and supportive school environment for adolescent girls.

D. Pre- and Post-Session Assessment

The service provider/consultant will:

- Develop or use an appropriate pre-session assessment to establish participants’ baseline knowledge and understanding.

- Conduct post-session assessments to measure changes in knowledge and confidence.

- Ensure that assessment tools are age-appropriate and easy for adolescent participants to understand.

- Analyze and summarize the assessment results.

- Include key findings in the final activity report.

E. Participant Feedback and Learning

The service provider/consultant will:

- Provide opportunities for participants to provide feedback on the sessions.

- Capture key questions, concerns, and learning points raised during the sessions.

- Identify areas where additional information or support may be required.

- Documented lessons learned and recommendations for future MHH education activities.

Target Group:

The primary target groups will be:

- 400 adolescent girls in selected project-supported schools, particularly girls in the relevant upper primary grades.

- Selected teaching staff and relevant school personnel.

Where appropriate, school management and designated focal persons may be engaged to support the successful implementation of the sessions.

Parents/caregivers and the wider school community are not direct participants under this assignment unless specifically agreed with the Project Team as part of the MHH awareness approach.

Key Deliverables:

The primary target groups will be:

- inception/work plan outlining the methodology, timeline, target schools, participant groups, and implementation approach.

- MHH education/session materials appropriate for adolescent girls and teaching staff.

- MHH education sessions delivered to 400 adolescent girls.

- Teacher orientation/training sessions completed for designated teaching staff.

- Pre- and post-session assessment tools and results measuring changes in knowledge and confidence.

- Attendance and participation records for all sessions.

- Participant feedback and session documentation.

- Summary of key questions, learning points, challenges, and recommendations.

- Final activity report documenting activities conducted, participants reached, key achievements, assessment results, challenges, lessons learned, and recommendations.

- Photographic documentation where appropriate and only where informed consent and safeguarding requirements are fully met.

Methodology:

The service provider/consultant should use a participatory, girl-centered, inclusive, and interactive methodology.

The methodology should include:

- Interactive discussions.

- Question-and-answer sessions.

- Small-group activities.

- Practical demonstrations were appropriate.

- Visual and age-appropriate learning materials.

- Scenario-based learning and discussions.

- Pre- and post-session assessments.

- Safe spaces for girls to ask questions confidentially.

- Participant feedback mechanisms.

The approach should be:

- Gender-sensitive.

- Culturally appropriate.

- Age-appropriate.

- Inclusive.

- Disability-sensitive.

- Child-friendly.

- Safeguarding-compliant.

- Respectful of confidentiality and privacy.

The service provider should use a participatory and girl-centered methodology, including:

- Interactive discussions.

- Question-and-answer sessions.

- Small-group activities.

- Demonstrations were appropriate.

- Visual and age-appropriate learning materials.

- Pre- and post-assessments.

- Safe spaces for girls to ask questions confidentially.

- Feedback mechanisms to capture girls’ experiences and recommendations.

- The approach should be gender-sensitive, culturally appropriate, inclusive, disability-sensitive, and safeguarding-compliant.

The service provider/consultant should ensure that the sessions are conducted in a manner that encourages participation and avoids reinforcing stigma, shame, discrimination, or harmful misconceptions related to menstruation.

Safeguarding and Ethical Considerations:

All activities involving adolescent girls must comply with the organization's safeguarding, child protection, prevention of sexual exploitation and abuse (PSEA), confidentiality, and informed-consent requirements.

The service provider must:

- Ensure a safe, respectful, and child-friendly environment for all participants.

- Avoid collecting unnecessary personal information.

- Maintain confidentiality of sensitive information shared during sessions.

- Obtain appropriate consent/assent for participation and documentation, as required.

- Ensure that photographs or videos of girls are only taken with the required consent.

- Ensure that all personnel working directly with children/adolescents understand and comply with safeguarding requirements.

- Use appropriate and respectful language when discussing menstruation and puberty.

- Avoid practices that could embarrass, stigmatize, or expose individual girls.

- Immediately report any safeguarding concerns through the established reporting mechanisms.

Coordination and Supervision:

The service provider/consultant will:

- Work closely with the Project Manager/Project Team.

- Coordinate with relevant MEAL staff as required.

- Coordinate with participating schools and designated schools’ focal persons.

- Coordinate with relevant government stakeholders where appropriate.

- Ensure that the agreed implementation schedule is followed.

- Provide regular updates to the Project Team on progress and any implementation challenges.

The Project Team will provide overall technical oversight and coordinate with participating schools and relevant authorities.

The service provider/consultant will be responsible for day-to-day planning and implementation of the assigned MHH sessions and will provide regular updates to the Project Team.

Duration and Location:

- The assignment will be implemented over an agreed period within the project implementation timeframe.

- The activities will take place in the selected project-supported schools in the target regions/districts.

- The detailed implementation schedule will be agreed upon between the service provider and the project team before commencement.

Required Qualifications and Experience:

The service provider/consultant should have:

- Relevant academic qualifications in public health, nursing, midwifery, gender, education, social sciences, or a related field.

- Demonstrated experience in Menstrual Health and Hygiene (MHH) programming.

- Experience delivering adolescent-focused health or hygiene education.

- Experience working with schools, teachers, and adolescent girls.

- Strong facilitation and communication skills.

- Understanding of gender, safeguarding, child protection, and adolescent participation.

- Experience in developing training/education materials.

- Experience in conducting pre- and post-training assessments and preparing activity reports.

- Experience working in humanitarian/development contexts is desirable.

Reporting:

The service provider will submit:

- Inception/work plan before implementation.

- Finalized MHH session materials.

- Attendance and activity records after each session/activity.

- Pre- and post-session assessment results.

- Participant feedback and key learning points.

- Summary of challenges and lessons learned.

- Final narrative/activity report summarizing implementation, results, achievements, assessment findings, challenges, lessons learned, and recommendations.

Expected Outcome:

By the end of the assignment, 400 adolescent girls are expected to have improved knowledge, confidence, and understanding of menstruation and menstrual hygiene and to feel more able to manage menstruation safely and with dignity.

Teaching staff are expected to have improved knowledge and capacity to provide accurate, supportive, and age-appropriate MHH information and to respond appropriately to girls’ questions and concerns.

The intervention will contribute to creating a more supportive and inclusive school environment for adolescent girls and help reduce barriers related to menstrual stigma, misinformation, and lack of awareness that may affect their regular attendance, participation, confidence, and engagement in education.

TECHNICAL EVALUATION AND SCORING CRITERIA

Proposals will be evaluated against the criteria below. The maximum technical score is 80 marks. Bidders/consultants should provide clear evidence against each criterion in their technical proposal.

| No. | Evaluation Criterion | Assessment / Evidence Required | Maximum Marks |
| --- | --- | --- | --- |
| 1 | Relevant Academic Qualifications | Relevant academic qualifications in public health, nursing, midwifery, gender, education, social sciences, or a related field. Candidates with demonstrated expertise in girls’ education, adolescent girls’ development, gender equality, or addressing barriers to girls’ school attendance, retention, and participation will also be considered. | 10 |
| 2 | MHH Experience and Technical Expertise | Demonstrated experience in Menstrual Health and Hygiene (MHH) programming, including knowledge of menstruation, menstrual hygiene, puberty, stigma, myths and misconceptions, and adolescent-focused MHH education. Relevant experience in girls’ education, adolescent development, gender, child protection, or working directly with adolescent girls will also be considered, particularly where the applicant demonstrates a strong understanding of girls’ educational needs, participation, confidence, and retention. | 20 |
| 3 | Experience with Adolescents and Schools | Relevant experience working with adolescent girls, schools, teachers, and education stakeholders, including experience in girls’ education, adolescent development, life skills, health/hygiene education, gender, child protection, or related programmes. The applicant should demonstrate an understanding of adolescent girls’ learning needs, confidence, participation, wellbeing, and barriers to education and retention, particularly among upper-primary girls | 10 |
| 4 | Proposed Methodology and Approach | Quality relevance, and practicality of the proposed methodology for delivering participatory, girl-centered, age-appropriate, culturally appropriate, inclusive, disability-sensitive, and interactive sessions. The approach should demonstrate understanding of adolescent girls’ needs and barriers to education, school attendance, retention, and participation, and include appropriate pre/post assessments, safe and confidential participation, practical activities, and feedback mechanisms | 15 |
| 5 | Safeguarding, Child Protection and Gender Sensitivity | Demonstrated understanding and application of safeguarding, child protection, PSEA, confidentiality, informed consent/assent, privacy, gender-sensitive approaches, and safe spaces for adolescent girls, including awareness of gender-related risks, protection concerns, and barriers that may affect adolescent girls’ participation, wellbeing, school attendance, and retention. | 10 |
| 6 | Facilitation, Communication and Training Materials | Demonstrated facilitation, communication, and training skills, including the ability to develop and/or adapt age-appropriate, girl-centered, culturally relevant, and adolescent-friendly MHH education materials. Ability to deliver engaging, interactive, and inclusive sessions and communicate effectively with adolescent girls, teachers, parents/caregivers, and relevant education stakeholders, with sensitivity to barriers affecting girls’ education, participation, and retention. | 5 |
| 7 | Reporting, Assessment and Documentation Capacity | Demonstrated experience in conducting pre- and post-session assessments, analyzing and interpreting results, documenting participation and feedback, and preparing clear, concise, and evidence-based activity/final reports. Ability to capture and report on adolescent girls’ learning, knowledge, confidence, participation, and key barriers related to MHH, school attendance, retention, and engagement. | 5 |
| 8 | Relevant Humanitarian/Development Context Experience | Demonstrated experience implementing similar assignments in humanitarian or development contexts, particularly in Somaliland or comparable settings, with experience working with adolescent girls, schools, teachers, communities, and relevant education or health stakeholders. Experience addressing MHH, girls’ education, gender-related barriers, school attendance, retention, and participation in resource-constrained or vulnerable settings will be an advantage. | 5 |
|  | TOTAL TECHNICAL SCORE |  | 80 |

Submission Information / How to Apply

Please send your complete technical and financial proposals, to this email address som.consultant@care.org clearly marking the subject line (Menstrual Health and Hygiene (MHH) Education and Awareness Sessions for Adolescent Girls and Teaching Staff)

no later than 22th October 2026 11:59 PM.