# Terms of Reference for the Provision of Competency-Based Climate-Smart Agriculture (CSA) Training for 60 Youth through an Accredited TVET Centre in Hargeisa, Somaliland

| Date of issue: | August 05,2026 |
| --- | --- |
| Project title: | Badbaado: Skills for Resilience and Green Economy in Somaliland |
| Deadline for submission of offers: | 18, 2026, 3:30 PM EAT. |
| Contracting authority: | FCA Somalia Country Office Contact: Procurement Committee E-mail: Procurement.Soco@kua.fi |

## Introduction & Background

FCA Somaliland is implementing the Badbaado – Skills for Resilience and Green Economy in Somaliland Project, which aims to enhance livelihoods, improve employment opportunities, and strengthen resilience among vulnerable youth and women through market-oriented skills development. The project supports the development of green skills by promoting competency-based vocational training that responds to labor market needs and equips young people with technical, environmental, entrepreneurship, and employability skills for employment and self-employment opportunities.

As part of this project, FCA will engage an accredited TVET Centre to deliver Competency-Based Climate-Smart Agriculture and Waste Management training to sixty (60) unemployed youth in Hargeisa. The training will combine classroom-based learning, practical hands-on training, demonstration activities, field-based learning, entrepreneurship, financial literacy, Career Guidance and counselling (CGC), and environmental sustainability practices to enhance participants’ capacity to access employment opportunities and establish climate-resilient livelihood activities.

To strengthen the quality and relevance of the program, FCA will engage a separate FCA-appointed Climate-Smart Agriculture Curriculum Consultant to review the existing agriculture modules and competency-based training modules currently used by the selected TVET Centre. The consultant will identify module gaps and integrate Climate-Smart Agriculture principles, technologies, climate resilience, environmental sustainability, resource-efficient production systems, and labor market requirements into the reviewed modules.

The selected TVET Centre shall actively participate throughout the module review process by providing existing curricula, training materials, lesson plans, assessment tools, and technical inputs. The TVET Centre shall participate in module review workshops, validate revised training modules, and adopt the approved curriculum/ modules for program delivery. Responsibility for modules review and revision shall remain with the FCA-appointed consultant, while responsibility for implementation of the approved training module shall rest with the selected TVET Centre.

The training will align with the Ministry of Education and Science TVET standards and integrate FCA's cross-cutting priorities on Gender Equality and Social Inclusion (GESI), safeguarding, environmental sustainability, accountability, and private-sector engagement.

## Background info on FCA

FCA is Finland's largest international development and humanitarian organization and a member of the ACT Alliance. FCA works in fragile and conflict-affected contexts to promote human dignity, resilience, and sustainable development through quality education, sustainable livelihoods, peacebuilding, and humanitarian assistance.

FCA has been implementing programs in Somaliland since 2007 in close collaboration with government institutions, local communities, civil society organizations, technical training institutions, and private sector actors.

## Background info on FCA SOCO requesting the services

Somaliland continues to experience high youth unemployment, climate variability, prolonged droughts, land degradation, and declining agricultural productivity. These challenges disproportionately affect young women and men, limiting access to sustainable employment and income-generating opportunities. At the same time, growing investments in irrigation, horticulture, greenhouse farming, and climate-resilient agricultural systems have increased the demand for skilled agricultural technicians.

Recognising these opportunities, the Badbaado Project promotes Climate-Smart Agriculture (CSA) as one of its core green economy sectors. The project supports competency-based vocational training that equips youth with practical technical skills required by employers and enables graduates to establish climate-resilient agribusiness enterprises. The project also supports the integration of green skills into the national TVET system through collaboration with relevant government institutions and accredited TVET providers.

The training will primarily contribute to Activity 1.2.3 (Climate-Smart Agriculture Training) while integrating complementary modules on financial literacy, entrepreneurship, career guidance and waste management to strengthen employability outcomes. Under this activity, FCA intends to engage an accredited TVET Centre to deliver competency-based Climate-Smart Agriculture training for 60 unemployed youth in Hargeisa. Ppriority will be given to vulnerable youth, including IDPs and persons with disabilities

The programme will combine classroom instruction, practical training, demonstration farm activities, field visits, entrepreneurship development, financial literacy, and waste management training to improve participants' employability and self-employment opportunities.

The training will adopt Competency-Based Training (CBT) principles and comply with the standards of the Ministry of Education and Science, TVET Department, while incorporating FCA's cross-cutting priorities on Gender Equality and Social Inclusion (GESI), safeguarding, environmental sustainability, accountability, and private-sector engagement.

## Objectives

The overall objective of this assignment is to engage an accredited TVET Centre to deliver high-quality Competency-Based Climate-Smart Agriculture (CSA) training to 60 unemployed youth in Hargeisa, Somaliland, enabling them to acquire practical technical competencies, entrepreneurship skills, and workplace experience that improve their employability and capacity for self-employment within the green economy.

## Specific Objectives

The selected TVET Centre shall:

- Deliver a competency-based Climate-Smart Agriculture training programme for 60 youth over 2 months.

- Facilitate practical hands-on training using demonstration farms, greenhouses, irrigation systems, and agricultural production sites.

- Build participants' competencies in climate-resilient agricultural production technologies and sustainable natural resource management.

- Strengthen participants' entrepreneurship, agribusiness management, financial literacy, and employability skills.

- Conduct competency-based assessments and certify successful trainees.

- Promote gender equality, disability inclusion, environmental sustainability, safeguarding, and accountability throughout programme implementation.

## Scope of work

The selected TVET Centre shall be responsible for planning, coordinating and delivering competency-based Climate-Smart Agriculture (CSA) training for sixty (60) unemployed youth in Hargeisa. The assignment shall be implemented in close collaboration with FCA, the Ministry of Education and Science (TVET Department), the FCA-appointed Climate-Smart Agriculture Curriculum Consultant, relevant government institutions.

The TVET Centre shall provide qualified trainers, training facilities, demonstration sites, training materials, administrative and logistical support, coordination, competency-based assessments, reporting, and all technical services necessary for successful implementation of the assignment.

The scope of work shall include, but not be limited to, the following activities:

| Phase | Activity/Responsibilities of the TVET Center. | Key Deliverables |
| --- | --- | --- |
| Phase I: Inception, Planning and Coordination | - Prepare a detailed implementation work plan, implementation schedule and training calendar. - Support the beneficiary selection process together with FCA and MoES. - Submit an Inception Report within five (5) working days after contract signing. | - Approved Inception Report. and Implementation work plan. |
| Phase II: Curriculum Review and Training Preparation | - FCA shall engage a FCA-appointed Climate-Smart Agriculture Curriculum Consultant to review and strengthen the existing curriculum and competency-based training modules. - The TVET Centre shall: provide existing curricula, lesson plans, trainer guides and assessment tools. - Participate in curriculum review and validation workshops. - Provide technical feedback on draft materials. - Adopt the curriculum approved by FCA and the Ministry of Education and Science. - Update lesson plans, participant manuals and trainer guides accordingly | - Updated training package based on the approved curriculum/ modules. - Revised lesson plans and training materials |
| Phase III: Training Preparation | - Prepare classrooms, practical fields and demonstration farms. - Prepare greenhouse facilities, irrigation systems, nursery sites and composting demonstration areas. - Prepare training materials, practical and PPE. - Prepare attendance registers, and assessment tools. - Ensure facilities are accessible to women and persons with disabilities | Fully equipped and operational training facilities ready for training implementation |
| Phase IV: Delivery of Competency-Based Climate-Smart Agriculture Training | - The training shall cover approved competency units related to Climate-Smart Agriculture, sustainable agricultural production, water and soil management, greenhouse production, irrigation technologies, composting, agricultural waste management, integrated pest management, agribusiness, entrepreneurship, financial literacy, occupational safety, environmental sustainability and workplace readiness. | Sixty (60) unemployed youth successfully complete the competency-based CSA training programme |
| Phase VI: Assessment, Certification and Reporting | - Conduct competency-based assessments throughout training implementation using continuous assessment, practical demonstrations, assignments, written and oral examinations. - Maintain assessment records. - Prepare progress and final reports. - Conduct the final exam and issue certificates in accordance with the national TVET certification framework. | - Assessment records and monthly Progress reports. - Final implementation report. - Certificates issued to successful trainees |
| Phase VII: Cross-Cutting Responsibilities | Throughout implementation, the TVET Centre shall integrate Gender Equality and Social Inclusion (GESI), disability inclusion, environmental sustainability, climate resilience, Occupational Health and Safety (OHS), FCA Code of Conduct, and integrated waste management, including waste reduction, segregation, recycling, composting of biodegradable agricultural waste, and environmentally safe disposal of agricultural and hazardous waste generated during training activities, also the financial literacy and digital financing | Compliance with FCA policies and national standards demonstrated throughout implementation and reflected in project reports. |

## Deliverables

The Activity shall commence with the review and strengthening of the Climate-Smart Agriculture training modules and competency-based curriculum by the FCA-appointed FCA- appointed Climate-Smart Agriculture Curriculum Consultant. The curriculum review process shall be completed within two (2) weeks from the commencement of the consultancy. Following completion of the review, the revised curriculum and training materials shall be validated and approved by FCA, and relevant stakeholders.

Upon approval of the revised curriculum, the selected TVET Centre shall develop and submit a detailed implementation work plan and inception report within the first week of implementation. During the training period, the TVET Centre shall submit monthly progress reports, maintain daily attendance registers, and keep continuous competency assessment records throughout the training implementation period.

The TVET Centre shall prepare and submit a Final Competency Assessment Report during the final week of training, maintain and submit a graduate database at the end of the assignment, and provide a comprehensive Final Report within five (5) working days following completion of all activities. All reports shall be submitted electronically in editable Microsoft Word and Excel formats, together with high-quality photographs, attendance sheets, assessment results, and any supporting documentation required by FCA. All deliverables must be submitted in English and approved by FCA Project Manager before finalization

## Expected Results:

By the end of the training:

- 60 unemployed youth possess market-relevant Climate-Smart Agriculture competencies.

- Youth demonstrate practical skills in greenhouse production, irrigation, composting, soil and water conservation, integrated pest management, and climate-resilient farming.

- Youth improve their employability through entrepreneurship, financial literacy, digital finance, and workplace readiness skills.

- Climate-smart agriculture and environmental sustainability are integrated into TVET delivery through updated competency-based modules.

- The TVET Centre has institutional capacity to continue delivering the improved CSA curriculum aligned with Ministry of Education and Science TVET standards.

## Duration of contract

The total duration of the assignment shall be three (3) months, comprising two (2) weeks for the review and strengthening of the Climate-Smart Agriculture (CSA) training modules, two (2) months for the delivery of the competency-based training, and two (2) weeks for final reporting and completion of all required documentation. The detailed implementation schedule shall be finalized and agreed upon during contract negotiations.

## Service Terms

The assignment shall be implemented through a one-time service contract with a fixed implementation period of three (3) months.

## Duty Station

The assignment shall be implemented in Hargeisa, Somaliland. The successful TVET Centre shall deliver classroom sessions at its accredited training facility and practical sessions at suitable demonstration farms, greenhouses, agricultural training sites, or partner institutions.

## Transport & Logistics

The selected TVET Centre shall be responsible for all operational arrangements required to implement the assignment, including:

- Classroom facilities.

- Demonstration farm and practical training facilities.

- Agricultural tools, equipment, and consumable materials.

- Qualified trainers and support staff.

- Coordination of field visits.

- Administrative support and documentation.

- Occupational health and safety measures during practical training.

- FCA will facilitate coordination with relevant government institutions and support participant mobilisation. Any cost-sharing arrangements will be specified in the service contract

## Methodology

The assignment shall be delivered using a Competency-Based Training (CBT) approach that combines theoretical instruction with practical learning. The methodology shall be learner-centered, participatory, and aligned with labor market needs and Climate-Smart Agriculture practices.

The training approach shall include:

- Interactive classroom instruction.

- Practical demonstrations and hands-on field exercises.

- Greenhouse, irrigation and demonstration farm activities.

- Group assignments and presentations.

- Case studies and problem-solving exercises.

- Field visits to relevant Climate-Smart Agriculture sites.

- Continuous competency-based assessments.

- Coaching and mentoring.

The training provider should integrate cross-cutting themes throughout the training, including gender equality, disability inclusion, safeguarding, environmental sustainability, occupational health and safety, entrepreneurship, digital literacy, financial literacy, climate resilience, and agricultural waste management.

# Validity

Tenders/Offers shall remain valid and open for acceptance for a period of 60 days after the closing date for the submission.

Prior to the expiry of the original tender/offer validity period, the Contracting Authority may ask tenderers/candidates in writing to extend this period. Tenderers/candidates that agree to do so will not be permitted to modify their tenders/offers. If they refuse, their participation in the tender procedure will be terminated.

# Timetable

| Deliverables | Duration |
| --- | --- |
| Inception and Mobilisation | 1 week |
| Training Preparation | 1 weeks (overlapping where appropriate) |
| Competency-Based Training | 2 months |
| Final Assessment, Certification and Reporting | 2 weeks |
| TOTAL DURATION | 3 months |

# Payment Modalities

Payments will be made in instalments linked to deliverables:

- 50% upon approval of inception report and work plan.

- 50% upon completion of training and approval of the final report and completion of training

Payments are subject to satisfactory performance and FCA approval of deliverables.

# Required Expertise and Qualification

The selected TVET Centre shall demonstrate the following minimum qualifications, experience and institutional capacity:

- Legally registered and accredited TVET institution recognized by the Ministry of Education and Science (TVET Department).

- Proven experience in delivering competency-based training (CBT) programmes, particularly in agriculture or related technical fields.

- At least five (5) years of experience implementing vocational training programmes, preferably including practical agricultural training.

- Demonstrated experience in Climate-Smart Agriculture, agriculture production, agribusiness, or related training areas.

- Availability of qualified trainers with relevant academic qualifications and practical experience in agriculture and Climate-Smart Agriculture.

- Experience applying practical, learner-centred training methodologies, including demonstrations, field-based learning and competency assessments.

- Availability of appropriate training facilities, including classrooms, practical training areas, demonstration sites, greenhouse facilities, irrigation systems, and other relevant agricultural training infrastructure.

- Proven capacity to develop training plans, conduct assessments, maintain training records, and prepare quality reports.

- Demonstrated experience working with youth, women, persons with disabilities, and vulnerable groups.

- Ability to integrate gender equality, disability inclusion, safeguarding, environmental sustainability, occupational health and safety, and climate resilience into training delivery.

- Strong administrative, coordination, reporting and documentation capacity to effectively manage the assignment.

- The selected TVET Centre must demonstrate commitment to FCA safeguarding principles, including prevention of sexual exploitation, abuse and harassment (PSEAH), child safeguarding, and safe learning environments.

# Contract Award Criteria

Proposals will be evaluated based on:

| # | Description | Weight | Scoring methodology |
| --- | --- | --- | --- |
| 1 | Technical approach and training methodology. | 20 | Technical proposal |
| 2 | Relevant experience in delivering short term CSA | 10 | Relevant document of implement similar procurements and timeframe |
| 3 | Qualifications of trainers and capacity of the training facilities | 10 |  |
| 4 | Financial score | 60% | Lowest bid receives highest score. Other candidates’ scores are calculated proportionally based on the lowest bid. |

# Evaluation Process

The evaluation process is managed by FCA’s Procurement Committee.

Tenderers will be first evaluated according to the requirements in section 16 - Required Expertise and Qualifications. Candidates which are eligible will be allowed to proceed to the evaluation phase and their offers will be evaluated according to the contract award criteria in section 17.

# Application procedure

Deadline for submission of offers is Aug 18, 2026, 3:30 PM EAT.

Candidates must send their offers via email to (Tenders.Soco@kirkonulkomaanapu.fi  or Tenders.Soco@kua.fi) no later than the deadline as mentioned above.

Any tenders received after the deadline will not be considered.

Bidders must put “ToR-Provision of Competency-Based (CSA) Training” in the subject line of their emails.

No tender may be changed or withdrawn after the deadline has passed.

The candidate shall bear all costs associated with the preparation and submission of the offer and the Contracting Authority will in no case be responsible or liable for these costs, regardless of the conduct or outcome of the procurement process.

# Questions

Candidates are not allowed to approach the Contracting Authority for verbal clarification.

Any prospective candidate seeking to arrange individual meetings with either the Contracting Authority and/or any other organisation with which the Contracting Authority is associated or linked may be excluded from the tender procedure.

Candidates may submit questions in writing via email to the address above latest three days before the deadline.

# Terms of contract

- Confidentiality

- The selected TVET center will responsible for payment of all social costs, other employment related costs and insurance contributions and for all other liabilities of a statutory nature.

- During the assignment, the consultant does not represent FCA and has no mandate to negotiate, make commitments or agree on behalf of FCA.

- The consultant is expected to use own computer and other equipment required for the works.

- By submitting an offer, the center confirms to abide by FCA Code of Conduct, Safeguarding policy

- The ownership and copyright(s) of the report(s) and any other produced material will remain with FCA.

- The Contracting authority may for its own convenience and without charge or liability cancel the tender process at any stage.

# Documents comprising this procurement

The TVET Center shall complete and submit the following documents with his tender:

- Financial Proposal, including a detailed budget breakdown for the delivery of the assignment.

- Signed FCA Code of Conduct.

- Institutional profile, registration and accreditation documents (Valid registration certificate of the TVET Centre. Valid accreditation/license from the Ministry of Education and Science (TVET Department). Valid Tax Clearance Certificate.)

- CVs, academic certificates and relevant qualifications of proposed trainers and key personnel.

- Evidence of relevant experience, including reference letters, completion certificates, or similar documentation from previous assignments.

# Annex I – Technical Proposal Template

To be filled-in by the candidates, in compliance with the following instructions

- Rationale (max. 1 page)

Any comments on the Terms of Reference of importance for the successful execution of activities, in particular its objectives and expected results, thus demonstrating the degree of understanding of the contract. Any comments contradicting the Terms of Reference or falling outside their scope will not form part of the final contract.

An opinion on the key issues related to the achievement of the contract objectives and expected results

(Optional: An explanation of the risks and assumptions affecting the execution of the contract)

- Proposed Methodology (max. 3 pages)

An outline of the approach proposed for contract implementation;

A list of the proposed activities considered to be necessary to achieve the contract objectives;

The related inputs and outputs.

- Timetable of activities (max 1 page)

The timing, sequence and duration of the proposed activities, taking into account mobilization time.

# Annex II – Financial Proposal Template

## Financial Proposal Template

Please provide a detailed financial proposal. Applicants' proposals must include a clear and competitive budget based on a cost per trainee per month model, inclusive of all fees, costs, taxes, training materials, equipment, trainers, facilities, administration, monitoring, reporting, and other costs required for successful implementation of the assignment.

Training Information

|  | 5 days a week (Saturday – Wednesday) 60 youth trainees (two classes) Including 30 minutes break. |
| --- | --- |
| Description | Quantity |
| Total trainees | 60 |
| Classroom and practical training duration | 2 MONTHS |
| Total training period | 2 months |

Financial Proposal Table

| Budget item | Unit | Quantity | Unit cost (USD) | Total Amount |
| --- | --- | --- | --- | --- |
| Training cost | Trainee per month |  |  |  |
| Transportation support | Trainee per day/month |  |  |  |
| Examination and certification cost | Lump sum |  |  |  |

Summary

| Description | Amount (USD) |
| --- | --- |
| Sub total |  |
| Taxes (if applicable) |  |
| Grand Total |  |

Costing Guidance

Costing Guidance

The proposed Training Cost per Trainee per Month shall include all costs related to:

- Climate-Smart Agriculture and waste management training.

- Practical training, demonstration activities, field visits, agricultural tools, equipment, and PPE.

- Entrepreneurship, agribusiness, employability skills, financial literacy, digital finance, and Career Guidance and Counselling (CGC).

- Trainers, training facilities, materials, administration, coordination, monitoring, assessment, certification, and reporting.

- Integration of GESI, disability inclusion, safeguarding, environmental sustainability, occupational health and safety, and climate resilience.