INVITATION TO BID FOR CONSULTANCY

TERMS OF REFERENCE: Integrated SMART

Survey Consultancy Bardhere District, Gedo Region-Somalia

February 2024

Introduction

Somalia has faced persistent challenges with acute food insecurity and malnutrition despite some recent improvements. The country continues to grapple with the prolonged impacts of recurring droughts and floods, conflict and insecurity, poverty, and inadequate health and nutrition services.

Currently, According to FSNAU Post Deyr IPC analysis, approximately 4 million people, representing 21% of the total population, are facing Crisis or worse acute food insecurity (IPC Phase 3 and higher). While projections for April-June 2024 indicate a slight improvement to 3.4 million people (18%), the crisis remains severe. Malnutrition, especially among children under 5, is also extremely concerning - around 1.7 million children are expected to suffer from acute malnutrition in 2024, with over 400,000 likely to develop severe acute malnutrition.

Several factors account for the high malnutrition in Somalia. Frequent droughts, floods, and erratic rainfall severely disrupt food production and access to nutritious foods. Ongoing conflict and violence frequently displace communities and limit humanitarian relief. Poverty forces families to cut down on quantity and diversity of foods. Somalia also has very low coverage of nutrition interventions, clean water, and sanitation services - all of which increase disease risk and undermine nutrition further. Harmful infant feeding practices such as sub-optimal breastfeeding are also widely prevalent.

Concern Worldwide has maintained programming in Somalia since 1986, working to save and transform lives in some of the worst-affected regions. Their operations concentrate largely in South Central areas like Mogadishu, Lower/Middle Juba and Gedo, where acute malnutrition prevalence remains well over emergency thresholds. Concern’s multi-sectoral programmes provide direct nutrition treatment for at-risk mothers and children, alongside integrated food security, health, hygiene and livelihoods assistance.

Bardhere town is located in the Gedo region along the Jubba River in southern Somalia. With an estimated population of 126,000 inhabitants, it serves as the center of Bardhere district as well as the main economic and transportation hub connecting Somalia to Ethiopia and Kenya. The town has historically depended on the Jubba River for water supply, irrigation and income generation through fishing and animal rearing

Torrential rains in October/November 2023 brought on by El Niño phenomenon caused unprecedented flooding across Somalia. The Jubba River burst its banks, inundating surrounding regions. In the riverine Bardhere district, the floods raged through the town washing away the main bridge that had spanned across the Jubba River for decades.

This bridge was a vital lifeline for Bardhere Town and its residents on both banks of the River. The bridge connected the two sides of the town enabling movement of people and goods and supported key infrastructure like water pipes and electricity lines. Its destruction has effectively severed the town into two disconnected parts with movement between them now only possible via scarcely available canoes at heavily inflated costs.

## Justification

The impact of the recent El Niño event has been profound, particularly evident in the critical collapse of the Bardera bridge, which has had a devastating effect on the population of Bardera. With the bridge divided into two halves, the flow of essential supplies has been severely disrupted, leading to a rapid depletion of food stocks and a staggering increase in prices for basic necessities. Consequently, many families are now facing the harsh reality of unaffordable essentials.

Adding to the crisis, the town's primary water infrastructure, situated along the collapsed bridge, has been rendered useless, resulting in a complete disruption of piped water supply. As a result, residents are left with no choice but to retrieve water from the flood-contaminated Jubba River, risking their health and exacerbating the already dire situation.

This dire scenario has not only compromised food security but has also triggered a cascade of issues, including high prevalence of Malnutrition, deteriorating health conditions, and widespread economic devastation across Bardhere District. A recent malnutrition MUAC screening conducted by the Jubland Ministry of Health presented during the annual review meeting revealed alarming levels of malnutrition in Bardera on top of the recently published seasonal IPC Acute Food Insecurity And Acute Malnutrition Analysis on Feb 15th 2024, underscoring the urgent need for a comprehensive assessment to accurately gauge the requirements of the affected population and guide to inform effective response.

Therefore, it it became necessary to initiate full fledged a SMART survey in the district promptly. This survey will serve as a crucial tool for gathering essential data on various critical aspects, including mortality rates, levels of malnutrition, outbreaks of diseases, and priority needs. The insights gleaned from this survey will play a pivotal role in informing and shaping targeted, life-saving interventions tailored to the specific needs of Bardhere's affected and vulnerable communities, thereby mitigating the impact of the crisis and facilitating the path towards recovery and resilience

## Survey details

| Description of the Survey Area |  |
| --- | --- |
| Survey Date | 3rd April 2024 |
| Timing | Lean season |
| Survey Location | Bardhere district, Gedo region |
| Survey type | Full SMART Survey |
| Type of setting | Urban, IDP and Rural |
| Total number of people living in the survey area | 125, 690 |
| Total number of villages in the area | 53 |

## Overall objectives

Estimate Nutrition status of children <5, retrospective Mortality rate (CMR and U5MR) and factors influencing nutrition status of children.

### Specific objectives

- Estimate prevalence of acute malnutrition among children 6-59 months.

- Asses maternal Nutrition status of WCBA (15-49 years) and PLWs by using MUAC of <21cm

- Estimate Retrospective CMR and U5MR

- Estimate morbidity rates among children <5years for the past two weeks prior to the survey

- Establish coverage of vitamin A and deworming among children under-fives?

- Estimate rates of handwashing during critical moments

- Estimate EPI programme coverage specially measles and Polio through routine immunization, outreach and campaigns

- Estimate key IYCF indicators following 2021 guidance

- Draft actionable recommendations based on the findings.

- Disability prevalence at HH level

# Methodology

## Sampling design and rationale

The survey will be a quantitative, cross sectional and descriptive by design. Standardized Monitoring and Assessment on Relief and Transition methodology (SMART) will be utilized in the assessment. The survey applies a two-stage cluster sampling.

## Sampling methods

Based on accessibility, level of vulnerability, and random sampling Concern World Wide will assess Urban and Adjacent rural villages from both Bardhere District. The study population will include the entire population in all selected survey areas. All (clusters/sampling units) in the selected population, which are accessible, secure, or not deserted, will be included in the sampling frame. The population estimates for the sampling units (villages) will be based on the UNFPA 2014 population census as well as data from the local authority.

## Sample size calculation

The following assumptions (based on the given context above) will be used to calculate the sample size in number of children, which will then converted into number of households to survey. All calculations will be made using ENA Software (version Jan 11th, 2020).

## Sampling procedure and data collection

A two -stage cluster sampling method will be applied, where Stage-I, involves selection of villages from all the accessible villages in Bardhere District. In Stage-II, households to be surveyed from the shortlisted villages, will be marked.

## Stage I: The Selection of Clusters and Households

First stage sampling will be done based on Probability Proportional to Size Sampling (PPS) method using ENA (version 11th Jan 2020) software. Lists of all villages within Bardhere District and their corresponding population estimates will be obtained from District Commissioner office as well from CWW field team and entered in ENA software. Villages will be considered as the smallest geographical unit (cluster). The number of clusters to be surveyed in the selected villages will be generated by ENA software. The sample of clusters will be selected from an updated sampling frame (list of all accessible and inhabited villages in the district)

## Stage 2: Household selection

Second stage sampling will consist of HH selection and this will be done by the teams in the field. Upon reaching the selected village, all HH will be listed and then using the random number generator-a mobile software app- 17 HHs will be randomly selected. The selected HH will then be surveyed by the team of data collection enumerators. Regardless of the presence of children Under Five, all HH will be interviewed for mortality questionnaire. HH having a child 6-59 month of age will be administered for data collection around anthropometric and other household related aspects of data collection.

Time frame

The survey will be conducted within a period of 30 days including training, travel, data collection, analysis and reporting. The consultant should clearly articulate their ability to accomplish the required tasks within the specified timeline due to the urgent need to use the findings in the current response. The field data collection is expected to take place between February and March 2024. The first draft of the report should be submitted no later than 10 working days after data  collection is completed

Survey Teams

The number of survey teams required for the SMART survey in Bardere district shall be determined based on the calculated sample size of children under 5 years and households needed to generate statistically reliable results at required precision levels.

As per globally validated SMART methodology protocols, each survey team for such nutrition and mortality assessments shall comprise of at least 4 members - 2 measurers, 1 team leader and 1 community guide. Team compositions may require adjustment accordingly to fulfill data collection timelines meeting quality standards.

Training of Enumeration Teams

5-day classroom and field training shall orient teams on:

- Survey purpose and protocols

- Digital data collection tools operation

- Anthropometry equipment use and standardization

- Cluster sampling and segmentation techniques

- Household random sampling procedures

- Consent procedures and ethics

- Real-time data uploading

A field pilot test shall enable identification of effectiveness challenges for further refinement before full data collection commencement.

Data Quality Assurance

The consultant is expected to put in place robust protocols in order to ensure high quality, reliable data including:

- Daily progress monitoring, random team audits and measurement technique correction by consultant and field supervisors

- Real-time data uploads to server by Team Leaders along with form review for completeness, accuracy and consistency

- Data encryption, restricted access authorization to protect participant confidentiality

- Daily cleaning and plausibility checks, with any anomalies verified promptly at cluster level

Consultant Roles and Responsibilities

The consultant shall:

- Develop inception report outlining survey protocol, tools and methods for Concern review

- Design data collection tools and configure them using appropriate platforms like ODK

- Lead entire survey planning, training of teams, daily field supervision and quality assurance

- Train data collectors and clerks on survey standards, procedures and use of tools

- Directly manage data gathering ensuring completeness and reliability

- Execute data cleaning, analysis, and interpretation using ENA and other platforms

- Draft initial SMART survey report incorporating all findings and metrics for Concern feedback

- Facilitate report review workshop for survey validation

- Submit final, comprehensive report with background, methods, results, discussions and actionable recommendations

Concern WorldWide’s Role and Responsibilities

- Provide technical guidance and review of survey methodology, tools and protocols

- Support ethical review and cluster notification/endorsement of survey

- Arrange field logistics like travel, enumerator payments and accommodation

- Recruit qualified enumerators proficient in English and local Somali language

- Liaise with relevant line ministries at Federal and state level

- Provide feedback on draft deliverables including inception and draft report.

Deliverables

The key deliverables from this consultancy shall include:

- Inception report detailing survey protocol, tools, analysis plan

- Enumerator training materials & attendance sheet

- Initial SMART findings PowerPoint debrief

- Draft Integrated SMART survey report for review and inputs

- Final, high quality SMART survey report

Qualifications & Experience

- University degree in public health, nutrition or relevant field

- Extensive expertise in leading SMART survey design, sampling, training, data collection, analysis using ENA/other packages

- At least Eight years of work experience at national or international levels in managing SMART nutrition surveys in Somalia or similar contexts

- Possess SMART+ Certification

- Proficiency in written and spoken English and Somali

- Demonstrated skills in data interpretation, technical report writing and presentation

- Prior experience with SMART Survey report validation at AIMWG

- Familiarity with Somalia context

- Be able to travel independently to Bardhere

Application Requirements

Interested consultants shall submit the following documents which shall be evaluated to determine selection:

- Technical Proposal: Demonstrating understanding of the TOR and proposed approach for successfully conducting the SMART survey including methodology, tools, implementation plan, prior experience etc.

- Financial Quote: Detail all costs related to consultancy including assistance and reporting analysis associated cost.

- Company/Consultant Profile: Highlighting technical capabilities, expertise areas, past emergency surveys conducted, quality standards

- Team Composition: Introducing key personnel that shall undertake this assignment along with respective roles and relevant CVs

- Work Samples: Minimum 3 previous SMART survey reports undertaken in Somalia in the last 2 years.

- Client References: Contact details of at least 5 prior organizations for which such assignments completed previously

Interested applicants that meet the requirements should send their complete documents with the subject line: “Application for Bardhere SMART Survey” to: som.vacancies@concern.net by 4th March 2024 5pm Mogadishu Time (EAT).

Application submitted after the deadline will not be considered.

https://fsnau.org/downloads/IPC-Somalia-Acute-Food-Insecurity-Malnutrition-Jan-Jun-2024-Report.pdf