# TERMS OF REFERENCE

Oxfam is a global movement of people who are fighting inequality to end poverty and injustice. Across regions, from the local to the global, we work with people to bring change that lasts.

| OVERVIEW |  |
| --- | --- |
| Title and brief description of the assignment | Call for expressions of interest: Research on the impact of climate change on the Bajuni Island population in Jubaland, Somalia |
| Assignment location | Jubaland, Somalia |
| Contract start date | 15th July, 2025 (tentatively) |
| How to apply | Interested candidates are invited to submit with the following documents: - A technical proposal with a detailed response to the TOR, with a specific focus on the scope of work, methodology, and timelines. - Initial work plan and an indication of availability. - A financial proposal detailing the daily rate expected including accommodation, transportation, stationery, taxes arising from the consultancy service (6% tax for National consultant and 12 % tax for international consultants), and all other costs related to this assignment. (Operational and consultancy fees). - Curriculum Vitae(s) (CV) of the proposed consultant(s), proving relevant experience and/or qualifications. If multiple people are involved, an outline of roles/ responsibilities also needs to be included. - Evidence of conducting previous similar work by providing minimum two signed contracts / purchase orders (preferably from UN agencies and INGOs). - Two relevant references (minimum) for previous comparable assignments. - Proof of registration: The bidders also must include a copy of their registration at the relevant authority. See section ‘7. Application Process’ for further details |
| Application deadline | 15 JUNE 2025 |
| Specific considerations |  |

# PURPOSE OF THIS CONSULTANCY

Oxfam is a global movement of people working together to end the injustice of poverty. Together we save, protect, and rebuild lives. We won’t stop until every person on the planet can defeat poverty or any type of inequality or discrimination. We are an international confederation of 19 organizations (affiliates) working together with partners and local communities in the areas of humanitarian aid, resilience building, development, and campaigning, in more than 90 countries. All our work is led by three core values: Empowerment, Accountability, Inclusiveness.

Increasing climate variations contribute to the erosion of pastoral livelihoods driven by  deteriorated pasture areas, limited productive resources and adapting capacities. The loss of livestock leads to recurrent humanitarian crises, including food insecurity and limited access to essential services. These challenges have resulted in large-scale displacement, as families move in search of water and viable grazing areas.

The impact of climate change is not uniform; different communities and demographic groups experience its effects in unique ways. In particular, women and men face different vulnerabilities and have distinct experiences, knowledge, and attitudes towards climate change, largely due to entrenched traditional gender roles and power imbalance. Understanding these gendered and community dynamics, alongside the broader environmental and socio-economic impacts of climate change, is essential to developing effective and inclusive adaptation strategies for the Bajuni Island population.

Considering this context, we are seeking an expression of interest from an experienced consultant / consultancy firm to conduct a comprehensive study on the impact of climate change on the Bajuni Island population and communities in Jubaland, Somalia. The study aims to assess the socio-economic, environmental, and health impacts of climate change on the Bajuni Island population, with a specific focus on minority groups. The findings will inform the development of strategies tackling climate change impacts on these vulnerable communities, while strengthening their central role in decision-making on proposed strategies.

# SCOPE OF WORK

We are seeking an expression of interest from experienced individuals or consultant firms to conduct a comprehensive study on the impact of climate change on the Bajuni Island population and communities in Jubaland, Somalia, including recommendations for addressing these negative impacts in an inclusive manner.

# EXPECTED OUTPUTS

## Overall objective

The objective of the assignment of approximately 30-day work is to produce a study in English of up to 50 pages, including annexes with the following specific outputs.

## Specific outputs

- An executive summary.

- Overall analysis of the climate change impact on Bajuni communities, highlighting socio-economic, environmental, governance and health challenges.

- Clear description of the specific impacts of climate change on key target groups, particularly youth, children, people with disabilities, minorities and elderly, specifying gender dimensions of the impacts in each of these groups.

- Assessment of the extent of the role played by Bajuni communities in governance and decision making and their participation in addressing climate change, including policy making and actions, highlighting barriers to participation and opportunities for better inclusion in decision-making processes for particular groups.

- Recommendations on how to address climate change and identified inequalities with a strong emphasis on participation of identified vulnerable groups in decision making.

- A specific section on opportunities for Bajuni communities to connect, build alliances, and reinforce their involvement in climate justice.

- Validation of findings and recommended strategies by the target groups and key stakeholders - including policy makers and donors.

# METHODOLOGY

- Desk research (specific literature and secondary sources to be reviewed will be agreed with Oxfam).

- Key informant interviews (a list of interviewees and a tool’s content to be agreed with Oxfam).

- Focus group discussions (a tool’s design to be agreed with Oxfam).

## Planned timeline

The assignment will be conducted with an estimated duration of 30 days from the date of signing the contract

# DELIVERABLES AND PAYMENT SCHEDULE

Remuneration is based on submission of final deliverables according to the schedule below.

| No. | Deliverables or Documents to be delivered | Estimated Dates | % Payment |
| --- | --- | --- | --- |
| 1 | DELIVERABLE 1 Inception report and Desk review – (Work plan, agreed guiding questions and methodology/specific tools, list of sources for desk review, interviewees, and final report format) | 24th July ,2025 | 40% |
| 2 | DELIVERABLE 2 Midpoint update presentation (key conclusions from literature review, initial programmatic recommendations). | 21stAugust 2025 |  |
| 3 | DELIVERABLE 3 Draft study submitted to Oxfam for comments. | 28th August 2025 |  |
| 4 | DELIVERABLE 4 Final report submitted and approved by Oxfam. | 4th Sept 2025 | 60% |
| TOTAL |  |  | 100% |

# PROFILE REQUIREMENTS

The company/ individual(s) should have the following competencies:

Essential

- Master’s degree in environmental science, climate change adaptation, international cooperation, social sciences etc.in or relevant disciplines.

- Extensive experience in social research includes designing and conducting formal and academic research, data collection (including through key informant interviews and focus groups) and analysis.

- Familiarity with the socio-political landscape in Somalia, particularly in coastal and island communities.

- Excellent report writing skills.

- In-depth understanding of gender issues in addressing climate change and climate justice in the context of Somalia.

- High proficiency in English (verbal, professional writing skills).

Desired

- Experience in using technology for research.

# APPLICATION PROCESS

## Submission deadline

Quotations and applications must reach Oxfam no later than [JUNE 15, 2025].

## Submission instructions

- Responses must be submitted electronically to: SOM-Consultancies@oxfam.org

- The subject of the mail should be Call for expressions of interest: Research on Study impact of climate change on Bajuni Island population/Communities in Jubaland, Somalia

- All attached documents should be clearly labelled so it is clear to understand what each file relates to.

## Clarifications

Any questions, remarks or requests for clarification can be sent up to 10 days before the submission deadline in writing. The (anonymised) questions will be answered to all applicants.

## Administrative compliance (list of documents to be submitted)

Responses must be submitted and prepared in [English] and received by the deadline.

To be shortlisted for evaluation against award criteria, the following documents must be included in the application:

| Administrative Criteria |  | Importance |
| --- | --- | --- |
| 1 | Technical proposal / approach paper to conduct the assignment and achieve objectives including methodology, proposed work plan and timelines | Mandatory |
| 2 | Financial offer (price quotation) including budget and pricing A financial proposal detailing the daily rate expected including accommodation, transportation, stationery, taxes arising from the consultancy service (6% tax for National consultant and 12 % tax for international consultants), and all other costs related to this assignment. (Operational and consultancy fees) | Mandatory |
| 3 | Curriculum Vitae(s) (CV) of the proposed consultant(s), proving relevant experience and/or qualifications. If multiple people are involved, an outline of roles/ responsibilities also needs to be included. | Mandatory |
| 4 | Two relevant references (minimum) for previous comparable assignments | Mandatory |
| 5 | Proof of registration: The bidders also must include a copy of their registration at the relevant authority. | Mandatory |
| 6 | Evidence of conducting previous Similar work by providing minimum two Signed Contracts / Purchase Orders - (Preferably from UN agencies and INGOs). | Mandatory |

## Evaluation and award criteria

Incomplete applications will not be assessed, only quotations that meet the administrative criteria will be assessed.

Award decisions will be based on best value for money criteria covering both technical quality and price.

The award criteria are assessed according to the following distribution of points:

| Award Criteria |  | Max. points |
| --- | --- | --- |
| Technical offer/ approach paper evaluation |  |  |
| Experience/ competencies | Relevant experience with the NGO sector | 5% |
|  | Positive references/reputation | 5% |
|  | Relevance and quality of sample previous work, reporting etc. | 5% |
|  | Knowledge of country, context | 5% |
|  | Knowledge of team languages | 5% |
|  | Clearly indicated alignment with Oxfam values | 5% |
| Technical quality | Quality of application: complete, good presentation and format, etc. | 9% |
|  | Understanding of the assignment and the scope of the project | 9% |
|  | Quality of the methodology, workplan and feasibility of the timeline (concrete and realistic) | 9% |
|  | Quality and experience of staff resources assigned to the services + sufficient assigned resources (where relevant) | 9% |
|  | Ability to lead/manage a team (where relevant) | 9% |
| TOTAL: |  | 75% |
| Financial offer |  |  |
| Financial offer | Submission of realistic and acceptable financial proposal – reasonable budget breakdown and cost consideration detailing the daily rate expected including travel, accommodation, transportation, stationery, taxes arising from the consultancy service (6% tax for National consultant and 12 % tax for international consultants), and all other costs related to this assignment. (Operational and consultancy fees). The lowest evaluated financial proposal that meets the administrative criteria will be awarded the maximum point (25%). The points for all other Applications will be prorated. | 25% |
| GRAND TOTAL: |  | 100% |

Oxfam withholds the right to conduct interviews with one or more potential applicants before an award decision is made. The purpose of the interview is to seek further clarification on the submitted documents and learn more about the background and previous experiences of the potential suppliers and their teams.

# OTHER CONDITIONS

Issuance of this Terms of Reference does not constitute an award commitment on the part of Oxfam, nor does it commit Oxfam to pay for costs incurred in the preparation and submission of a bid.

The attached Annexes are an integral part of this Request for Proposals – see section 13.

Oxfam may contact bidders to confirm contacts, addresses, bid amount and to confirm that the bid was submitted for this solicitation.

OXFAM has the right to undertake due diligence to verify the references, and very details submitted before award.

## Quotation validity

- The quotation shall be valid for 90 days from the submitted. If this is not possible, the bidder may propose a different timeframe.

- If the bidder is awarded the contract, all information provided in the quotation and negotiation process is contractually binding.

## Right to Select/ Reject

Oxfam reserves the right to select and negotiate with those firms it determines, in its sole discretion, to be qualified for competitive proposals and to terminate negotiations without incurring any liability. Oxfam also reserves the right to reject any or all proposals received without explanation.

## Reserved rights

All applications and quotes become the property of Oxfam, and Oxfam reserves the right in its sole discretion to:

- Disqualify any offer based on applicant’s failure to follow solicitation instructions.

- Waive any deviations by the applicant from the requirements of this terms of reference that, in Oxfam’s opinion, are considered immaterial defects requiring rejection or disqualification; or where such a waiver will promote increased competition.

- Extend the time for submission of responses after notification to all applicants.

- Terminate or modify the process at any time and re-issue the request for quotation to whomever Oxfam deems appropriate.

- Issue an award based on the initial evaluation of offers without discussion.

- Award only part of the activities in the solicitation or issue multiple awards based on solicitation activities.

# CODE OF CONDUCT

Oxfam is committed to integrity in its operations and supply chains and ensuring high ethical standards. Complying with all laws and regulations and ensuring fair competition are fundamental to this commitment. We actively promote these principles and standards and expect all Oxfam suppliers to demonstrate commitment towards them.

All consultants/applicant are required to agree and adhere to the Oxfam Supplier Code of Conduct, whereas individuals (including consultants) must sign the Oxfam Non Staff Code of Conduct. These Codes of Conduct set out the specific standards and principles in the areas of human and labour rights, environmental impact and anti-corruption that suppliers must follow.

Oxfam has the following requirements of its service providers, to ensure integrity in its supply chain:

## Bribery and collusion

Oxfam does not tolerate fraud, including bribery or kickbacks, collusion among bidders, bribery or kickbacks. Any firm or individual violating these standards will be disqualified from this procurement and barred from future procurement opportunities.

Employees and representatives of Oxfam are strictly prohibited from asking for or accepting any money, fee, commission, credit, gift, gratuity, object of value or compensation from current or potential vendors or suppliers in exchange or as a reward for business.

## False statements

Bidders must provide full, accurate and complete information as required by this solicitation and Annexes. False statements in bids constitutes grounds for immediate termination of any agreement with the supplier. OXFAM takes misstatements, falsification, manipulation, alteration of facts and/or documents very seriously, has a zero-tolerance policy to such behaviours, and may choose to take legal action in a case of misrepresented disclosures by

## Conflict of interest

Bidders must provide disclosure of any past, present or future relationships with any parties associated with the issuance, review or management of this solicitation and anticipated award.  Failure to provide full and open disclosure may result in Oxfam having to re-evaluate the selection of a potential bidder.

## Diversion of funds

Oxfam is determined that all its funds and resources should only be used to further its mission and shall not be subject to illicit use by any third party nor used or abused for any illicit purpose. Suppliers (and their affiliates/group companies, employees, officers, owners, agents and sub-contractors) may be subject to formal screening against global lists of individuals subject to designation or proscription under financial sanctions or counter terrorism regulations.

# Monitoring

Due diligence: As a charitable organisation, Oxfam must take care to protect its assets and funds, as well as the communities that we work with. One of the steps that Oxfam takes to comply with this legal duty is to conduct adequate and proportionate due diligence on suppliers prior to entering a contract. This includes checking legal registration and financial solvency, but may also include other checks, such as misconduct/performance reference checks and if working with children or vulnerable adults, a criminal records check.

Important note: Oxfam performs a regular screening check of all suppliers against international sanctions lists.

Audit: Any audit requirements are detailed in the terms and conditions of business

Data protection: Oxfam is legally bound to ensure that all personal details held by the organisation relating to any individual or entity are kept secure and according to international data protection standards.

# MISCONDUCT REPORTING AND WHISTLEBLOWING

Oxfam’s reporting and whistleblowing mechanisms are available for Service Providers as well Oxfam employees, to ensure that Oxfam continues to operate under the highest ethical standards and principles.

You can use these reporting channels confidentially, anonymously, and in your own language to report any concerns involving fraud, corruption, waste, abuse or safeguarding concerns.

| Speak up |  |  |  |
| --- | --- | --- | --- |
|  | Oxfam GB | Oxfam Novib | Oxfam Intermón |
| Email: | SpeakUp@oxfam.org.uk | integrity@oxfamnovib.nl | buzon.etico@oxfam.org |
| Online: | Oxfam Misconduct Reporting Webform (including possibility for anonymous reporting) https://oxfam.clue-webforms.co.uk/webform/misconduct/ |  |  |
| Phone: | Global phone number: +44 1249 661808 Check https://speakup.oxfamnovib.nl for local numbers (you can request interpretation) |  |  |

# ANNEXES

- Oxfam Supplier Code of Conduct: https://oxfam.box.com/v/Oxfam-Supplier-CodeConduct

- Oxfam Non-Staff Code of Conduct: https://oxfam.box.com/v/Nonstaff-CodeConduct

- Conflict of interest declaration form: https://oxfam.box.com/v/Supplier-COI-declaration

- Safeguarding policy

- (If applicable) Oxfam child safeguarding policy

- (Edit if applicable) Example privacy notice: https://oxfam.box.com/s/mo8artt9l8a2x0cnpqrqqrugt8k0r773

Non-Staff Code of Conduct applies for any self-employed individuals or contracted employees of suppliers who are working on Oxfam sites, or who have access to Oxfam materials, or who may represent Oxfam in any manner but are not part of Oxfam’s legal entity)