INVITATION TO BID FOR CONSULTANCY

| 1 | Title of Consultancy | TERMS OF REFERENCE FOR JOINT CAPACITY ASSESSMENT OF CHILD PROTECTION AND JUSTICE LINE MINISTRIES IN SOMALIA FOR NORAD 2024-2028 |  |
| --- | --- | --- | --- |
| 2 | SCI Contracting Office | Save the Children Somalia/land Country Office |  |
| 3 | Period of Consultancy | The duration of the assignment will be 45 calendar days, inclusive of travel days and weekends |  |
| 4 | Consultant type required | Consultancy Firm/Individual consultant |  |
| 5 | Responsibility for Logistics arrangements and Costs | Save the children will pay the consultant fee in a lump sum and will not reimburse any incurred costs during the assignment. The consultant will cover their own Logistical arrangements, costs; including food, accommodation, local transport and all cost associated with data collection work and whole activities. |  |
| 6 | Taxation Provisions | The consultancy firm/Consultant shall be responsible for all taxes arising from the consultancy in line with the local Tax regulations applicable at the SCI contracting office. |  |
| 7 | Travel requirements | The consultancy firm/Individual will cover all travel costs (tickets) and arrange local travel to field sites. |  |
| 8 | Security requirements | The consultancy firm/individual will comply with standard of Save the Children Security procedures, including the completion of SCI online security training (applicable to international consultants) prior to travel to Somalia in case needed. |  |
| 9 | Professional quality and Expertise | The following are the minimum requirements for the Consultant Firm/individual to be considered for carrying out the assignment. - Master’s degree in social sciences, Development Studies, Public Administration, Human Rights, or related field. - A minimum of 7-10 years of professional experience in international development, with a significant focus on institutional strengthening and capacity development of government bodies. - Proven, extensive experience conducting institutional capacity assessments for government ministries, preferably in fragile or post-conflict contexts. (Evidence of at least two similar previous assignments is required). - Deep technical expertise in Child Protection and/or Gender-Based Violence systems strengthening. - Demonstrated experience working in Somalia or the Horn of Africa, with a strong understanding of the political, social, and institutional landscape. - Excellent analytical, facilitation, and participatory methodology skills. - Outstanding report writing skills in English, with the ability to produce high-quality, concise, and actionable reports. |  |
|  | KEY PROFESSIONAL STAFF REQUIREMENT |  |  |
|  | Description | Minimum Qualification and professional experience |  |
|  | Teachers Situational Study Expert/Technical Team Lead | - A minimum of 7-10 years of professional experience in international development, with a significant focus on institutional strengthening and capacity development of government bodies. - Conducting studies in child protection and child right governance domains - Strong background and experience in data collection and evidence-based analysis with the use of digital aided platforms/tools. - Demonstrable experience in conducting similar assignments in Somalia. Knowledge of local context is highly preferred - demonstrated ability to produce clear, compelling, and succinct analytical reports from multiple sources that inform quality programming. - Excellent communication and report writing skills. |  |
|  | 11 EVALUATION CRITERIA The proposals submitted by consulting companies will be evaluated based on the following criteria: |  |  |
|  | Essential Criteria |  | Pass/Fail |
| 1 | The Bidder and its staff agree and Sign to comply with SCI policies embedded below at this ITB. The Bidder is to download below listed items, read, understand and sign off appropriate section in below. a) Terms & Conditions of Bidding b) Supplier Sustainability Policy and the included mandatory policies |  | Pass/Fail |
| 3 | A valid Certificate of Registration from the relevant Ministry of Commerce in Somalia NB: This is only applicable to firms and not individual consultants. |  | Pass/Fail |
| 4 | A valid Tax Compliance Certificate the relevant ministry of Finance/Revenue Authority in Somalia NB: This is only applicable to firms and not individual consultants. |  | Pass/Fail |
|  | Capability Criteria (Technical Evaluation): |  |  |
| 5 | Detailed technical proposal with clear understanding of the TOR and Methodology of how the consultant intends to conduct assignment with detailed work plan, clear milestones, methodologies, data analyses plan including any software to be used for analysis. This to be evaluated based on: - Overall quality, clarity, organization and relevance of the technical proposal document – (20 marks max.) - The level of work plan detail and how it is related to the proposed methodology - (10 marks max.) |  | 30 marks |
| 6 | Two Copies of the previous similar reports relevant to the subject matter. (10 marks – with each similar report being awarded 5 marks) |  | 10 Marks |
| 7 | Submit official and genuine signed official bank statement from 1st August 2025 to 30th September 2025 (15 Marks). |  | 15 Marks |
| 8 | Experience in conducting similar assignments related to the subject matter as proven experience. This to be evaluated based on: - Submission of at least two (2) contracts or LPOs demonstrating prior experience in the design and development of child protection and child rights assessments (10 Marks) - Submission of CVs for key technical staff, clearly detailing their qualifications and relevant experience (10 Marks) - A cover letter introducing the company, outlining its technical expertise, interest in the assignment, and demonstrating technical suitability (5 Marks) - Updated Company Profile (Optional) |  | 25 Marks |
|  | Commercial Criteria (Financial Evaluation): |  |  |
| 9 | Detailed financial proposal with budget breakdown including all expenses, fees, and taxes. 100% x Lowest bid valueCurrent value bid x 0.20 |  | 20 marks |
|  | Total |  | 100 marks |
| Note: For the technical analysis, a company must pass the essential criteria and score 60% and above on the capability to be considered in the next evaluation process and the ultimate decision will be based on interview performance. |  |  |  |
| 11 | Application Procedure | - Interested consultant (s) who meet the consultancy requirements are requested to submit their bid and each application package should include the above required minimum requirements. Applications can be submitted by: Protected Email box below - Email should be addressed to Somalia.Tenders@savethechildren.org - Should you need any clarifications please direct your queries to Somalia.procurement@savethechildren.org and expect responses within maximum of two working days. - Note – this is a sealed tender box which will not be opened until the tender has closed. Therefore, do not send tender related questions to this email address as they will not be answered. The subject of the email should be TERMS OF REFERENCE OF CAPACITY ASSESSMENT OF CHILD PROTECTION AND JUSTICE LINE MINISTRIES IN SOMALIA FOR NORAD 2024-2028 - All attached documents should be clearly labelled so it is clear to understand what each file relates to. - Emails should not exceed 15mb – if the file sizes are large, please split the submission into two emails. - Do not copy other SCI email addresses into the email when you submit it as this will invalidate your bid. All applications MUST be submitted on or before the closing date below to be considered for the assignment. Only shortlisted Candidates will be contacted. |  |
| 12 | Closing date for Applications | Interested consultants shall submit their applications through the above procedures on or before 10th November 2025. |  |

| We, the Bidder, hereby confirm we compliance with the following policies and requirements: |  |  |
| --- | --- | --- |
| Policy | Policy / Document | Signature |
| Terms & Conditions of Bidding |  |  |
| Supplier Sustainability Policy and the included mandatory policies | Click Here to Access |  |

| We confirm that Save the Children may in its consideration of our offer, and subsequently, rely on the statements made herein. |  |
| --- | --- |
| Signature: | ………………………………………………….. |
| Name: | ………………………………………………….. |
| Title: | ………………………………………………….. |
| Company: | ………………………………………………….. |
| Date: | ………………………………………………….. |

Joint Capacity Assessment of Child Protection and Justice Line Ministries in Somalia

TERMS OF REFERENCE

Introduction

This Terms of Reference (ToR) details a critical and strategic institutional capacity assessment of the Ministries of Women and Human Rights Development (MoWHRD), which are line ministries responsible for Child Protection (CP), Gender-Based Violence (GBV)in Puntland, Hirshabelle, and Galmudug states of Somalia. The fundamental rationale for this assessment is the recognition that sustainable, long-term protection for children and survivors of GBV can only be achieved through a capable and functional state-led system. The primary focus of this assignment is on the institutional level. We are assessing the ministry's core internal capacity to perform its designated functions, using its Child Protection and GBV mandate as the thematic lens for the analysis. The goal is to diagnose the ministry's foundational systems governance, human resources, planning, and coordination to inform a strategy for building a resilient institution from the inside out.

It is important to note that the approach for Puntland will differ from that for Hirshabelle and Galmudug. The Puntland MoWHRD underwent a broader capacity assessment in 2022 and 2023. Therefore, this exercise will focus on updating and validating those existing findings specifically for the CP/GBV functions and, crucially, developing a costed capacity strengthening action plan which was not previously completed due to funding constraints. For Hirshabelle and Galmudug, a full, comprehensive assessment will be conducted from the ground up.

Although these line ministries are the designated duty-bearers with the mandate to lead prevention and response, their current capacities are nascent and severely limited, particularly in the fragile contexts of Hirshabelle and Galmudug. At present, SC and other actors provide essential support, but these capacity-building efforts are often ad-hoc, scattered, and supply-driven, consisting of one-off trainings that are not grounded in a holistic understanding of the ministries' systemic weaknesses. This fragmented approach risks being inefficient and unsustainable.

Therefore, this assessment is designed to correct this course. It will move beyond scattered trainings to inform a cohesive, evidence-based, and government-owned strategy. The findings will provide a clear evidence base for SC and other like-minded organizations to design and implement a targeted, multi-year capacity strengthening plan, fostering a more sustainable and effective state-led protection system for children and survivors of GBV.

2. Background

The protection environment for children, adolescents, and women in Somalia is severely compromised by armed conflict, displacement, recurrent climate-induced disasters, and deeply entrenched harmful social norms. Children face a multitude of risks, including family separation, recruitment into armed groups, child labor, and various forms of GBV such as child marriage and female genital mutilation (FGM). The linkages between CP and GBV are inextricable, as children, particularly adolescent girls, are disproportionately affected by sexual violence and exploitation.

The line ministries mandated to provide protection and services (e.g., Ministries of Women and Human Rights Development,) are the legitimate and essential leaders for creating a protective environment in their respective states. However, they are severely constrained by limited domestic funding, a shortage of skilled human resources, weak inter-ministerial coordination, and underdeveloped legal and policy frameworks.

In this context of low state capacity, the humanitarian and development community, including SC, has provided essential services and support. However, this support has often resulted in parallel systems and the aforementioned uncoordinated capacity-building initiatives. These well-intentioned but 'one-off' training, delivered without a comprehensive institutional diagnosis, rarely lead to lasting systemic change. They fail to address foundational issues in governance, financial management, human resource development, and service delivery infrastructure. This leaves ministries dependent on external actors and hinders the development of a cohesive national protection architecture.

Therefore, this joint capacity assessment is not merely a technical exercise; it is a foundational step towards rationalizing support, fostering genuine government ownership, and strategically building a more resilient and effective protection system from the ground up. It will provide the critical analysis needed to ensure that future investments by SC and other partners are targeted, synergistic, and contribute directly to strengthening the long-term capacity of the state to fulfill its protection mandate.

3. Objectives

3.1 Main Objective:

To conduct a comprehensive, participatory assessment of the institutional, organizational, and operational capacities of Ministries of Women and Human Rights Development in Puntland, Hirshabelle, and Galmudug regarding their mandate on Child Protection (CP) and Gender-Based Violence (GBV), in order to inform a targeted, long-term capacity strengthening strategy.

3.2 Specific Objectives:

- For Hirshabelle and Galmudug, conduct a full assessment to map and analyze the existing legal, policy, and institutional frameworks governing CP, and GBV.

- For Puntland, review, update, and validate the findings of the 2022/2023 capacity assessments as they pertain to the MoWHRD's CP and GBV mandate.

- To assess the internal governance, management, and coordination structures of the target ministries, including their planning, budgeting, and information management systems (IMS) for protection-related work.

- To evaluate the human resource capacity (workforce) of the ministries, assessing staffing levels, technical knowledge, skills, and attitudes related to survivor-centered CP and GBV case management, and psychosocial support.

- To map and assess the functionality of existing service delivery mechanisms and referral pathways between the ministries, and with non-governmental actors, for CP and GBV survivors.

- For all the three states, develop a detailed, costed, and phased capacity strengthening plan that provides actionable recommendations for government, SC, and other partners.

- To provide evidence-based recommendations to support harmonized donor engagement and resource mobilization for the capacity development of partner line ministries at the sectoral level.

4. Scope of Work

4.1 Geographic Scope:

The assessment will be conducted in the federal member states of Puntland, Hirshabelle, and Galmudug. The institutional focus will be exclusively on the MoWHRD in each state. The assessment will further seek to identify and engage with the specific departments within each MoWHRD that hold the direct mandate for Child Protection and GBV The specific locations for primary data collection will be determined during the inception phase based on accessibility, security, and the presence of ministry personnel.

4.2 Thematic Scope: Key Assessment Domains

The assessment will be structured around the following five core domains of capacity with a specific focus on the child protection systems strengthening functions of the ministry:

| Domain | Core Focus Areas of Inquiry |
| --- | --- |
| 1. The Enabling Environment (Policy & Legal Frameworks) | - Analysis of existing laws, policies, and strategies related to CP and GBV. - Alignment of state-level frameworks with federal policies and international standards (e.g., UNCRC). - Level of government commitment and political will to advance CP and GBV agendas. |
| 2. Institutional Capacity & Governance | - Clarity of mandates, roles, and responsibilities within the ministry, particularly for CP and GBV functions - Effectiveness of internal and inter-ministerial coordination mechanisms (e.g., working groups). - Functionality of planning, monitoring, and reporting systems. - Capacity for information management (e.g., use of CPIMS+/GBVIMS+ or other data systems). - Linkages with community-based protection structures and informal/traditional dispute resolution mechanisms relevant to child protection. |
| 3. Human Resources (Workforce) Capacity | - Assessment of staffing levels, organograms, and job descriptions for protection-related roles. - Evaluation of staff knowledge, skills, and competencies in core areas: case management, survivor-centered principles, MHPSS, and child-friendly communication. - Availability and quality of professional development, training, and supportive supervision. - Staff motivation, retention, and well-being (burnout prevention). |
| 4. Service Delivery & Operational Capacity | - Mapping of services provided directly by ministries (e.g., social work, legal aid). - Assessment of the quality and accessibility of these services, particularly for vulnerable groups. - Functionality and effectiveness of the referral pathway for CP and GBV cases (health, safety, psychosocial, justice). - Engagement with community-based protection structures and civil society organizations. |
| 5. Financial & Resource Management | - Analysis of budget allocation from the state for CP and GBV programming versus actual expenditure. - Processes for resource mobilization and ability to attract and manage external funding. |

5. Methodology

The assessment will employ a mixed-methods, participatory approach that combines qualitative inquiry to understand context and causation with quantitative elements to measure and compare capacity levels. This approach is designed to ensure that the findings are robust, evidence-based, and co-owned by the partner ministries. The methodology will be adapted to the specific context of each state:

- For Hirshabelle and Galmudug (Comprehensive Assessment):

A full assessment from the ground up, following all phases below.

- For Puntland (Update, Validation, and Action Planning):

A streamlined process focusing on reviewing existing data, validating its current relevance, and dedicating significant effort to a participatory action planning workshop.

Phase 1: Inception and Desk Review

- This aims to establish a foundational understanding of the current context, avoid duplication of past efforts, and finalize the assessment plan.

- A thorough desk review will be conducted of all relevant documentation, including national and state-level policies (National Development Plan, CP/GBV strategies), legal frameworks, ministry organograms, annual reports, existing case management SOPs, service mapping reports, and previous assessments. For Puntland, this review will center on the 2022/2023 capacity assessment reports. The consultant will produce a detailed Inception Report outlining the finalized methodology, sampling strategy, draft data collection tools for review, a detailed work plan, a risk mitigation plan, and ethical considerations for data collection.

Phase 2: Primary Data Collection

- A Semi-structured (KII) interview will be conducted to gather in-depth qualitative insights on institutional governance, strategic vision, policy implementation, and systemic challenges. KIIs will target high-level officials (DGs, Department Heads), technical staff within the MoWHRD, and key external partners (UN agencies, INGOs, NNGOs, CP/GBV Sub-Cluster coordinators) to understand coordination and partnership dynamics.

- FGDs will be used to explore the operational realities, day-to-day challenges, and shared experiences of ministry staff, such as social workers and case managers. This method is ideal for understanding practical workflows, peer-to-peer support, and the functionality of service delivery on the ground. Where appropriate, FGDs with community-based child protection committees will explore the interface between the ministry and community structures.

- Capacity Self-Assessment / Action Planning Workshops which are highly participatory workshops are central to the methodology.

  - In Hirshabelle and Galmudug, a facilitated participatory workshop where ministry staff score their own capacity against a predefined set of indicators, fostering ownership of the findings. These workshops will be structured using a standardized capacity assessment tool derived from the five core domains. A facilitator will guide ministry participants (from leadership to technical staff) through each indicator, prompting a group discussion to reach a consensus on a score (e.g., 1-4 scale) and, most importantly, to provide a detailed qualitative justification for their chosen score. This process co-creates a baseline understanding of strengths and areas for improvements and ensures staff ownership of the results.

  - In Puntland, this workshop will focus on presenting the validated findings from the desk review and targeted KIIs, and then shifting directly into a structured, participatory process to co-create a prioritized, costed, and phased capacity strengthening action plan.

Phase 3: Data Analysis and Triangulation

- To synthesize all data into a coherent and validated analysis. The consultant will systematically cross-verify findings from different sources (e.g., validating a low quantitative score from a workshop with qualitative explanations from KIIs and documentary evidence from the desk review).

  - Qualitative data from KIIs and FGDs will be thematically analyzed to identify emerging patterns, root causes of challenges, and opportunities.

  - Quantitative data from the self-assessment scores will be analyzed using descriptive statistics to identify and rank capacity gaps across different domains and locations.

Phase 4: Validation and Dissemination

- Validation Workshop, in each state, a workshop will be held with key ministry stakeholders and partners. The purpose is not just to present preliminary findings but to co-validate the analysis and collaboratively refine the proposed recommendations. This step is crucial for ensuring the final report is accurate, relevant, and supported by the primary stakeholders who will be responsible for its implementation.

- Final Reporting: Incorporation of feedback from the validation workshops into the final, high-quality report and the detailed Capacity Strengthening Plan.

6. Key Deliverables

- Inception Report- Submitted within 10 days of contract signing, outlining the detailed methodology, tools, and work plan.

- Draft Assessment Report- A comprehensive draft report of the findings and analysis for review by SC and key partners.

- Validation Workshop Report- A brief report summarizing the proceedings and key feedback from the validation workshops.

- Final Comprehensive Assessment Report- A final, high-quality report (max 40 pages, excluding annexes) detailing the full assessment findings, analysis, and conclusions. The report must include:

  - An executive summary.

  - Detailed analysis against each of the five thematic domains.

  - Annex: An actionable Capacity Strengthening Plan with clear, prioritized recommendations for the short-term (1 year), medium-term (2-3 years), and long-term (4-5 years).

- PowerPoint Presentation: A concise summary of the key findings and recommendations for briefing senior management, donors, and government counterparts.

6. Consultant Qualifications and Experience

The ideal consultant(s) will possess the following qualifications and competencies:

Essential Qualifications:

- Master’s degree in social sciences, Development Studies, Public Administration, Human Rights, or a related field.

- A minimum of 7-10 years of professional experience in international development, with a significant focus on institutional strengthening and capacity development of government bodies.

- Proven, extensive experience conducting institutional capacity assessments for government ministries, preferably in fragile or post-conflict contexts. (Evidence of at least two similar previous assignments is required).

- Deep technical expertise in Child Protection and/or Gender-Based Violence systems strengthening.

- Demonstrated experience working in Somalia or the Horn of Africa, with a strong understanding of the political, social, and institutional landscape.

- Excellent analytical, facilitation, and participatory methodology skills.

- Outstanding report writing skills in English, with the ability to produce high-quality, concise, and actionable reports.

Desirable Qualifications:

- Previous experience working directly with the Ministries of Women and Human Rights Development (MoWHRD) in Somalia's Federal Member States.

- Familiarity with donor requirements for capacity-building programs (e.g., NORAD).

- Proficiency in the Somali language is a strong asset.