Federal Republic of Somalia

Ministry of Transport and Civil Aviation “MoTCA”

Somalia Horn of Africa Infrastructure Integration Project (SHIIP)

Terms of Reference (TOR) for Consultancy Services to Develop National Road Safety Strategy and Action Plan

December, 2025

TABLE OF CONTENTS

1)	BACKGROUND & ROAD SAFETY CHALLENGES	1

2)	THE PROJECT	3

3)	OBJECTIVE OF THE ASSIGNMENT	3

4)	SCOPE OF WORK FOR DEVELOPING NRSAP	4

4.1. Review, Assessment and Diagnostics	4

4.2. Strategic Planning	5

4.3. Road Safety Action Plan	5

4.4	Design Monitoring, Evaluation, and Reporting System	7

4.5	Investment plan and Resource Mobilization	7

4.6	Stakeholder Engagement and Capacity Building	7

5)	EXPECTED OUTPUTS AND SCHEDULE OF DELIVERABLES AND PAYMENTS	8

6)	PAYMENT SCHEDULE	9

7)	QUALIFICATIONS OF THE KEY PERSONNEL	9

8)	ESTIMATED STAFF INPUTS	13

9)	REPORTING ARRANGEMENT	14

9) OBLIGATIONS OF THE CLIENT (MoTCA)	14

9.1 Documents and Reports	14

9.2 Liaison	15

10) CONSULTANTS’ OBLIGATIONS	15

# BACKGROUND & ROAD SAFETY CHALLENGES

Somalia’s transport infrastructure has deteriorated due to decades of civil conflict and underinvestment, resulting in inadequate road networks, limited airport facilities, and poor maritime transport. These gaps restrict economic development and access to essential services, with 90% of the population relying on unsafe and poorly maintained roads.

Somalia’s high rates of road deaths, serious injuries, and economic losses are effects not the core problem. They stem from two root challenges:

- Weak enforcement and limited public awareness contribute to risky behaviors—such as speeding and poor seat-belt and helmet use resulting in frequent, severe crashes.

- Inadequate coordination among government agencies and stakeholders responsible for road safety compounded by lack of reliable crash data and fragmented data systems between police and health sectors

  - results in non-selective investment and weak planning

  - produces deficient infrastructure (poor road conditions, inadequate markings, weak safety features)

  - drives lane-departure and intersection collisions, night-time crashes due to low visibility, and increased pedestrian injuries.

In response to these challenges, the Ministry of Transport and Civil Aviation (MoTCA), as the lead government authority with the official mandate for road safety, recognizes the urgent need to develop and implement a comprehensive Road Safety Strategy and National Action Plan for Somalia. This initiative will provide a clear road map to:

- Analyze current road safety data to understand the scope of the problem and identify data gaps.

- Identify critical risk factors such as speeding, driver behavior, road infrastructure, and enforcement weaknesses.

- Engage relevant stakeholders – MOTCA, the Ministry of Public Works, Reconstruction, and Housing, the Somali Police Force, the Ministry of Health, Local Government (Municipalities, District Offices), transport operators, civil society, and road users – to ensure inclusive input and ownership.

- Align the strategy with international best practices and standards (e.g., UN Decade of Action, Safe System Approach) while tailoring to Somalia’s local context.

- Establish monitoring and evaluation mechanisms to track progress and ensure continuous improvement.

- Collaborate with international partners such as the World Bank and GRSF to access technical expertise, global tools, and financial resources.

The Road Safety Strategy and Action Plan will play a pivotal role in:

- Raising public awareness of road safety,

- Promoting responsible driving culture,

- Reducing fatalities and serious injuries,

- Enhancing traffic management,

- Increased investment and

- Contributing to national development and prosperity.

By preparing the strategy and action plan proactively, MoTCA seeks to improve result focus, save lives, protect vulnerable road users, and build a safer transport system for Somalia.

# THE PROJECT

Somalia - Horn of Africa Infrastructure Integration Project” (SHIIP), which is funded by the World Bank, is part of a larger program aimed at enhancing connectivity among the countries in Horn of Africa and improving access to seaports, facilitation of domestic and regional trade and economic integration, and road safety.  The project is aligned with Somalia's National Development Plan (SNDP) and aims to enhance regional connectivity and resilience through strategic infrastructure development. The project's overarching goal is to foster economic growth and strengthen governance by preparing a spatially coordinated investment pipeline of economic corridor projects and enhancing the federal government's management of selected sectors.

# OBJECTIVE OF THE ASSIGNMENT

The main objective of this assignment is to support Somalia to achieve sustainable, life-saving impact on road safety by preparing a Safe System–based national strategy and action plan and strengthening institutional capacity, aligned with the National Transport Policy and informed by the Road Safety Management Review (RSMR) report.

- National Strategy & Action Plan. Develop and secure Government endorsement of a results-focused National Road Safety Strategy and a prioritized, sequenced, and costed National Road Safety Action Plan (NRSAP) with time-bound national targets; a performance framework (baselines, KPIs, monitoring and learning); and a clear accountability architecture (strengthened lead agency and inter-ministerial coordination). The NRSAP will translate policy into implementable measures across safe roads & mobility, safe speeds, safe vehicles, safe road users, and post-crash care; identify sustainable financing options; and advance enabling legislation and enforcement to close policy-to-action, coordination, financing, data, and legal/regulatory gaps.

- Capacity Building. Strengthen core institutional management functions to secure and scale results: clarify roles and mandates; build competencies for program management, data systems (police–health integration, crash database, routine performance reviews), evidence-based enforcement, communications, and post-crash care; and equip the de-facto road safety lead agency and key ministries with the tools, procedures, and partnerships needed to implement, monitor, and update the NRSAP.

The specific objectives include:

- Assess the current road safety situation, including data, frameworks, laws, enforcement, infrastructure, vehicle safety, and post-crash care. Benchmark against international best practices.

- Strengthen institutional and governance frameworks by clarifying roles, improving coordination, and recommending sustainable financing mechanisms.

- Develop a national road safety strategy with a long-term vision, clear goals, and priorities aligned with global commitments and tailored to national needs.

- Prepare a detailed, costed, and time-bound action plan with defined interventions, responsibilities, monitoring, and opportunities for capacity building.

- Engage stakeholders through consultations, build consensus, and facilitate capacity development across all sectors involved in road safety.

- Align strategy and action plans with international frameworks (UN Global Plan, SDGs, Safe System Approach) and seek international partnerships and funding.

- Deliver an implementation and monitoring framework, proposing data-driven mechanisms, measurable indicators, and guidance for regular reviews and updates.

# SCOPE OF WORK FOR DEVELOPING NRSAP

Based on the findings of a Somalia road safety management review (in progress), the consultant needs to prepare a national Strategy and action plan (sample template will be shared by the Employer) and an investment plan. The consultant(s) shall review and follow up on an investigation into challenges that the RSMR will identify, including but not limited to the following tasks. All recommendations and actions will align with the Safe System principles outlined above.

## 4.1. Review, Assessment and Diagnostics

The consultant(s) shall conduct not limited to but the following activities to supplement the results of a Somalia road safety management review and to prepare a national action plan, including coordination for consultations with key delivery agencies and stakeholders.

4.1.1 Existing Road Safety Data and Systems

- Collect and analyze five years of national crash, fatality, and serious injury data through police records, hospital data, population census, and relevant agency’s data. The data should be categorized by at least passenger cars, heavy vehicles, two-wheelers, and, three-wheelers, and non-motorized transport. Data collection should ensure a nationally representative sample.

- Identify gaps in data quality, underreporting, and institutional arrangements for data sharing and analysis. Referenced data should include at least WHO, IHME Global Burden of Disease, and local/international estimates etc.

- Conduct hazardous road location (HRL) analysis based on collected data and any relevant supplemental information.

- Assess current road safety data collection procedures and challenges through stakeholder consultations.

4.1.2 Legislative and Policy

- Assess the legal and regulatory framework governing road safety (e.g., traffic laws, behavioral aspects including safety performance indicators, enforcement, penalties).

- Identify gaps and recommend improvements to strengthen the legislative environment

4.1.3 Institutional Capacity

- Identify and engage key stakeholders (government, civil society, private sector, development partners and communities).

- Evaluate the capacity of agencies responsible for road safety management, including coordination mechanisms.

- Review the existence and effectiveness of a (de facto) lead road safety agency or council.

## 4.2. Strategic Planning

4.2.1 Vision, Goals, and Targets

- Facilitate stakeholder workshops to define a national vision for road safety.

- Establish national baseline safety performance indicators on speed compliance, helmet wearing, seatbelt use, drink driving, and mobile phone use while driving.

- Prioritize resolving high-risk corridors, improving the safety and mobility of the most vulnerable road users, and addressing behavioral risk factors by combining infrastructure improvements with enforcement measures.

- Set measurable short- (less than a year), medium- (3–5 years), and long-term (more than 5 years) targets (e.g., reduction in fatalities, improved safety for vulnerable road users).

4.2.2 Development of Road Safety Strategy

- Develop a road safety strategy, addressing identified challenges and priorities.

- Integrate cross-cutting issues such as climate resilience, gender, and universal access

## 4.3. Road Safety Action Plan

The consultant(s) shall prepare the strategy and action plan for 2026-2030, make recommendations with specific scopes and methodologies in the following areas of actions based on road safety pillars, tailored to Somalia’s context, in accordance with the road safety management review findings.

4.3.1 Road Safety Management

- Develop and update Accident report form and other safety performance data in line with WHO and African Road Safety Observatory (ARSO).

- Formalize police, health and transport data-sharing approach; suggest initial steps to develop a national road safety database with SPI baselines/targets; finalize the M&E toolkit and mid-term review of the plan.

- Priority activities to operationalize the lead agency (mandate, structure, staffing, coordination); prepare an annual work plan and budget; convert the Training Needs Assessments into a costed, multi-agency training program with mentoring/university partners.

- Advise prioritized legal and regulatory amendments (speed, helmet/seatbelt/child restraint, drink-driving, phone use etc.)

4.3.2 Safer Roads and Infrastructure

- Conduct comprehensive road safety audits and inspections on priority corridors to pinpoint high-risk locations (based on collected crash and behavioral data), using iRAP and RSA approaches targeting corridors where more than 50% of national crashes are happening. Prepare action items based on the assessment results with a focus on how to optimize the resources to get quick fatality reduction.

- Review the adequacy of current manuals that are being used to design roads, school zones and road safety audits and advise what the country should prioritize within the time frame of the action plan.

4.3.3 Safer Road Users

- design and deliver public education campaigns and enforcement addressing key behavioral risk factors such as; speeding, drink-driving, seatbelt and helmet use, while focusing on vulnerable groups like children, pedestrians, and cyclists. Advise action items on behavioral aspects based on evidenced based approaches including improving the safety of commercial motorcyclists and any other group that come up from the behavioral analysis.

- Review the current road safety curricula for schools and advise on improvement options based on safe system principles.

4.3.4 Safer Vehicles

- Review vehicle safety standards and advise on improvement options ensuring that vehicles are equipped with essential safety features.

- Advise on Somalia’s approach on regular vehicle inspections and maintenance programs and suggest action items.

4.3.5 Safe Speeds & Enforcement

- Review the speed limit and advise on action items based on safe system speed, further advise on strengthening traffic law enforcement through targeted measures such as speed management initiatives, robust drink-driving controls and use of technologies ( speed gun, automated speed enforcement

4.3.6 Post-Crash Care

- Conduct high level assessment of current Emergency medical service situation and advise action items on how to improve emergency medical services and trauma care systems for timely and effective responses to road traffic incidents.

- Review the current protocols and advise on standardized protocols for post-crash response, including first aid training for drivers and first responders, to mitigate injury severity and support recovery.

## 4.4	Design Monitoring, Evaluation, and Reporting System

4.4.1 Performance Indicators and M&E Framework

- Develop key performance indicators (KPIs) for road safety, including measures such as fatalities, injuries, and compliance rates, with methodologies connected to relevant agencies.

- Establish a monitoring and evaluation framework to track progress and the impact of actions over short-term, medium-term, and long-term targets as applicable.

## 4.5	Investment plan and Resource Mobilization

- Build a costed five-year and ten-year investment plan and identify funding partners; prepare standard Implementation Frameworks and TORs for the national road safety action plan items (based on the road safety strategy pillars), a realistic delivery schedule, and a risk/mitigation matrix; establish a document/data repository and handover procedures.

- The GRSF Calculator (https://www.globalroadsafetyfacility.org/road-safety-calculator) should be used, in addition to road safety assessments using the iRAP approach and Road Safety Audits in high-risk corridors, to validate these estimates.

- The investment plan should include cost estimates for each activity and should be able to estimate the expected reduction in fatalities resulting from the investment.

## 4.6	Stakeholder Engagement and Capacity Building

- Conduct a national training needs assessment (TNA) that should look at the capacity improvement options. Both national and municipal agencies in addition to academia should be consulted in this process. The plan should specify action items for both rural and urban areas

- Activities related to national capacity building should be proposed based on the findings of Training Needs Assessment, focusing on both the public and private sectors. These activities should also emphasize data collection and the role of academia.

- Deliver four-day residential dissemination workshops (in person) targeting policymakers, enforcement officers, civil society representatives, private sector stakeholders, academia, and media personnel. The consultant is responsible for arranging the cost estimates and all necessary logistical arrangements. The workshops will cover the fundamentals of road safety for two days and the Strategy and action plan and investment plan for one day. Local language should be used in the dissemination workshop.

# EXPECTED OUTPUTS AND SCHEDULE OF DELIVERABLES AND PAYMENTS

The consultant will be expected to deliver the following outputs within the agreed timeline. All key reports will be prepared in English and translated into Somali for official use. MoTCA, as the mandated lead authority, will review, approve, and provide feedback at each stage.

| Deliverable | Description | Due Date After Commencement |
| --- | --- | --- |
| Inception Report | - Approach and methodology - Deliverable milestones/work plan - Responsibility of each team member - Project risks and mitigation measures - Stakeholder mapping and engagement plan - Data needs etc. | Within two (2) weeks from contract effectivity. |
| Stakeholder Engagement Report | - Stakeholder identification report - Stakeholder engagement report - Stakeholder engagement findings etc. | Within four (4) weeks from contract effectivity. |
| Road Safety Diagnostic Report | - Road safety status - Data review - Institutional framework review - Review of human capacity - Funding review - Policy, legislative and regulations review - Enforcement status review - Infrastructure assessment - Review of resource mobilisation systems in place - Review of existing M&E systems - Benchmarking findings - etc. | Within nine (9) weeks from contract effectivity. |
| Training Needs Assessment Report | Capacity needs | Within twelve (12) weeks from contract effectivity. |
| National Stakeholders Workshop (4 days) Report | - Workshop report including feedback and responses - Way forward etc | Within fourteen (14) weeks from contract effectivity. |
| Draft National Road Safety Strategy, Action Plan and Investment Plan | Strategy and Action Plan with costing & interventions in addition to findings from Hazardous Road location (HRL) analysis and on-ground data | Within sixteen (16) weeks from contract effectivity. |
| Final Reports 1. Somalia National Road Safety Strategy 2. Somalia National Road Safety Action Plan 3. National Road Safety Investment Plan (linked to the Action Plan) | Somali + English versions with annexes | Within twenty-one weeks (21) weeks from contract effectivity. |

# PAYMENT SCHEDULE

This shall be a lump sum contract.

The payments will be made to the Consultant(s) according to the following schedule.

| No. | Deliverable | Payment Schedule (% Contract Price) |
| --- | --- | --- |
|  | Submission and approval of the Inception Report | 20% |
|  | Submission and approval of the Diagnostic Assessment Report | 30% |
|  | Submission and approval of the Draft National Road Safety Strategy and Action Plan Reports | 30% |
|  | Submission and approval of the Final National Road Safety Strategy and Action Plan Reports | 20% |

# QUALIFICATIONS AND EXPERIENCE REQUIREMENTS FOR THE FIRM AND KEY PERSONNEL

Firm qualification and experience:

- Core business and years in business: The firm shall be registered/incorporated as a consulting firm with core business in any of the following areas: (i) Civil Engineering / Transportation Engineering; (ii) Transport Planning and Traffic Engineering; (iii) Road Safety Engineering; or (iv) Road Safety Management and Policy Development;  for a period of  at least fifteen (15) years.

- Relevant experience: The firm shall demonstrate experience in: (i) Traffic management and traffic flow studies; (ii) Road safety audits; (iii) Proficiency in crash data analysis and GIS-based mapping systems, including use of iRAP and the Global Road Safety Facility (GRSF) Calculator; (iv)  Expertise in Safe System–based, multi-sectoral approaches aligned with the UN Decade of Action; as well as experience in any of the following: (i) Behavioral and public health approaches to road safety; or (iii) Emergency response and post-crash care. Additionally, the firm should demonstrate successful execution and completion of at least one (1) assignment of a similar nature and in a similar operating environment in the last five (5) years. Details of similar assignments - Name and address of the client, scope, value, and period should be included in the Expression of interest (EOI).

- Technical and managerial capability of the firm: The firm(s) shall demonstrate as having the requisite technical capability, which shall entail a description of relevant personnel, equipment, software, etc, and managerial capacity to undertake the assignment. Key experts will not be evaluated at the shortlisting stage.

To perform the assignment, the following key personnel, as a minimum, will be required from the firm.

| Position No. | Position / Qualifications | No. of Staff |
| --- | --- | --- |
| Key Expert No. 1: | Team Leader / Road Safety Policy and Strategy Expert | 1 |
| Qualification, Experience and skills | - Master’s degree in Road Safety, Transport Policy/Management, Transport Engineering, or related disciplines. - At least 20 years of experience in road safety policy development and strategy formulation. - Proven track record in leading multidisciplinary teams on road safety projects - Strong leadership and coordination skills. - Excellent communication and stakeholder engagement abilities. - In-depth knowledge of international road safety standards and legislation. |  |
| Key Expert No. 2: | Road Safety Engineering / Infrastructure Expert | 1 |
| Qualification, Experience and skills | - Master’s degree in Civil Engineering or Transportation Engineering. - Minimum 15 years of experience in road safety engineering or traffic infrastructure projects. - Familiarity with road design standards and safety assessment methods. - Proficiency in traffic simulation software and engineering design software. - Strong analytical and problem-solving skills. |  |
| Key Expert No. 3: | Crash Data and Analysis Expert | 1 |
| Qualification, Experience and skills | - Master’s degree in Statistics, Data Science, or a related field. - At least 10 years of experience in crash data analysis and traffic safety research. - Experience with data collection and management systems. - Advanced data analysis skills, including proficiency in statistical software (e.g., R, SPSS, or Python). - Ability to translate data findings into actionable recommendations. |  |
| Key Expert No. 4: | Traffic Policing and Enforcement Specialist | 1 |
|  | - Bachelor’s degree in Criminal Justice, Public Policy, or a related field. - At least 15 years of experience in traffic law enforcement or policing strategy development. - Understanding of traffic enforcement technologies and methodologies. - Expertise in policy formulation and application related to traffic enforcement. - Strong interpersonal and communication skills for training and collaboration. |  |
| Key Expert No. 5: | Traffic Policing and Enforcement Specialist | 1 |
|  | - Medical degree or Master’s in Public Health or Emergency Management. - At least 15 years in emergency care, trauma management, or road safety response systems. - Experience working with first responders and emergency services. - Knowledge of emergency response protocols and medical best practices. - Strong organizational and communication skills for coordinating multi-agency efforts. |  |
| Key Expert No. 6: | Road User Behavior, Education and Communication Expert | 1 |
|  | - Master’s degree in Psychology, Sociology, Communication, or Education. - At least 15 years of experience in road user behavior research or public awareness campaigns. - Excellent communication and presentation skills. - Ability to design and implement educational programs and behavior change initiatives. |  |
| Key Expert No. 7: | Road User Behavior, Education and Communication Expert | 1 |
|  | - Master’s degree in Public Administration, Governance, or a related field. - Minimum of 15 years of experience in governance and institutional capacity building. - Strong understanding of institutional frameworks and governance processes in transportation. - Excellent stakeholder engagement and negotiation skills. |  |
| Key Expert No. 8: | Transport Economics and Financing Expert | 1 |
|  | - Master’s degree in Transport Economics, Finance, or related field. - At least 10 years of experience in transport economics or transport financing projects. - Experience in cost-benefit analysis and economic modeling. - Strong analytical and quantitative skills. - Ability to communicate complex economic concepts to diverse audiences. |  |
| Key Expert No. 9: | Environmental and Social Impact Assessment Expert | 1 |
|  | - Master’s degree in Environmental Science, Environmental Engineering, or Social Sciences. - At least 10 years in conducting environmental and social impact assessments for infrastructure projects. - Proficiency in relevant impact assessment methodologies and regulatory requirements. - Excellent report writing and communication skills. |  |
| Key Expert No. 10: | Monitoring and Evaluation (M&E) Specialist | 1 |
|  | - Master’s degree in Development Studies, Social Sciences, or a related field. - At least 10 years of experience in monitoring and evaluation of projects, preferably in road safety or transportation sectors. - Strong expertise in M&E frameworks, tools, and data analysis. - Proficient in project management and report writing, with excellent analytical skills. |  |
| Key Expert No. 11: | Translator: English and Somalia languages | 1 |
|  | - Bachelor’s degree in Translation, Linguistics, or a related field. - A minimum of 3 years of professional translation experience between English and Somali, preferably in technical fields such as transportation, public policy, or road safety. - Experience in localization and cultural adaptation of documents. - Excellent proficiency in both written and spoken English and Somali. - Strong attention to detail and ability to maintain the original meaning and context during translation. |  |

# ESTIMATED STAFF INPUTS

The contracted consulting firm(s) will provide the key experts listed above including any support staff required.

Tabulated below are the estimated inputs by the key staff.

| No. | Key Expert | Estimated Person-Months |
| --- | --- | --- |
| 1 | Team Leader / Road Safety Policy and Strategy Expert | 5 |
| 2 | Road Safety Engineering / Infrastructure Expert | 3 |
| 3 | Crash Data and Analysis Expert | 2 |
| 4 | Traffic Policing and Enforcement Specialist: | 2 |
| 5 | Post-Crash Response / Emergency Care Expert | 2 |
| 6 | Road User Behavior, Education and Communication Expert | 2 |
| 7 | Institutional and Governance Expert | 2 |
| 8 | Transport Economics and Financing Expert | 2 |
| 9 | Environmental and Social Impact Assessment Expert | 1 |
| 10 | Monitoring and Evaluation (M&E) Specialist | 1 |
| 11 | Translator: English and Somalia languages | 1 |
|  | Total | 23 |

# REPORTING ARRANGEMENT

The overall responsibility for administration and coordination of the RSMR and NRSAP shall be with MOTCA and SHIIP PCU. In the conduct of its work, the consultant(s) shall cooperate fully with MOTCA.

- The consultant will report functionally to the Director General, Ministry of Transport and Civil Aviation (MoTCA), which holds the official mandate for road safety in Somalia.

- The consultant will report contractually to the Director General, Ministry of Public Works, Reconstruction and Housing.

- Day-to-day coordination of the consultancy assignment will be carried out with the Director General and the Technical Focal Point for Road Safety, MoTCA.

- The consultant will provide regular progress updates and reports to MoTCA, aligned with the agreed timeline and deliverables.

- Periodic review meetings will be held with MoTCA and the World Bank/GRSF to track progress and resolve challenges.

- MoTCA will ensure inter-ministerial coordination and facilitate access to relevant data and stakeholders.

- All reports shall be submitted in both hard copy and soft copies.

- Collected data should be submitted in Excel in addition to other relevant formats.

- All reports should be submitted in English language.

# 9) OBLIGATIONS OF THE CLIENT (MoTCA)

## 9.1 Documents and Reports

- MoTCA shall provide the consultant(s) with the Somalia Road Safety Management Review (in progress), which will serve as the baseline document for developing the National Road Safety Strategy and Action Plan and Investment Plan.

- MoTCA shall supply all relevant available data, reports, and official information required for the assignment and shall provide necessary facilitation for the consultant(s) to perform their duties.

- MoTCA shall retain the right to review and formally approve all reports and deliverables before submission to the World Bank/GRSF.

- All official data shared (e.g., crash data, PRA statistics, hospital records) shall remain the property of the Government of Somalia and cannot be used for any other purposes without MoTCA’s written consent.

- The consultant(s) shall be responsible for procuring and covering costs of required software, workspace, models, maps, manuals, and other materials necessary for effective delivery of the assignment.

- The consultant(s) shall archive all records used during the assignment for a minimum of five (5) years before destruction or disposal, in accordance with international best practices.

## 9.2 Liaison

- MoTCA shall provide official liaison with other ministries, agencies, and departments to introduce the consultant(s) and ensure access to stakeholders.

- MoTCA shall facilitate coordination between the consultant(s) and relevant institutions at both federal and state levels to ensure smooth data collection and stakeholder engagement.

# 10) CONSULTANTS’ OBLIGATIONS

- The consultant(s) shall be fully responsible for all logistics arrangements, including:

  - VISAs, work permits, and travel insurance.

  - International and domestic travel, accommodation, and daily transport.

- The consultant(s) shall be responsible for data collection and analysis, including:

  - Designing and administering questionnaires.

  - Conducting stakeholder interviews and focus group discussions.

  - Ensuring ethical data collection and protection of sensitive information.

- The consultant(s) shall arrange and confirm appointments with stakeholders in coordination with MoTCA.

- The consultant(s) shall provide all necessary equipment, software, and tools (e.g., laptops, GIS software, statistical packages) required for the assignment.

- The consultant(s) shall ensure that all deliverables are produced in English, and are of professional quality acceptable to MoTCA and the World Bank/GRSF.

- The consultant(s) shall maintain the confidentiality of all government data and shall not disclose or use such data for any other purposes without MoTCA’s prior written consent.

African Development Bank. (2016). Somalia Transport Sector Needs Assessment and Investment Programme(Online). (Accessed online on 16 December 2024). Available fromhttps://www.afdb.org/fileadmin/uploads/afdb/Documents/Publications/Somalia_Transport_Sector_Needs_Assessment_and_Investment_Programme.pdf