Request for Proposal

[Consultancy Work]

RFP DOCUMENT # [JL/ 36572]

RFP Issue Date:  11/07/2024]

Proposal submission DEADLINE: [26/07/2024]

CARE SOMALIA/SOMALILAND

ISKUFILAN FAANOOLE

Kismayo, Somalia

Confidential Document

Prepared by

CARE ®

Table of Contents

1.	ABOUT CARE	2

2.	GENERAL CONDITIONS and CLAUSES	2

2.1.    	CARE’s GENERAL CONDITIONS	2

2.2.	CONFIDENTIALITY/ NON-DISCLOSURE	3

2.3.	PUBLICITY	3

2.4.	LIABILITY	3

2.5.	FORCE MAJEURE	3

2.6.	ERRORS AND OMISSIONS	4

2.7.	OWNERSHIP OF WORK	4

2.8.	CONFLICT OF INTEREST	4

3.	COMPANY PROFILE & BIDDER’S DECLARATION	5

3.1.	COMPANY PROFILE	5

3.2.	BIDDER’S DECLARATION	6

4.	CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL	7

4.1.	PROPOSOSAL GUIDELINES	7

4.2.	PROJECT PURPOSE AND DESCRIPTION	7

4.3.	PROJECT OVERVIEW	8

4.4.	PROJECT REQUIREMENTS	9

4.5.	PROJECT TIMELINE	11

4.6.	EVALUATION CRITERIA	11

# ABOUT CARE

At CARE, we seek a world of hope, inclusion, and social justice, where poverty has been overcome and people live with dignity and security.

This has been our vision since 1945, when we were founded to send lifesaving CARE Packages® to survivors of World War II. Today, CARE is a leader in the global movement to end poverty. We put women and girls in the center because we know we cannot overcome poverty until all people have equal rights and opportunities. In 2019, CARE worked in 100 countries and reached 70 million people with an incredible range of life-saving programs.

To know more about CARE, visit: https://www.care.org/our-work/

# GENERAL CONDITIONS and CLAUSES

# CARE’s GENERAL CONDITIONS

The enclosed document is not an offer to contract, but a solicitation of a vendor’s proposed intent.  Acceptance of a proposal in no way commits CARE to award a contract for any or all products and services to any vendor.

CARE reserves the right to make the following decisions and actions based on its business interests and for reasons known only to CARE:

- To determine whether the information provided does or does not substantially comply with the requirements of the RFP.

- To contact any bidder after proposal submittal for clarification of any information provided.

- To waive any or all formalities of bidding

- To accept or reject a proposal in whole or part without justification to the bidder.

- To not accept the lowest bid

- To negotiate with one or more bidders in respect to any aspect of the submitted proposal.

- To award another type of contract other than that described herein, or to award no contract.

- To enter into a contract or agreement for purchase with parties not responding to this RFP

- To request, at its sole discretion, selected Vendors to provide a more detailed presentation of the proposal.

- To not share the results of the bids with other bidders and to award contracts based on whatever is in the best interest of CARE.

Any material statements made orally or in writing in response to this RFP or in response to requests for additional information will be considered offers to contract and should be included by vendor in any final contract.

# CONFIDENTIALITY/ NON-DISCLOSURE

All information gained by any vendor concerning CARE work practices is not to be disclosed to anyone outside those responsible for the preparation of this proposal.  Any discussion by the vendor of CARE’s business practices could be reason for disqualification.  CARE, at their discretion, reserves the right to require a non-disclosure agreement.

Reciprocally, CARE commits that information received in response to this RFP will be held in strict confidence and not disclosed to any party, other than those persons directly responsible for the evaluation of the responses, without the express consent of the responding vendor.

Finally, the information contained within this RFP is confidential and is not to be disclosed or used for any other purpose by the vendor.

# PUBLICITY

Any publicity referring to this project, whether in the form of press releases, brochures, or photographic coverage will not be permitted without prior written approval from CARE.

# LIABILITY

The selected vendor(s) will be required to show proof of adequate insurance at such time as CARE is prepared to procure the services.  The participating vendor will also be required to indemnify and hold harmless CARE for, among other things, any third-party claims arising from the selected vendor’s acts or omissions and will be liable for any damage caused by its employees, agents or subcontractors.

# FORCE MAJEURE

- Neither Party shall be responsible for a performance that is delayed, hindered, or is rendered inadvisable, commercially impracticable, illegal, or impossible by a “Force Majeure Event.” A Force Majeure event includes, without limitation, an act of nature, a pandemic, emergency, civil unrest or disorder, actual or threatened terrorism, war, fire, governmental action or interference of any kind, power or utility failures, strikes or other labor disturbances, a health warning issued by the Center for Disease Control (or similar agency), any other civil or governmental emergency and/or any other similar event beyond a Party’s reasonable control.

- The Party that seeks to invoke this Force Majeure provision (the “Affected Party”) shall provide the other Party (the “Unaffected Party”) with a written notice within ten (10) days of the date the Affected Party determines a Force Majeure Event has occurred.

# ERRORS AND OMISSIONS

CARE expects the vendor will provide all labor, coordination, support, and resources required based on the vendor’s proposal and corresponding final SOW.  No additional compensation will be available to the vendor for any error or omission from the proposal made to CARE.  The only exclusions are add-ons, deletions, and/or optional services for which the vendor has received written authorization from CARE.

# OWNERSHIP OF WORK

All work created during this evaluation must be original work, and no third party should hold any rights in or to the work.  All rights, title and interest in the work shall be vested in CARE.

# CONFLICT OF INTEREST

CARE encourages every prospective Supplier to avoid and prevent conflicts of interest, by disclosing to CARE if you, or any of your affiliates or personnel, were involved in the preparation of the requirements, design, specifications, cost estimates, and other information used in this RFP.

# COMPANY PROFILE & BIDDER’S DECLARATION

Bidders are requested to complete this form, including the Company Profile and Bidder’s Declaration, sign it and return it as part of your proposal. No alterations to its format shall be permitted and no substitutions shall be accepted.

# COMPANY PROFILE

Table 4.1.A Previous Work with CARE

| Have you already had previous transactions with CARE? | Yes | No |
| --- | --- | --- |
| If marked “Yes”, please provide the year of the latest transaction with CARE and the requirement that was delivered. (This is to inform everyone that this information is for system checking only. This will not be part of any evaluation process.) |  |  |
| If you marked, “No” on the table above, please answer the Table 4.1.A. below: |  |  |

Table 4.1.B Other Information

| Item Description | Detail(s) |
| --- | --- |
| Legal name of bidder |  |
| Legal Address, City, Country |  |
| Website |  |
| Year of Registration |  |
| Company Expertise |  |
| Bank Information (Please answer below) |  |
| Bank Name: |  |
| Bank Address: |  |
| IBAN: |  |
| SWIFT/BIC: |  |
| Account Currency: |  |
| Bank Account Number: |  |

| Previous relevant experience: 3 contracts |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name of previous contracts | Client & Reference Contact Details | Contract Value | Period of activity | Types of activities undertaken |

# BIDDER’S DECLARATION

| Yes | No |  |
| --- | --- | --- |
|  |  | Ethics: By submitting this Proposal/Quote, I/we guarantee that the bidder has not engaged in any improper, illegal, collusive, or anti-competitive arrangements with any competitors; has not directly or indirectly contacted any buyer representative (aside from the point of contact) or gather information regarding the RFP; and has not attempted to influence or offer any type of personal inducement, reward, or benefit to any buyer representative. |
|  |  | I/We affirm that we will not engage in prohibited behavior or any other unethical behavior with CARE or any other party. We also affirm that we have read the general clause and conditions included in this RFP and that we will conduct business in a way that avoids any financial, operational, reputational, or other undue risk to CARE. |
|  |  | Conflict of interest: I/We warrant that the bidder has no actual, potential or perceived Conflict of Interest in submitting this Proposal/Quote; or entering into a Contract to deliver the Requirements. CARE Procurement's Point of Contact will be notified right away by the bidder if a conflict of interest occurs during the RFP process. |
|  |  | Bankruptcy: l/We have not declared bankruptcy, are not involved in bankruptcy or receivership proceedings, and there is no judgment or pending legal issues that could hinder the ability to conduct business. |
|  |  | Offer Validity Period: I/We confirm that this Proposal/Quote, including the price, remains open for acceptance for the Offer Validity. |
|  |  | I/We understand and recognize that you are not bound to accept any proposal you receive, and we certify that the goods offered in our Quotation are new and unused. |
|  |  | By signing this declaration, the signatory below represents, warrants and agrees that he/she has been authorized by the Organization/s to make this declaration on its/their behalf |

| Supplier Name: |  |
| --- | --- |
| Title/Designation: |  |
| Company Name: |  |
| Date: |  |
| Signature |  |

# CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL

# PROPOSOSAL GUIDELINES

This Request for Proposal represents the requirements for an open and competitive process.

All vendors must provide written notification via email to (som.procurement@care.org) of their intent to participate, or not to participate in the bidding process by July 26th 2024.

Proposals will be accepted until July 26th, 2024. in case you may need any clarification on the TOR you can delivered via email solely to Hassan Gullet Ibrahim.Gullet@care.org.] no later than 26/07/2024.

Any proposals received after this date and time will not be accepted.  All proposals must be signed by an official agent or representative of the company submitting the proposal.

If the organization submitting a proposal must outsource or contract any work to meet the requirements contained herein, this must be clearly stated in the proposal.  Additionally, all costs included in the proposals must be all-inclusive to include any outsourced or contracted work. Any proposals which call for outsourcing or contracting work must include the name and description of the organizations being contracted.

All costs must be itemized to include an explanation of all fees and costs.

Contract terms and conditions will be negotiated upon selection of the winning bidder for this RFP.  All contractual terms and conditions will be subject to review by the CARE legal department, and will include scope, budget, schedule, and other necessary items pertaining to the project.

You must respond to every subsection including statement, question, and/or instruction without exception.

Any verbal information obtained from, or statements made by representatives of CARE shall not be construed as in any way amending this RFP.  Only such corrections or addenda as are issued in writing by CARE to all RFP participants shall be official.  CARE will not be responsible for verbal instructions.

# PROJECT PURPOSE AND DESCRIPTION

CARE is issuing this RFP (Request for Proposal) soliciting qualified bidders to submit proposals intended for ENGINEERING CONSULTANCY SERVICES

This RFP is an invitation to bid, not an offer of contract.  Bidders must submit a response that complies with the minimum requirements contained herein.

# PROJECT OVERVIEW

CARE is seeking a provider to submit proposals intended for the

TERMS OF REFERENCE

FOR

ENGINEERING CONSULTANCY SERVICES

| Services required | Consultancy Services for the development of Architectural plans/design, Bill of Quantities, Bill of materials for 20 new girls’ school and construction/renovation of 296 twin toilets in 74 schools to be constructed in Jubaland, Southwest, Galmudug, Puntland, Hirshabelle and Benadir Regional Administration of the Federal Government of Somalia. Supervision and monitoring of all ongoing construction works across the six states including Benadir Regional Administration. |
| --- | --- |
| Location | Mogadishu – Somalia |
| Reporting to | Chief of Party – GPE |
| Time input | 480 working days |

Background

The Federal Government of Somalia through the Ministry of Education, Culture and Higher Education secured funding from the Global Partnership for Education (GPE) for Girls’ Education Accelerator (GEA) grant. CARE International is the Grant Agent for this grant. The GEA is designed to contribute to the achievement of the government priorities reform defined in the 2023 Partnership Compact, which is aligned with the priorities of the Education Sector Strategic Plan (2022-2026). The GEA grant is a three-year grant intended to enhance equitable access to quality and inclusive education in rural and urban areas by addressing supply and demand barriers, particularly those related to gender and social inclusion. The GEA program aims to address gender disparities in education sector, focusing on strengthening system capacity on gender and inclusion to boost equitable access and gender-responsive and socially inclusive practices at classroom and school management levels.  The GEA will support the MOECHE and FMS MOEs to enroll an additional 41,140 vulnerable girls through various interventions.

Key objectives under outcome 1 include (i) construct 20 new girls’ schools in underserved areas with high concentration of out-of-school girls and limited or no provision of education services and (ii) provide capitation grants and special grants to maximize access for extremely vulnerable girls.  For outcome 2, the grant aims to improve girls’ learning outcomes by addressing barriers including limited availability of qualified female teachers, limited teacher capacity to implement gender-responsive teaching, lack of harmonized institutional guidance on gender for teacher training and coaching, limited institutional capacity for gender-responsive teacher training and coaching and lack of policies and guidelines on school safeguarding.

Under outcome 3, the program seeks to address barriers to gender-responsive planning and policy development / implementation including limited availability of staff qualified to serve internal resources and advocates for gender and inclusion at the MOECHE/ FMS MOEs, limited capacity at FMS MOEs level for gender-responsive and inclusive education planning and rollout of the Gender and SEND & IE policies, lack of guidelines for systematic tracking of gender and inclusion in quality assurance processes, limited tracking of gender and inclusion in institutional monitoring processes and lack of consistent guidance for incorporation of gender and inclusion in EiE.

The overall program beneficiary targets include:

15,600 vulnerable out of schoolgirls in underserved areas with the highest concentration of out-of-school girls and limited or no provision of education services will be enrolled through construction of 20 new schools for girls.

15,000 vulnerable out-of-school girls will be enrolled through capitation grants.

10,000 vulnerable out-of-school girls and girls affected by emergencies receiving 30-month special grants to enroll and remain in primary school.

1200 (60% girls) out-of-school children with severe disabilities attending special needs education through a 30-month special grant.

Description of the Locations

The GEA will support construction of new girls’ schools in each Federal Member state as indicated in the table below:

Table 1: Number of girls schools to be constructed in each state

| State | No. of schools |
| --- | --- |
| Benadir Regional Administration | 5 |
| Jubaland state | 3 |
| Galmudug | 3 |
| Southwest | 3 |
| Hirshabelle | 3 |
| Puntland | 3 |
| Total | 20 |

Selection of target districts, locations and schools will be led by MOECHE in consultation with the five FMS MOEs and BRA and the Grant Agent. The selection process will be finalized as part of the needs assessment exercise that is now on-going. The targeting procedures will include prioritization of areas with limited or no provision of education services and high concentration of out-of-school girls for construction of girl’s schools and schools without toilets for girls excluding schools already targeted by STG for renovations and expansion.

Objectives of the Consulting Services

The overall objective of the consultancy is to develop an architectural plan/design, Bill of Quantities and Bill of materials for 20 new girls’ school and 296 twin toilets in 74 target schools as well as supervision of on-going construction work across the project target locations.

The consultancy is expected to achieve the following specific results:

Produce an inception report.

Develop architectural plans/designs for construction of new schools and toilets.

Develop Bill of Quantities for construction of new schools and toilets.

Develop Bills of Materials for construction of new schools and toilets.

Supervision of school Construction as well as construction/renovation/expansion of twin toilets

Draft tender documents with the general conditions of the construction firm, standards specifications for the civil works, supplies, and construction materials for the construction of the 20 schools and 296 twin toilets in 74 target schools.

Execution of the Study

Overall approach and management of the assignment

Prior to commencement of the consultancy assignment, the Federal Ministry of Education, Culture and Higher Education (MoECHE) shall have engaged the regional states and educations partners, identified, and completed selection of target districts/locations and schools. The consultant shall undertake a desk review of all available relevant information and reports on the target districts/locations and schools leading to the attainment of the objectives of the assignment and shall, with the prior agreement of the client, do field surveys to collect primary additional information as necessary. The consultant shall cooperate with MoECHE and FMS MOEs including BRA during the mobilization period and obtain a consensus with the key stakeholders. The consultants will work with the Program Management Committee (PMC) to ensure smooth execution of the assignment.

The consultant Firm shall attach a site Engineer who will be supervising the construction work on a regular basis ensuring that the Contractor does quality works and complies with the terms of the construction contract and provide the approvals necessary for the payment of the works.

6. Reports and Schedules

6.1 General

The Consultant will prepare and submit to the client 5 copies each of the following listed reports for circulation to CARE, MOECHE and the respective Federal Member states.

6.2. Schedule of Submission of reports

The schedule for submission, from the mobilization date, is given as follows.

| # | Description |  |
| --- | --- | --- |
|  | Inception Report | 15 days upon signing contract |
|  | Architectural plans/designs | 5 days upon approval of the inception report |
|  | Bill of Quantities | 5 days upon approval of the inception report |
|  | Bill of Materials | 5 days upon approval of the inception report |
|  | Supervision plan of construction works | 5 days upon approval of the inception report |
|  | Draft designs and tender documents | 10 days upon approval of the inception report |
|  | Final reports | Upon completion of the consultancy (assignment) |
|  | Progress report of each site | As it falls due. |

Inception Report

The Inception Report shall be submitted not more than 15 days upon signing the contract. The inception report will describe the consultant's organizational work plan for carrying out the assignment as well as any important initial findings.

Final Reports

These reports will be submitted at the end of the consultancy work. The report shall be accompanied by copies of the work plan and staff scheduling chart marking clearly the progress made up to the end of the reporting period as compared with the work plan. They shall be submitted within ten days to the end of the report period.

Detailed Designs and Tender Documents

The detailed design shall be prepared including the full results of the work carried out by the consultants for the proposed subprogram. Design calculations, drawings, cost estimates, economic and financial justifications shall be presented in annexes. The report shall be submitted first in draft form and the final editions of the report will be submitted after incorporating comments by the client. Tender documents shall be prepared for each of the agreed contract packages including bidding documents and bid drawings.

7. Key Personnel and Required Qualifications

The consulting firm will fill an appropriate team with qualified members to undertake the services outlined above. The team shall include key experts with qualifications described below. The firm is welcome to propose additional experts for efficient implementation of the assignment.

Architect with MSc/BSc in Architectural Engineering or related field with at least 3-4 years of familiarity with Auto CAD,ArchiCAD and LUMION or other rendering software’s.

Civil Engineer with MSc/BSc in Civil Engineering or related field with 3-4 years of paractical experience in construction supervision and construction management or equivalent civil works.

Surveyor with MSc/BSc in Surveying or Civil Engineering with 5 years of experience in topographic and land surveying with field expertise, workined similar role in infrastructure projects.

8. Implementation Schedule

The total implementation period of the assignment phase will be 480 days from the award of the contract and mobilization. The consulting firm shall commence work within 15 days of receipt of Notice to Proceed (award of contract) and shall complete all work within a maximum period of 480 days from award of contract. The consultant shall submit a tentative proposed implementation schedule, however in the inception report the consultant shall submit a detailed work plan and implementation schedule showing dates for key activities by calendar months.

9. Responsibilities of the Consulting Firm

The consulting firm shall be able and willing to access selected target districts/location and schools for effective implementation of the consultancy terms of reference.

The Firm shall cooperate fully with the executing agency, MoECHE, FMS MOEs and CARE Somalia. The Firm shall also liaise with CARE program teams and GEA Program Management Team.

The Firm shall exercise all reasonable skill, care, and diligence in the performance of services under the Agreement and shall carry out all responsibilities in accordance with recognized professional standards.

The Firm shall consider relevant comments from the Program Team, MoECHE, FMS MOEs and shall be responsible for the accuracy of its work, conclusions and recommendations.

The Firm shall provide sufficient work power to complete the assignment within the stipulated period.

The Firm, the employees of the Firm, and any sub-contractors whilst in Somalia shall respect the laws and customs and culture of the communities.

The copyright of documents prepared by the Consultants in connection with this contract rests with the client. The Consultants may take copies of such documents but shall not use the contents thereof for any purpose unrelated to the contract without the prior written approval of the client.

The Firm shall be liable to the client for the performance of the services in accordance with the provisions of the Contract and for any loss suffered by client because of gross negligence or criminal action by the Firm.

10. Responsibilities of CARE, MOECHE and FMS MOEs.

The MoECHE, FMS MOEs and CARE here referred to as the “clients” shall assist the Consulting Firm to obtain and/or access all available reports, maps, and documents pertinent to the proposed location.

The Clients shall be responsible for all liaisons between the consultant and all other parties involved in the assignment.

The client will make decisions on all reports, recommendations and other matters properly referred to by the consultant for a decision, within such a reasonable time so as not to delay the progress of the assignment.

MoECHE and FMS MOEs shall facilitate the speedy granting to the Consultant and any of the Consultant's personnel in respect of services to be carried out in this contract: Unobstructed access to all sites and locations involved in carrying out the assignment, notwithstanding other factors, and discretion of the national and local authorities.

Evaluation Criteria

A detailed technical proposal with a detailed methodology in line with the TOR and work plan to be undertaken to fulfil the tasks mentioned in this TOR.

Updated CV detailing key qualifications of the professional team as outlined below.

Architect with MSc/BSc in Architectectural Engineering or related field with at least 3-4 years of familiarity with Auto CAD,ArchiCAD and LUMION or other rendering softwares.

Civil Engineer with MSc/BSc in Civil Engineering or related field with 3-4 years of paractical experience in construction supervision and construction management or equivalent civil works.

Surveyor with MSc/BSc in Surveying or Civil Engineering with 5 years of experience in topographic and land surveying with field expertise, workined similar role in infrastructure projects.

A Financial proposal including breakdown of the tasks to be carried out and the corresponding payments.

- At least 5 years’ experience of conducting similar assignments in Somalia.

- Should be duly registered in Somalia with valid registration documents including a valid compliance certificate.

- A sample of recently written report/work for a similar assignment. Share proof in terms of contracts or LPOs.

- Demonstrated experience and a good track record of working with government, international organizations such as international NGOs, or the UN in Somalia.

- Contact details of three references.

How to Apply

Interested firms are expected to submit their applications (technical and financial proposal), the profile of the company and updated CVs of individual team members along with the duly filled of the attached RFP form to som.procurement@care.org. Please indicate “Engineering Consultancy Services” as the subject heading not later than July 26, 2024

Please note that we are interested in firms only

| Requirement & Specs | Qty. | Unit of Measurement | Required Delivery Lead Time | Delivery Address | Contract Period |
| --- | --- | --- | --- | --- | --- |

[Provide additional requirements]

| Item # | Other Requirements |  |
| --- | --- | --- |
| 1 | Delivery Date & Time | Bidder shall deliver the goods at least ____ weeks after Contract signature. |
| 2 | Delivery Terms (incoterms) | EXW [Ex-works (Place)] |
|  |  | FCA [Free Carrier (Port)] |
|  |  | FAS [Free Along-Side Ship (Port)] |
|  |  | FOB [Free On-Board (Port)] |
|  |  | CFR [Cost, & Freight (Port)] |
|  |  | CIF [Cost, Insurance & Freight (Port)] |
|  |  | CPT [Carriage Paid-To (Place)] |
|  |  | CIP [Carriage & Insurance Paid-To (Place)] |
|  |  | DAP [Delivered at Place (Place)] |
|  |  | DPU [Delivered at Place Unloaded (Place)] |
|  |  | DDP [Delivered Duty Paid (Place)] |
| 3 | Custom Clearance (Must be linked to Incoterms at origin) | Not Applicable. Shall be done by _______________ |
|  |  | Shouldered by CARE |
|  |  | Supplier/ Bidder |
|  |  | Freight Forwarder |
| 4 | Exact Address(es) of Delivery Location | Please provide addresses |
| 5 | Warranty Period | Standard Manufacturer’s Warranty (if applicable) |
| 6 | Payment Terms | 30 Days upon Receipt of items |
| 7 | Quotation Validity | The quote needs to be valid for 90 days to cover all the days from bidding up to the award process. However, once the contract has been released, it shall be valid for the same coverage as reflected in the requirement above. |

[Provide additional requirements]

# PROJECT TIMELINE

All bidders are advised to strictly follow the below timeline as noted.

Any technical questions arising during the preparation of your response to this RFP should be submitted in writing via email to [Ibrahim.Gullet@care.org) no later than 26/07/2024.

| Schedule of Activities/ To-do | Date of the Activity/ Deadline of Submission | Responsible | Remarks |
| --- | --- | --- | --- |
| RFP Issued | 11/07/2024 | CARE |  |
| Supplier to notify CARE of intention to participate in bidding |  | Supplier | Deadlines must be strictly observed. |
| Deadline for submission of clarification questions to CARE | 23/07/2024 | Supplier | Deadlines must be strictly observed. |
| CARE to answer all clarifications | 24/07/2024 | CARE |  |
| Supplier’s Deadline of Submission of Proposal | 26/07/2024 | Supplier | Deadlines must be strictly observed. |
| Evaluation of Proposal |  | CARE |  |
| Vendor presentation (if required) |  | Supplier |  |
| Finalists selected |  | CARE | Upon notification, the contract negotiation with the winning bidder will begin immediately. |

# PROJECT REQUIREMENTS

- Technical Requirements

a.1 Technical Proposal of the Product

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Overall Proposal Suitability |  |  |
| 1 | Please see the Scope of Work and any other required specifications for this project. |  |
| 2 | Provide Delivery Lead Time |  |
| 3 | Provide after-sales service (if applicable) |  |
| 4 | Ability to provide sample (if applicable) |  |
| 5 | Provide Warranty Period |  |
|  | (Any additional requirement that is deemed necessary for “Previous Works & Awards” Category |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Previous Works and Awards |  |  |
| 1 | Provide 3 or more client experiences or testimonials (References whose environment, size, and scope are most similar to CARE. Include a summary of the work completed for each account. Include reference contact names, with telephone numbers and email addresses.) |  |
| 2 | Provide previous records of performance and service. |  |
| 3 | Provide citations and awards. This encompasses reviewing the citations and awards a vendor has received from other customers and award-giving bodies. |  |
| 4 | Provide any testimonials, survey response/s from previous buyers and/or partners. |  |
| 5 | (Any additional requirement that is deemed necessary for “Previous Works & Awards” Category. |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Technical Expertise and Organizational Experience |  |  |
| 1 | Provide 5 Availability of vendor’s representatives to call upon and consult with. |  |
| 2 | Any proof that the vendor has the Ability to render satisfactory service in this instance. |  |
| 3 | Provide Years of experience in providing the same requirement to other companies. |  |
| 4 | Provide the latest audited Financial Statement |  |
| 5 | (Any additional requirement that is deemed necessary for “Technical Expertise and Organizational Experience. |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Others |  |  |
| 1 | Provide any relative requirements which were not mentioned above. (delete if not applicable) |  |

- VALUE & COST (Financial Requirements)

(Provide below requirements, payment terms, etc., if there’s any)

See attached template (in Excel File) to be used for your financial bid.

Compliance with Requirements

|  | Yes, we will comply | No, we cannot comply | If marked as “No”, please provide counter proposal |
| --- | --- | --- | --- |
| Minimum Technical Specifications |  |  |  |
| Delivery Lead Time |  |  |  |
| Delivery Term (INCOTERMS) |  |  |  |
| Warranty Period (if applicable) |  |  |  |
| Validity of Quotation |  |  |  |
| Payment Terms (30 Days) |  |  |  |
| Other Requirements (Please specify) |  |  |  |

# EVALUATION CRITERIA

CARE will evaluate all proposals based on the following criteria.  To ensure consideration for this Request for Proposal, your proposal should be complete and include all of the following criteria:

- Overall Proposal Suitability: proposed solution(s) must meet the scope and needs included herein and be presented in a clear and organized manner

- Previous Work and Awards: Bidders will be evaluated on examples of their work pertaining to the requirement as well as client testimonials and references.

- Technical Expertise and Organizational Experience: Bidders must provide descriptions and documentation of staff technical expertise and experience. Bidders also need to provide their experiences as an organization which include but not limited to years of experiences, financial stability, expertise, and edge to other competitors.

- Value and Cost: Bidders will be evaluated on the cost of their solution(s) based on the work to be performed in accordance with the scope of this project.

Note for Country Offices (CO): The specific criteria must closely represent the objective and scope given the nature of the procurement required. Evaluation criteria reflected above can be added and or adjusted depending on the requirement and the type of purchase. The final evaluation criteria must be reflected above prior to releasing of this RFP.

CARE will review proposed budgets and pricing after the initial review of the criteria above. *