Terms of Reference (TOR) for

Smart agriculture fodder production and crop sharing initiatives with an agro-dealer in Baled hawo and Dollow districts and villages under these districts.

# Background

The Building Opportunities for Resilience in the Horn of Africa (BORESHA-NABAD) is a three-year EU-funded project that is part of the broader EU’s Peaceful and Resilient Borderlands Initiative implemented in the Horn of Africa. The Project aims to enhance the effectiveness of conflict prevention and mitigation, disaster risk reduction and management, and resilience-building in Kenya, Somalia, and Ethiopia Borderland areas that are faced with multifaceted shocks (drought, floods, conflicts/violence extremism, and diseases). We focus on strengthening resilience capacities of communities, government and businesses using mixed approaches to enable them withstand these shocks and stresses. BORESHA-NABAD is building off on past BORESHA 1, II, III, Project’s investments and lesson learned to maximize impact.

# BORESHA-NABAD Overall Goal

To enhance the effectiveness of conflict prevention and mitigation, disaster risk reduction and management, and resilience-building in cross-border communities.

## Specific Objectives to Achieve Results:

  - Disaster risk reduction and conflict prevention capacities of cross-border stakeholders and communities are strengthened: This first outcome focuses on building the capacity of community structures, fostering (horizontal) cross-border engagements, and testing their delivery and response capacity. This will be achieved with an integrated approach by linking different thematic interventions. Equally important will be to build on horizontal linkages (connections between communities and actors across borders) and establish vertical linkages (foster engagement between vulnerable groups/communities and government actors).

  - Peacebuilding is enhanced through stronger linkages between communities and local, national, and regional authorities: This outcome focuses on ensuring the community-level efforts (Outcome l) are integrated into existing mechanisms and higher-level institutions. These linkages will ensure efforts are aligned with wider government priorities and help to achieve the programme’s sustainability.

  - Women and youth in marginalized borderland communities have improved access to income generation opportunities: This outcome focuses on improving access to income generation opportunities for women and youth in marginalized borderland communities. Using a market systems approach, women and youth will be prioritized for activities such as expanding access to financial and business development services, accessing loans through formal and informal financial structures and provision of TVET training and apprentices in sectors with market demand.

  - Borderland communities are better able to adapt their livelihoods to climate change and environmental degradation: This outcome focuses on improving the communities' adaptation to climate change and environmental degradation, including climate-smart livelihood activities.

# Purpose of the TOR

The purpose of this TOR is to identify a suitable Agro-Dealer to work closely with DRC through Boresha-Nabad in delivering high-quality, demand-driven services laid to the needs of 420 Farmers. This includes providing training on sustainable agricultural practices, monitoring fertilizer and pesticide applications, facilitate access to certified seeds.

# Objectives of the TOR.

- Extension agents from the Ministry of agriculture and the Agro-dealer will jointly Train and support Livestock Common Interest Groups with farm inputs, climate smart fodder production, seed bulking and learning advocacy.

- The Agro-dealer will support crop sharing initiatives/ designed to connect poor households with farm owners to promote sustainable agricultural practices and food security in the Boresha-Nabad targeted areas.

- Catalyze agricultural Inputs by providing Certified seeds, helping and facilitating the farmers on the use of high-quality fertilizers, pesticides, and other agricultural inputs to farmers.

- Extension agents and gro-dealer will jointly Strengthen the skills and knowledge of farmers through continuous Engagement, training and support.

- Strengthen the capacity of Natural resource management committees.

- Enhance Agricultural Productivity, to Improve farmers access to training and resources that promote sustainable agricultural practices.

# Scope of Work and Methodology

. The selected Agro-Dealer will be responsible for the following tasks:

- The Agro dealer will engage with the identified 420 farmers in the Boresha-Nabad targeted locations   to ensure effective service delivery.

- To develop and implement Training and capacity building programs focusing on:

  - Climate smart Agriculture and sustainable fodder production practices which the Agro-dealer will facilitate training of 420 Farmers.

  - Agro-dealer will deliver good agricultural practice training, including but not limited to: Marketing and Farm Economics, Harvest and Post-Harvest Handling, Crop Production and Protection, Soil Management and water management.

  - Effective use of fertilizers and pesticides, The Agro-dealer will do this task based on the need and Quarterly bases.

- Provide Capacity building training on the fertilizers, pesticides, and other agricultural inputs for 420 farmers with a total of 200 hectares of land and Monitor the application of these inputs to ensure effective usage and adherence to safety standards. The purchase of Fertilizers and pesticides could be contribution from the farmers but the Agro-Dealer will provide them intensive training on the handling and application of fertilizers and pesticides.

| S/N | Description | Unit | # participants | Days | Remark |
| --- | --- | --- | --- | --- | --- |
| 1 | Refreshment of the Trainings for the Farmers | Persons | 420 farmers | 5 days each group for need base | Refreshment for 420 farmers for 5 days each group |
| 2 | Facilitators for the Training | persons | 3 facilitators | 25 days for each facilitator with the total of 75 days | 12 Framer cooperatives with a total of 300 Individuals and 8 LCIG groups with a total 120 individuals for 5 days each group. |
| 3 | Training materials needed for the capacity Building of the Farmers. | Lumpsum | 420 framers with 15 sites | 25 days for each facilitator with the total of 75 days | Training will be carried out in the field for practical and theory and the Agro-dealer should list all the materials needed for Field sessions practical and if need theory in the field. (This is need from the Agro-dealer.) |

  - Good Agriculture practices for Quarterly bases/Monthly bases.

- Supply High Quality Certified seeds to 420 Farmers. With 8 LCIG groups with 120 individuals and 12 Famer Cooperatives with 300 poor Households.

| S/N | Description | Unit | Quantity Required |
| --- | --- | --- | --- |
| 1 | Maize Seed | Kg | 900kg |
| 2 | Sorghum | Kg | 900kg |
| 3 | Sudan Grass | kg | 900kg |
| 4 | Super Napier Grass | kg | 900kg |
| 5 | Water Melon | Kg | 150kg |
| 6 | Onion | kg | 150kg |
| 8 | Capsicum | Kg | 150kg |
| 9 | Danida | kg | 150kg |
| 9 | Beans | kg | 900kg |
| 10 | Cow Beas | kg | 900kg |
| 11 | Cabbage | Kg | 150kg |

- Provide regular reports to DRC on training activities, agricultural input utilization, performance of the fodder production and other products and market access. Monthly update for the progress and performance of the crops.

- Provide Regular reports on the success stories, Impacts and human-interest stories on the LCIG groups and Farmers co-operatives individuals. Quarterly bases

# 6.Deliverables and Results

- Training Programs, Comprehensive training materials and sessions laid to farmers' needs.

- Increased Agricultural Access, Enhanced access to agricultural inputs and training for farmers.

- Monitoring Reports, Monthly reports detailing training outcomes, agricultural input usage, and market access success.

## Final Report:

a. A comprehensive and detailed final report that encompasses:

- Critical Success Factors: An in-depth analysis of the key elements contributing to the success of Agro-dealer Farmers partnership interventions.

- Stakeholder Feedback: A summary of feedback gathered from stakeholders, including participants/Farmers and community representatives, highlighting their perspectives on the effectiveness and relevance of the partnership interventions.

- Achievements: A clear presentation of tangible outcomes achieved, such as:

  - Number of farmers/TOTs who successfully Achieved on the Training manuals.

  - Documented impact stories or case studies demonstrating the transformation of participants on Climate smart Agriculture.

  - Enhanced skills and knowledge demonstrated by participants in Modern farming, marketing, and Land preparation.

- Challenges: An honest account of the challenges faced during the partnership and training phases, including logistical, cultural, or systemic barriers, and how these were addressed or mitigated.

- Recommendations: Strategic insights and actionable recommendations for enhancing future interventions. These may include scaling up successful strategies, addressing identified gaps, and fostering sustainable partnerships.

# Duration

The total expected duration to complete the assignment will be no more than 60 working days. The Agro-dealer shall be prepared to complete the assignment no later than 30th September 2025. This is subject to change based on the co- creation/kick-off meeting.

| Deliverable | Payment | Timeline |
| --- | --- | --- |
| Inception Report, ToT needs assessment report, detailed work plan and tailored training manuals | 30% of contract value upon approval of the deliverable | Two weeks upon signing the contract |
| Interim report | 40% of the contract value upon submission and approval of: - The Needs assessment report for the 420 farmers and the TOTs. - Procurement of certified seeds, Fertilizer and pesticides. - Training report for the Capacity building Extension services, mentorship report and documented critical success factors for the Agricultural services. | Six weeks upon signing of the Contract |
| Final Report | 30% upon approval of final Report A detailed final report incorporating critical success factors for Smart Agriculture interventions in the context of the tri-border region, feedback from stakeholders and highlighting achievements, challenges, and recommendations for future interventions | Twelve weeks upon signing of the contract |

# Proposed Composition of the Team

The team composition will be agreed upon in detail during the co-creation/kick-off meeting. However, the Agro-dealer are advised to propose the desired team needed to achieve the objectives of this partnership. However, we expect to have the Team Leader, Field supervisors.

## Extension service Team Leader (Full time).

The key expert proposed for the role of Project Manager/Team Leader must hold a Bachelor’s degree in Agriculture, Agronomy, Agricultural Extension, Crop Production, Soil Science, or a related agricultural field. The Agro-dealer Team Lead should have a minimum of three years of proven experience in delivering Good Agricultural Practices (GAP) training, implementing fodder production techniques, and conducting capacity-building initiatives for farmers.

The ideal candidate should demonstrate strong interpersonal, communication, and facilitation skills, and have experience working with community-based organizations, particularly in cross-border or remote rural contexts.

## Four Agronomists Supervisors (Full Time)

The key experts proposed for the position of Field Supervisors must possess a minimum Diploma in Agriculture, Agribusiness, or a related field. The field supervisors will possess at least three years of working experience in Agricultural Extension service in Somalia.

The Extension Service Field Supervisors will be responsible for providing technical support to farmers, cooperatives, and community-based agricultural groups. They must hold at least a Diploma or Certificate in Agriculture, Agronomy, Agricultural Extension, Crop Production, Soil Science, or a related agricultural field. Field supervisors should demonstrate proven expertise in agricultural planning, sustainable farming practices, climate-smart agriculture, pest and disease management, and input use efficiency.

Strong interpersonal, communication, and participatory facilitation skills are essential. The supervisors should have experience working with rural communities, farmer groups, and local institutions, especially in cross-border or pastoral/agro-pastoral contexts. Familiarity with the agro-ecological conditions and farming systems of Mandera and the wider borderlands region is highly desirable. Somali-speaking candidates are strongly encouraged to apply.

.

# Eligibility, qualification, and experience required for the Agro-dealer

The Agro-dealer Company or Consultant should possess the following qualifications:

- Must be a legally registered entity in Somalia under the Ministry of agriculture federal Somalia and Jubaland state and Has SAARIS certificate with relevant experience in agricultural support.

- Proven experience working with small scale and large-Scale farmers and providing training in sustainable agricultural practices especially on fodder production.

- Demonstrated ability to supply agricultural inputs such as fertilizers and pesticides.

- Must have operational presence in target location in Dollow and Baled -Hawa Districts.

- Experience in providing Agricultural services in Dollow and Baled-Hawa is an added advantage.

- Ability to engage effectively with Livestock Common interest groups and farm co-operatives and in the target areas.

- Capacity to manage and deploy field teams effectively to project locations.

- Ability to work effectively and deliver all reports in English.

- Experience in conducting needs assessments, designing training programs.

- Previous experience in similar projects focused on agricultural development.

# Technical supervision

The selected Agro- dealer will work under supervision of:

- Abdimajid Mohamed Abdi - Economic recovery Team Leader

- Daniel Okumu – Inclusive Markets Coordinator

- Nasri Hussein Adam – Deputy Chief of Party

- Hassan Bile Gabey- Acting Base Manager

- Location

## The consultant/firm will be expected to travel and work within the Villages/Locations under Baled Hawo and Dollow. DRC will facilitate the resources for the implementation of the Activities.

11.Travel	 Travel will be required, and the Agro-dealer will therefore be expected to arrange their own transportation, accommodation, insurance and food.

12 	Submission process

# The firm should submit a detailed technical proposal and financial proposal together with DRC recommended documentation and the firms statutory documents.

13.Evaluation of bids

All bidders will be scored on a scale from 1 - 10 for each of the below criteria.

## The Selection of the Agro-dealer will be made based on cumulative analysis (i.e., mandatory requirement and technical qualifications, financial evaluation) as follows.

14.Evaluation criteria

| Availability of Qualified Agricultural Trainers (20%) | - The Agro-dealer should submit CVs and academic/professional certificates agricultural trainers and Yeam leader with formal training and relevant field experience in Good Agricultural Practices (GAP), agronomy, or extension services. - Excellent writing skills, good data presentation, cultural sensitivity, gender balance, and adherence to humanitarian principles. - The consultant (or lead consultant in the case of a firm) has proof of at least 3 similar assignments done and reports shared |
| --- | --- |

| Demonstrated technical capability to complete the Agriculture services (25%) | - The technical proposal has a description of the consultant’s understanding of the ToR in the consultant’s own words, - The consultant has adequate personnel necessary to complete the works on time with clear roles & responsibilities - Technical proposal's objectives and scope adequately meet the objectives and scope as set out in the ToR |
| --- | --- |
| #### Proven Experience in Delivering Similar Agricultural Trainings (25%) | - The Agro-dealer should provide at least one contract showing successful implementation of relevant GAP or agricultural extension training valued at USD 5000 or more, |
| #### Monitoring, Documentation, and Impact Tracking Systems (20%) | - The Agro-dealer should demonstrate a well-established system for tracking training attendance, farmer performance, field adoption of practices, and post-training |
| Detailed work plan (10 %) | - Detailed work plan with realistic timelines and duration for the assignment |
| Total 100% |  |

DRC will conduct reference checks from at least 2 previous works as an additional mandatory requirement prior to contracting.

15.Conclusion.

This TOR outlines a comprehensive framework for the collaboration between an Agro-Dealer and DRC through Boresha-Nabad program to support farmers in enhancing agricultural productivity and sustainability. By addressing training, agricultural inputs, this initiative aims to empower farmers, promote resilience, and foster economic growth in the targeted areas. The successful execution of this project will significantly contribute to improving livelihoods and supporting sustainable agricultural practices in Somalia.

Prepared by:

Name: Abdimajid Mohamed Abdi

Title: Economic Recovery Team Leader

Signature:

Date: 22/7/2025 Approved by Daniel Okumu

Inclusive Markets Coordinator Date: 23rd July 2025.