# REQUEST FOR PROPOSAL

For Allignment & Implementation of SOS CV Health & Nutrition services inline with Somalia Essential Package of Health Services (EPHS)

Table of Contents

REQUEST FOR PROPOSAL	1

1	Context and rationale	3

1.1	About SOS Children’s Villages	3

1.2	Description of programme location and context	3

1.3	Rationale and overall objective of the [insert type] evaluation	3

2	Instruction to bidders	3

2.1	Process of Submission of Bids	3

2.2	Documents to submit	3

2.3	Deadline for submission	4

2.4	Modification and withdrawal of bids	4

2.5	Signing of the contract	4

2.6	Rights of SOS Children’s Villages	4

2.7	Evaluation of proposals	4

3	Terms of Reference	5

3.1	Objectives of the evaluation	5

3.1.1	Overall objective	5

3.1.2	Specific objectives	5

3.1.3	Scope	5

3.2	Work plan and expected deliverables	5

3.3	Report criteria	6

3.4	Qualification of the researcher / research team	6

3.5	Logistical arrangements	6

3.6	Timetable	6

3.7	Duration of the contract and terms of payment	7

3.8	Notice of delay	7

3.9	Copyright and other proprietary rights	7

3.10	Termination	7

4	Annex	8

4.1	SOS Children’s Villages child protection policy and code of conduct	8

4.2	Bid submission / identification form	9

4.3	Previous experience form	10

4.4	Price schedule form	11

4.5	Technical proposal (guideline)	12

# Context and rationale

## About SOS Children’s Villages

SOS-Kinderdorf International, also known as "SOS Children's Villages International – SOS CVI" is an association duly registered under the laws of Austria, with registration number (ZVR-Zahl) 083115702, with its Head Quarter office at Hermann-Gmeiner-Straße 51, 6020 Innsbruck, Austria. SOS CVI is a Global Federation of National and Member Associations working in 137 countries and territories with focus to provide alternative care for children who have lost parental care, or at risk of losing. SOS Children’s Villages in Somalia is a Member Association of the Global Federation which has officially been working in Somalia since 1983. SOS Children’s Villages concept, the organization pioneered a family approach to the long-term care of orphaned and abandoned children in Somalia. SOS has a zero-tolerance policy on child safeguarding and prevention of sexual harassment and exploitation at work place. SOS Children’s Villages in Somalia currently works in four regions; Banadir Regions (Heliwa, Garasbaley, Kahda, Dharkenley and Daynile districts) southwest-state (Bay and Bakool regions) Hirshabelle State (Middle-Shabelle region- Balcad, Jowhar, Adan Yabaal & Adale districts).

SOS CV manages a huge multisectoral assistance project covering three districts (Heliwa, Baidoa & Balcad) in Somalia with annual reach of more than six hundred thousand beneficiaries in 2023 alone through Cafimad plus Consortium. Cafimad Plus comprising of six partners is at different levels of EPHS alignment. The consultant will guide the implementation teams to align the project with Somalia EPHS standards and norms.

## Description of programme location and context

Health service delivery in Somalia heavily relies on donor funding and SOS CV through Cafimad Plus ECHO funding provides funding to implement multisectoral assistance to lives of crisis affected communities in the country. The project implemented in Heliwa, Baidoa & Balcad districts offers health, nutrition, WASH, protection and crisis response to vulnerable women, children, adults and elderly in select priority districts. Somalia adopted the EPHS policy to guide and accelerate access to Universal Health Coverage (UHC) and promote a set of cost effective evidence based interventions with high impact.

The EPHS 2020 policy therefore aims to address all high-burden conditions through simple, low-cost, high-impact interventions, establish demand-driven services to facilitate more accurate costing, facilitate integrated service delivery, link services to level of care/platform of delivery, allow dynamic adaptation to operationalize the package in variable contexts with distinct delivery platforms, provide a foundation for service planning, workforce mapping and training competencies, support progressive realization and account for the need to increase service delivery capacity over time and support expansion to additional services when additional resources become available.

SOS CV through static facilities, mobile clinics and community level actions provides 6 CORE EPHS interventions including maternal and reproductive health, child health, communicable diseases surveillance and response, none communicable diseases, HIV/TB control and first aid and injury. Secondary health component is offered in district hospitals providing 4 additional services namely: - Management of chronic & other diseases, palliative care, and care of elderly; Mental health and mental disability; Dental health; and eye health. Integrated services including nutrition, protection, health, and Water, Sanitation, and Hygiene (WASH), is offered to women and children. Treatment and care for women and children provided is based on Somalia's standard treatment guidelines

SOS CV operates across 8 HTR districts, addressing the needs of fresh IDPs by delivering humanitarian assistance and providing EPHS aligned services to women and crisis-affected children. Pregnant and lactating women (PLWs) have access to quality maternal health services, including Antenatal Care (ANC), Postnatal Care (PNC), deliveries, Prevention of Mother-to-Child Transmission (PMTCT), and Comprehensive Emergency Obstetric and Newborn Care (CeMONC). ANC/PNC clients undergo various assessments, including weight/height measurements, hemoglobin testing, urinalysis, syphilis screening, fundal height measurement, Iron and Folic Acid Supplementation (IFAS), Sulphadoxine-Pyrimethamine (SP) prophylaxis, and PMTCT. Women seeking delivery benefit from inpatient care, intravenous antibiotics/fluids, labor monitoring using partograph, complications management, mother and newborn resuscitation. The integration of Gender-Based Violence (GBV) and child protection (CP) services is scaled up using cluster-approved guidelines, including sensitization to minimize stigma. Case management and psychosocial support for GBV victims is provided, with periphery staff referring cases to static facilities.

Child health package covers EPI, treatment of common childhood illnesses, hospitalization care for children and surveillance of epidemic diseases for children is provided.

The facilities provide first aid treatment for injuries and refer major surgical cases to more specialized facilities.

Malnutrition screening for PLWs and under-five children, treatment of SAM & MAM is offered including SAM with complications in children through inpatient care.

WASH services are integrated into the health and nutrition program, and caregivers educated on good hygiene, hand hygiene, and enrolled in the WASH program. Beneficiaries receive soap, detergents, and water treatment tablets, and WASH Information, Education, and Communication (IEC) materials  distributed.

Community empowerment through CHWs, VHCs, Mother-to-Mother Support Groups (MTMSGs), and Father-to-Father Support Groups (FTFSGs) are prioritized for scale-up. CHWs were deployed to High Targeted Response (HTR) areas, providing ICCM, ICCM+, hygiene promotion, follow-up, case referrals, and health education to households.

Referral services link SOS CV and other facilities including referral for HIV/TB cases.

## Rationale and overall objective of EPHS Alignment

The main purpose of the consultancy is to study Somalia EPHS policy and align SOS CV health & nutrition services  with the policy and support implementation. The specific objectives of the assignment are to:

- Study current SOS CV health & nutrition program to determine the level of EPHS alignment in terms of EPHS package, staffing norms and standards, financing, health information system, leadership & governance, supply & equipment needs.

- Develop guidelines or SOPs to guide SOS CV Senior Management in EPHS alignment & implementation

- Guide the EPHS Alignment and implement smooth handover of EPHS services to government and federal member states stewardship

- Support the process of EPHS alignment, engagement with key stakeholders to ensure smooth transition of SOS CV health & Nutrition program in select districts to government ownership and leadership

- Document learnings from the EPHS alignment design, process and implementation to guide future EPHS alignment and make recommendations

# Instruction to bidders

The bidders are welcome to submit their EPHS Alignment & implementation proposal.  This bid is open to all national and international suppliers (independent consultants or companies) who are legally constituted and can provide the requested services. The bidder shall bear all costs of the bid; costs of a proposal cannot be included as a direct cost of the assignment. The proposal and all supplementary documents have to be submitted in English. Financial bid needs to be stated in US dollars

## Process of Submission of Bids

To facilitate the submission of proposals, the submission duly stamped and signed can be done electronically in PDF format and sent to procurement@sossomalia.org  Electronic submissions preferred.

Postal address: P.O Box 599, Bula Xubey, Wadajir district, Mogadishu

The titles of submitted documents should clearly state “Technical proposal for SOS CV EPHS Alignment & Implementation in Somalia, by the company/consultant title” and “Financial Proposal for SOS CV EPHS Alignment & Implementation in Somalia by the company/consultant title”. Please make sure that the technical and financial proposals are handed in separately (financial proposal to be sealed in a closed envelope or a separate PDF file in case of electronic submission. During the process of evaluation, technical bids will be opened and evaluated first. The financial part of those proposals, which are shortlisted after evaluation of the technical proposal, will be opened in a second step.

## Documents to submit

- Bid submission / identification form

- Previous experience format

- Price schedule form (to be sealed in a closed envelope or a separate PDF file)

- Technical proposal

- CVs of the Consultant team member(s) including current geographical location(s)

- Three references (at least two of them must be familiar with your work)

- An example of a recent/relevant evaluation report (if available for public use)

## Deadline for submission

The proposal has to be received by latest on 15th Oct, 2024 by 4.00 p.m . Proposals received after the deadline will be not be considered.

## Modification and withdrawal of bids

Proposals may be withdrawn on written request prior to the closing date of this invitation. Any corrections or changes must be received prior to the closing date. Changes must be clearly stated in comparison with the original proposal. Failure to do so will be at bidder’s own risk and disadvantage.

## Signing of the contract

SOS Children’s Villages will inform the successful bidder electronically and will send the contract form within 3 weeks after closure of the bid submission deadline. The successful bidder shall sign and date the contract, and return it to SOS Children’s Villages Somalia within seven calendar days of receipt of the contract. After the contract is signed by two parties, the successful bidder shall deliver the services in accordance with the delivery schedule outlined in the bid.

## Rights of SOS Children’s Villages

- contact any or all references supplied by the bidder(s);

- request additional supporting or supplementary data (from the bidder(s));

- arrange interviews with the bidder(s);

- reject any or all proposals submitted;

- accept any proposals in whole or in part;

- negotiate with the service provider(s) who has/have attained the best rating/ranking, i.e. the one(s) providing the overall best value proposal(s);

- contract any number of candidates as required to achieve the overall evaluation objectives

## Evaluation of proposals

After the opening, each proposal will be assessed first on its technical quality and compliance and subsequently on its price. The proposal with the best overall value, composed of technical merit and price, will be considered for approval. The technical proposal is evaluated on the basis of its responsiveness to the Terms of Reference (TOR). Bidders may additionally be requested to provide additional information (virtual presentation or phone interview) to SOS Children’s Villages on the proposed services.

The criteria for selection are:

Method: The proposed method for evaluating the programme is suitable

Timetable/work plan: The timetable/work plan is realistic and meet the needs of the programme

Cost: The cost of the proposal is reasonable and feasible, given the other aspects of the proposal

Experience: The training and experience of the consultants in evaluations and recommendations from organisations for which the consultant(s) has previously worked

# Terms of Reference

## Objectives of the evaluation

### Overall objective

The main purpose of the consultancy is to review and redesign SOS CV Health & Nutrition services to conform to Somalia EPHS norms, standards and align with the policy to achieve more efficient, effective and sustainable EPHS delivery systems.

### Specific objectives - The specific objectives of the assignment are to:

  - Review relevant policies and develop EPHS alignment guidelines for use during transfer of such services to federal government and federal member states.

  - Review current SOS CV staffing pattern, norms, standards and align these with EPHS & WHO staffing norms and standards for the different levels of services delivery in SOS CV Health & Nutrition program.

  - Engage SOS CV Senior Management Team and key stakeholders to achieve smooth transfer of staff, facilities and supplies.

  - Document the EPHS alignment process and highlight best case scenarios to guide future endeavours involving EPHS similar assignments.

  - Lead the EPHS implementation, monitor milestones achieved in implementation and come up corrective action in case of low milestone achievement.

### Scope

The consultant is expected to carry out the following tasks in order to achieve the above-mentioned objectives:

  - Review EPHS, HSSP 111, National Transformative Plan, UHC, WHO guidelines and SOS CV Country Health Strategy documents to gain insights to successful EPHS alignment & design.

  - Develop an appropriate and acceptable work plan with clear timelines for the execution of the assignment

  - Develop tools and guidelines needed to align SOS health & Nutrition program with EPHS Policy for Somalia.

  - Implement and spearhead EPHS Alignment action and transfer staff, supplies, equipment, infrastructure and ownership of health facilities to government & federal member states

  - Lead and support engagement with key stakeholders such as donors, INGOs, government and local authorities and communities

  - Evaluate the success, best practices or failures of EPHS alignment and share documented learning of the alignment with SOS SMT.

  - Make suitable recommendations to guide further implementation of the EPHS Alignment

3.8 Facilitate consultative workshops to validate the findings and recommendations from stakeholders and implementation modalities.

## Work plan and expected deliverables

The EPHS Alignment will be carried out in 3 stages. All steps that lead to deliverables are marked in bold.

Stage 1: Prepare

Undertake all required preparations for the EPHS Alignment: propose detailed alignment methodology, conduct desk research, identify key informants, plan the EPHS implementation process, organisation & logistics, and prepare field visit schedule. Submit and secure approval for the refined EPHS Alignment, design and methodology in an inception report: checklists, participant lists and other management/organisational information for data collection.

Stage 2: Conduct

  - Facilitate learning during the EPHS Alignment.

  - Collection of data as per the agreed methodology and tools.

  - Implement the EPHS Alignment and engage all stakeholders to achieve a smooth handover

  - Document the alignment process and outcomes

Stage 3: Submit findings

- Preparation of a draft report in English

- Presentation of the findings to the programme staff / national office staff / international team (face-to-face).

- After having received feedback from the various stakeholders – finalise the report and submit it in English [and other language if needed].

Deliverables:

  - EPHS Alignment is implemented in line with the TOR and services handover to government and federal member states

  - Refinement of EPHS Alignment report and methodology in an inception report

  - First draft of the final report in English

  - Presentation of preliminary results to SOS Children’s Villages Somalia Country and International (face-to-face)

  - Revised EPHS Alignment report

## Report criteria

The EPHS Alignment will result in the concise EPHS Alignment implementation and EPHS Alignment report in English with a maximum length of 25 pages including an Executive Summary. All confidential information should be kept in a separate annex to protect participants. The final report should be provided electronically and in hard copy.

The report format below must be strictly adhered to:

- Cover page

  - Title of EPHS Alignment report

  - Country, programme, date of the EPHS Alignment report

  - Name of consultant

- Executive summary (maximum 2 pages; cross-reference pages or paragraphs in the main body)

  - EPHS Alignment action

  - Purpose and methodology (incl. limitations and challenges)

  - Main conclusions, recommendations, and lessons learned

- Main body

  - Each UNIT (Subject) , learning outcomes, mode of learning, contents, assessment methods, key references, The structure of the main body is determined by the desired results (See 2.3)

  - For each key conclusion, there should be a corresponding recommendation that is realistic, pragmatic, and operational

- Annexes

  - Terms of Reference

  - List of persons interviewed and sites visited

  - Map of areas covered by the programme

## Qualification of the consultant / consulting firm

The consultant / team of researchers must have:

- Proven competency (record of previous experiences) in EPHS reforms implementation & alignment

- A strong health background and experience in Health System Strengthening

- A good understanding of UHC, National Transformative Plan (NTP), HSSP 111 & EPHS Policy and practice

- Familiar with Somalia Human Resources for Health (HRH) policy and Health workforce regulations

- a good understanding of child rights and issues affecting vulnerable children and their families

- good facilitation, organizational and interpersonal skills

- proven experience in health sector reform and health policy

- strong analytical and conceptual skills

- excellent written communication skills

## Logistical arrangements

When at the programme location, accommodation and transport to the field will be organized by the member association, including the full coverage of costs during the entire stay of the researcher(s) (not to be included into price proposal).

National or location level staff (SOS) will be available to help organizing the interviews including contacting SOS, announcement and local preparation of evaluation, linking to community duty bearers and national authorities if required.

## Timetable

The evaluation will be conducted 18th Oct and final report prepared over a period of [27 days. The final report should be submitted by 14th Nov 2024

[please fill in / customize activities and dates]

| Activities | Dates | Time frame | Location |
| --- | --- | --- | --- |
| Prepare an inception plan, methods and interview partners to the contracting body (inception report) | 18-19th Oct | 2 days |  |
| Conduct desk research (general)- SOS CV policies, Somalia HRH policies, UHC, EPHS policy | 20- 22th Oct | 3 days |  |
| Conduct field visits (Balcad, Baidoa & Garasbaley) to meet with staffs | 23-26th Oct | 4 days |  |
| Engagement with key stakeholders | 27-29th Oct | 3 days |  |
| Implement EPHS Alignment | 30 Oct- 12th Nov | 14 days |  |
| Incorporate EPHS Alignment feedback and prepare final report and presentations | 13-15th Nov | 3 days |  |

## Duration of the contract and terms of payment

Payment will be made only upon SOS Children’s Villages acceptance of the work performed in accordance with the above deliverables. Financial proposals should include proposed stage payments. Payment will be effected by bank transfer in the currency of billing and is due 30 days after receipt of invoice and acceptance of work.

Funding and Payment: The consultant will be paid by SOS Children’s Villages as follows:

25% on the submission and approval of inception report

25% on completion of the draft report

50% on completion of final report

Duration of contract: the contract is effective from the moment it was signed until the acceptance of work by the international project team.

## Notice of delay

Shall the successful bidder encounter delay in the performance of the contract which may be excusable under unavoidable circumstances; the contractor shall notify SOS Children’s Villages in writing about the causes of any such delays within one (1) week from the beginning of the delay.

After receipt of the Contractor's notice of delay, SOS Children’s Villages shall analyse the facts and extent of delay, and extend time for performance when in its judgment the facts justify such an extension.

## Copyright and other proprietary rights

SOS Children’s Villages shall be entitled to all intellectual property and other proprietary rights including, but not limited to, copyrights, and trademarks, with regard to products, processes, inventions, ideas, know-how, or documents and other materials which the Contractor has developed for SOS Children’s Villages under the Contract and which bear a direct relation to or are produced or prepared or collected in consequence of, or during the course of, the performance of the Contract. The Contractor acknowledges and agrees that such products, documents and other materials constitute works made for hire for SOS Children’s Villages.

All materials: plans, reports, estimates, recommendations, documents, and all other data compiled by or received by the Contractor under the Contract shall be the property of SOS Children’s Villages and shall be treated as confidential, and shall be delivered only to SOS Children’s Villages authorized officials on completion of work under the Contract. The external consultant is obliged to hand over all raw data collected during the assessment to SOS Children’s Villages.

## Termination

SOS Children’s Villages reserves the right to terminate without cause this Contract at any time upon forty-five (45) days prior written notice to the Contractor, in which case SOS Children’s Villages shall reimburse the Contractor for all reasonable costs incurred by the Contractor prior to receipt of the notice of termination.

SOS Children’s Villages reserves the right to terminate the contract without any financial obligations in case if the contractor is not meeting its obligations without any prior notice:

- agreed time schedule

- withdrawal or replacement of key personal without obtaining written consent from SOS Children’s Villages

- the deliverables do not comply with requirements of ToR

# Annex

## SOS Children’s Villages child protection policy and code of conduct

SOS Children’s Villages International has a child protection policy and code of conduct that all consultants will be expected to comply with and will be required to sign a statement of commitment to the policy. This will happen upon signing of contract, together with an orientation of consultants on internal child safeguarding processes and data protection regulations.

Before the actual start of data collection, a police check is to be provided, in case any direct contact with programme participants and/or any sensitive data is planned.

In addition to the above mentioned, the following key areas for ethical consideration need to be taken into account: http://childethics.com/ethical%20guidance/

Graham, A., Powell, M., Taylor, N., Anderson, D. & Fitzgerald, R. (2013). Ethical Research Involving Children. Florence: UNICEF Office of Research - Innocenti.

The successful bidder is requested to obtain written consent from all participants of the evaluation process and/or their official guardians/representatives (when applicable).

## Bid submission / identification form

This bid form must be completed, signed and returned to SOS Children’s Villages. Bids have to reflect the instructions described in the Request for Proposal and Terms of Reference.

Any requests for information regarding this Request for Proposal shall be send to [insert name and email address].

The Undersigned, having read the complete Request for Proposals including all attachments, hereby offers to supply the services specified in the schedule at the price indicated in the Price Schedule Form, in accordance with the Terms of Reference included in this document.

Offering service for: [insert organization and name].

Company/Institution Name/Individual’s Name___________________________________________

2. Address, Country: ________________________________________________________________

3. Telephone: __________________ Fax _________________ Website_______________________

4. Date of establishment (for companies): _________________________________

5. Name of Legal Representative (if applicable): _________________________________________

6. Contact Person: _____________________________________ Email: ______________________

7. Type of Company: Ltd. Other _________________________

8. Number of Staff: ______________________________________

9. Subsidiaries in the region:

Indicate name of subsidiaries and address

a)___________________________________________________________

b)___________________________________________________________

c)___________________________________________________________

Validity of Offer:	valid until:____________________________________

Date

Signature and stamp

## Previous experience form

| Description (services and products provided to the clients relevant to the current RFP) | Client | Contact person/phone, e-mail address | Date of assignment (from/to) |
| --- | --- | --- | --- |

## Price schedule form

The financial proposal needs to include all taxes.

|  | Activity | Staff involved (indicate profile) | Number of people | Number of days | Daily rate | Total price per row | % of total price |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | A | B | C | D=AxBxC | E=D/F |
| 1 | Preparation & inception plan |  |  |  |  |  |  |
| 2 | Desk research |  |  |  |  |  |  |
| 4 | Field visits & stakeholder engagement |  |  |  |  |  |  |
| 5 | Implementation plan |  |  |  |  |  |  |
| 6 | Final report |  |  |  |  |  |  |
|  | Total Price (F) |  |  |  |  |  | 100% |

Accommodation and local transportation to be covered by Member Association, not to be included into price proposal.

This proposal should be authorized, signed and stamped

________________

(Name of Organisation)

Name of representative

Address:

Telephone/Fax/Email:

## Technical proposal (guideline)

| Name of Organisation/Firm/Independent Consultant |  |
| --- | --- |
| Name of contact person for this proposal (for organisation/firm) |  |
| Address: |  |
| Phone/Fax: |  |
| E-mail: |  |

The technical bid should be concisely presented and structured in the following order to include, but not necessarily be limited to the following information listed below.

1. Quality and Relevance of Technical Proposal

- Describe all actions related to defining data collection methodology and conducting the baseline study

- Realistic work plan with time lines in accordance with ToR

- Detailed quality assurance process for data collection and analysis

2. Qualification and expertise of or organisation/team of consultants/consultant submitting proposal

- Reputation of firm/organisation and staff and individual consultant/s (competence and reliability) in carrying out evaluations

- Relevance of:

- Specialized knowledge

- Proven expertise in carrying out formative evaluations

- CVs for key staff