TERMS OF REFERENCE FOR BASELINE EVALUATION FOR PROMOTING RESILIENCE AND PEACEFUL CO-EXISTENCE FOR CLIMATE CRISIS AFFECTED COMMUNITIES

SOMALIA’ PROJECT

- INTRODUCTION AND BACKGROUND

Up to 69% of the Somali population live below the poverty line mainly due to the negative effects of climate change.   Climate change-related droughts, intermittent floods and desert locust infestation has resulted in loss of livestock and agricultural production which account for more than 70% of the country's GDP.  These sectors also employ millions of Somali people directly and indirectly.  The destruction of education and WASH facilities, and the loss of local communities’ main livelihood sources by floods and drought continues to increase the number of Internally Displaced Persons (IDPs) and resultant humanitarian crises. Furthermore, climate change and variability impacts, and conflicts are interlinked in Somalia, and these affect the most vulnerable (particularly women and children) and communities that depend on natural resources like land, water and pasture. resource-dependent communities (NCD 2021).  More than 4.3 million people are projected to suffer from acute hunger and malnutrition, including 1.5m children under the age of five who are expected to suffer from acute malnutrition in 2024, more than half of the population is water insecure with almost two-thirds of displaced households considered as water insecure. Low school enrolment rates contour to bedevil children of Somalia during droughts and flooding.  During droughts, the children migrate with their families in search of pasture and those left at home have very little to survive on, school becomes a secondary need.  During floods, the children may not access schools as pths to schools are washed away and the dangers of being washed away by raging flood waters pose a safety risk.  Some learning facilities also get destroyed (including learning materials) making learning impossible.  Where the schools remain relatively safe, these are used by displaced communities as safe havens until the flood waters subside. The Gross Enrolment Rate (GER) in Somalia is estimated at 31 percent (28 percent female) for primary education and 23 percent (19 percent female) for secondary education (Joint Review of the Education Sector Report, 2023). It is therefore projected for 2024 that between 3.6 million and 4.9 million school-aged children in Somalia will not have access to formal education and that nearly 2.4 million school-aged children will require assistance to enable them to begin, return to, or remain in school. Floods, droughts, conflicts, and displacement are putting women and girls at risk in Somalia.

It is against this background that the ACT Alliance Somalia Forum (ASF), comprising of the NCA WS, DKH, DS, FCA, NCA and Bread for the World (BftW), is committed to support community’s capacities to mitigate the effects of climate change, focusing on their respective thematic sectors. Through a Consortium Project, we intervene in the crisis employing a humanitarian- development-peace nexus approach, leveraging resources, skills, and expertise of individual members and linking with local partners and institutions (including community-based organizations and government institutions) as key partners in advancing the initiative.

- OVERALL, PURPOSE OF THE CONSULTANCY

The primary objective of this Request for Proposals is to identify potential bidder(s) for the execution of a Baseline evaluation and an Infrastructure technical assessment for WASH and Livelihood. The evaluation aims to provide a benchmark from which to measure the progress of the WASH and livelihood intervention in the target districts of Garowe, Galkacyo, and Qardho. It will also look at how community stakeholders, such as local government, schools, farmer groups, and community leaders, are intervening to understand the needs in WASH and livelihood. The purpose of this evaluation, therefore, is to provide the current status of the results framework indicators and enable the tracking of progress toward meeting project objectives.

- KEY OBJECTIVES OF THE ASSIGNMENT

- Identify the current landscape or status of WASH services, food security, and climate resilience in the targeted districts.

- Assess the current status of project indicators, such as access to portable water, prevalence of waterborne diseases, and school meal program attendance rates.

- Investigate gaps in service delivery chains, including WASH infrastructure, agricultural training, and school-based food programs.

- Identify potential additional interventions required to strengthen WASH services, food security strategies, and climate resilience efforts.

- Identify community knowledge, attitudes, and practices towards WASH, food security, and climate adaptation.

- Assess the attitudes and capacity of service providers, teachers, and community leaders toward implementing inclusive and sustainable WASH and food security interventions.

- Conduct a WASH technical assessment in the proposed project area on proposed infrastructures- document attached

- SCOPE OF THE BASELINE EVALUATION

The evaluation and technical assessment will be conducted in the target locations of Puntland State through surveys and both KII and FGDs, from girls and boys at different ages, women & men, young people, Marginalized groups and from related stakeholders including government, NGOs and UN agencies.

Geographical coverage: The evaluation will cover the following specific areas:

| State | Region | District | Village |
| --- | --- | --- | --- |
| Puntland state | Nugal | Garowe | Balley |
| Puntland state | Nugal | Qardo | Kubo |
| Puntland state | Mudug | Galkacyo | Roox |

- APPROACH AND METHODOLOGY

The mixed-method approach will be adopted for the Baseline Evaluation, combining quantitative and qualitative methodologies to capture the conditions at baseline in the project areas. The consultant should also review relevant project documents, previous evaluations, and reports to contextualize baseline findings within the broader project goals. Participatory tools should also be applied, such as community mapping and problem ranking, to capture local priorities and needs. Data should be validated through direct observations of existing WASH infrastructure, agricultural practices, and school-based initiatives. The study should strive for inclusiveness and gender responsiveness by ensuring that women, youth, and marginalized groups are adequately represented. The study will adhere to ethical principles on the protection of confidentiality and informed consent and will be culturally sensitive. Since NCA is CHS-certified, the baseline study must be guided by the nine commitments of Core Humanitarian Standards. For the proposed infrastructure, before photos must be capture on the basis of provided GPS coordinates

- DELIVARABLES

The consultant will be responsible for preparing and submitting the following deliverables.

- An inception report.

- A draft report of the findings submitted to the NCA program team for feedback (including related materials from interviews conducted).

- A final report written in English (soft copy), including findings, best practices, lessons learned, recommendations. The structure and format of the final report will be agreed upon by NCA and the consultant.

- SUBMISSION CRITERIA

PART A: TECHNICAL PROPOSAL

- The Technical Proposal shall be straightforward and concise, describing how the consultant intends to carry out and deliver on the above-mentioned task. No cost or pricing information is to be included in the technical proposal.

- Technical proposals are limited to 15 pages in total. Organizational Information, CVs of proposed personnel, and examples of previous relevant work are to be included in an Annex. The page limitation does not include key personnel resumes, dividers, and past performance report forms. Bidders are encouraged to provide an Annex, or “portfolio,” of samples demonstrating experience performing similar activities. The Annex can include copies of photographs, other visual representations, and media/social media clippings. The Annex should not exceed ten pages.

The technical proposal shall be formatted using the following sections:

Technical Approach– Narrative not to exceed five (5) pages.

- The bidder shall demonstrate his/her understanding, ability, and overall approach to perform the requirements described in the Scope of Work/Tasks/Activities. S/he shall clearly explain how they propose to structure, design, manage, and execute the work required that meets NCA objectives.

- The Technical Approach must include a timeline or Gantt chart of the deliverables required to execute this project.

- The Technical proposal will include the approach with which the technical assessment will be conducted

Capability Statement - Narrative – not to exceed two (2) pages.

- The bidder shall demonstrate his/her specialized competence about the requirements of the tasks/activities. S/he shall demonstrate they have the necessary personnel to successfully comply with the contract requirements and accomplish the deliverables.

Past Performance – Narrative not to exceed five (3) pages.

- The Bidder shall provide at least three (3) examples of past performance of implementing similar projects. The past performance examples must be within the last three (3) years and similar in scale and relevance. S/he must provide references for each example, including the reference's name, title, phone number, and email address.

- The firm's technical lead person/ individual consultant must have at least a master’s degree or PhD in climate change, environmental science, Dryland agriculture, or related qualifications, with extensive expertise and experience in evaluating development programs. The firm technical lead person should have at least 6 years of experience working with international organizations and donors on monitoring, and evaluations or climate change-related programs, with particular experience in the context of Somalia.

Personnel/Staffing – A narrative not to exceed two (2) pages.

- A summary describing the proposed staff for the project, including up to three team members. The summary shall include names, relevant qualifications of similar experience, and the proposed role for each individual. A Project Manager must be identified with a minimum of five years’ experience in related project management.

- The bidder must also include the CVs of the key staff members involved in the Project, including the Project Managers and up to 3 Team members. Each CV should not exceed three (3) pages.

PART B: Financial PROPOSAL

- The bidder shall propose a realistic and reasonable cost for this work.

- The cost should be in dollars and include all applicable local taxation. The financial proposal shall list all costs associated with the assignment.

- Items described in the technical proposal but not priced shall be assumed to be included in the prices of other items or at the consultant’s own cost.

Administrative compliance document.

The interested candidate must present the following documents which will be used during the evaluation in the administrative compliance section.  Please note that the technical evaluation will not consider any company with the missing document below.

- Proposal Submission Form duly completed and signed by the Candidate.

- A valid certificate of business license or similar document of Somalia federal state and federal Member Government.

- Valid tax registration, tax clearance certificates or similar documents, and where applicable advance tax clearance certificate of Federal state and federal Member Government. i.e., Jubaland and Puntland.

- Information on ownership structure (Name of directors of the company / Owner)

List three corporate clients (attach documentary evidence which may include copies of Similar Contract assignments issued in the last 5 years

- EVALUATION CRITERIA

- This solicitation is open to individuals or local firms/companies registered in Somalia, specializing in research.

- The selected Consultant will be responsible for designing and executing all activities outlined in this Request for Proposal in coordination with NCA.

- Proposals will be evaluated using quality and cost-based selection, with a total score calculated out of 100% of which 80% is the weight of the technical proposal and 20% is the weight of the financial proposal.

| Proposals meeting the mandatory requirements will be evaluated for technical merit based on the criteria in the below chart. Those proposals scoring 65 points or higher (out of 80 points) will be considered for cost-effectiveness Section | Description | Maximum Points |
| --- | --- | --- |
| Technical Approach | Proposed structure, design, and approach to conducting the need assessment evaluation. (25 points) Timeline or Gantt chart of the activities required for evaluation. (10 points) | 35 |
| Capability Statement | Demonstrate the necessary organizational systems and personnel to successfully comply with the contract requirements and accomplish the expected results. (15 points) | 15 |
| Past Performance | Inclusion of at least three relevant pasts performance examples of similar projects. (10 points) References provided by past clients for these examples and their evaluation of the bidder’s ability to deliver on time and within quality and budget expectations. (5 points) | 15 |
| Personnel/Staffing | Qualifications and past relevant experience of the lead consultant and up to 3 team members proposed to perform the requirements of this scope of work. (15 points) | 15 |
| Technical Evaluation Threshold (only offers that receive a technical evaluation score of 65 and above points (out of 80) will be considered for cost evaluation.) |  |  |
| Cost Evaluation | The financial proposal will be evaluated using the following formula: FS=20X Lowest PriceF | 20 |
| Total Points |  | 100 |

- HOW TO APPLY

Interested and qualified consultant(s) should submit their technical and financial proposals to Procurement.Somalia@nca.no  with the e-mail subject line clearly marked; Baseline Evaluation on or before 22nd January 2025