TERMS OF REFERENCES (TOR)

Endline evaluation- SOM1053

## INTRODUCTION AND CONTEXT

| Country: | Somaliland |
| --- | --- |
| Project title: | Women’s empowerment for improved nutrition of infants, young children and mothers in Maroodi-Jex and Togdheer Regions. |
| Project holder: | Welthungerhilfe (WHH) and African Children's Rights Found (ACRIF). |
| Co-financer (line): | BMZ |
| Project period: | 01/12/2022 - 30/11/2025 |

### 1.1 Welthungerhilfe and Partner.

Deutsche Welthungerhilfe e. V., or Welthungerhilfe (WHH), is one of the largest non-governmental organizations in Germany working in the fields of humanitarian assistance and development cooperation. Established in 1962 as the German section of the United Nations’ “Freedom from Hunger Campaign,” it was one of the first international initiatives focused on eradicating hunger. Today, Welthungerhilfe’s work remains guided by its founding vision: All people have a right to a self-determined life in dignity and justice, free from hunger and poverty.

In line with its Strategy 2025–2030: Zero Hunger on a healthy Planet, Welthungerhilfe promotes systemic change through evidence-based, impact-oriented approaches that are environmentally sustainable and socially just. The organization works in close partnership with local actors and communities to strengthen resilience, ensure food and nutrition security, and advance the realization of rights and agency among people affected by hunger and poverty.

Welthungerhilfe is committed to program quality, accountability, and continuous learning. Comprehensive Monitoring, Evaluation, Accountability, and Learning (MEAL) systems are embedded across the program cycle to ensure that interventions are effective, context-sensitive, and continuously improved. A central element of this approach is the Defining Impact paper, which outlines how WHH distinguishes between outcomes and impact to enhance clarity, credibility, and learning in its work. The organization fosters a culture of reflection, transparent sharing, and collaboration - ensuring that evaluations contribute to both organizational learning and broader sectoral knowledge.

Since being founded in 1962, it has provided funding of EUR 5.07 billion for more than 12,128 overseas projects in about 72 countries. In 2023 alone, WHH supported about 16.4 million people with its 630 overseas projects in 36 countries.

Welthungerhilfe has been present since 2001, working in both emergency relief and long-term development. Its portfolio is multi-sectoral and aligned with WHH’s global strategy (2025–2030) to achieve “Zero Hunger wherever we work,” with interventions ranging from food and nutrition security initiatives that promote improved diets and nutrition practices, to WASH programmes that strengthen access to safe water and hygiene, alongside livelihoods and resilience activities that support communities in adapting to shocks, and civil society and governance efforts that build the capacity of local organizations and promote inclusive participation.

ACRIF, formerly known as ANPPCAN Somaliland, is a child rights organization founded in 2008 with its headquarters in Hargeisa. It is a development and humanitarian organization that advances children’s rights and equality for girls and boys, working to ensure a healthy start in life, access to learning opportunities, and protection from harm. Over the past 17 years, ACRIF has implemented projects across all six regions of Somaliland in the areas of health, nutrition, education, agriculture, protection, human rights, legal affairs, and social work, with a particular focus on the most vulnerable groups—children, adolescent girls, and women. The organization has extensive experience in nutrition programming and has successfully delivered integrated interventions for mothers and children.

### 1.2 The Project and its context

The project Women’s Empowerment for Improved Nutrition in Somaliland is implemented by Welthungerhilfe in partnership with ACRIF. It targets six communities in Maroodi-Jex (Hargeisa, Gabiley) and Togdheer (Oodweyne) regions. The intervention responds to persistent nutrition challenges among women of reproductive age (15–49 years) and children 6–23 months, focusing on both improved nutrition practices and strengthened women’s decision-making at the household level.

Objectives and expected results

The overall objective  of the project is that the nutritional status of children and women in the Togdheer and Maroodi-Jex regions of Somalia has been sustainably improved.

Outcome 1,200 women of reproductive age (WRA) and other male and female caregivers of children under the age of five years in selected communities in Togdheer and Maroodi-Jex regions have improved nutrition-related behaviours, practices, and decisions.

Output 1: 1,200 WRA and other caregivers have improved nutrition-related knowledge and behaviours/practice.

Output 2: Advocacy initiatives by the Somaliland Civil Society Network for Scaling-Up Nutrition (SLCSN-SUN), targeting the Somaliland government line ministries, donors and all international and local NGOs working within the nutrition sector, are scaled up.

Output 3: Relevant organizational and technical capacities as well as internal learning of the local project partner organization ACRIF (formerly ANPPCAN-SOM) are strengthened.

Stakeholders and participants

Direct participants: Women of reproductive age (15–49) and caregivers of children 6–23 months in the six target communities.

Indirect participants: Household members benefiting from improved dietary practices and decision-making dynamics.

Change agents: Community Nutrition Workers and nutrition promoters trained to deliver counselling and SBC sessions.

Civil Society and Government Stakeholders: The project closely collaborates with the Somaliland Civil Society Network for Scaling-Up Nutrition (SLCSN-SUN) and engages 180 key stakeholders, including policymakers and parliamentarians. These actors are involved in SUN platforms and networks to strengthen advocacy for scaling up the nutrition agenda across both nutrition-specific and nutrition-sensitive sectors. Stakeholders include Somaliland line ministries, donors and funding agencies, and local and international NGOs.

The project applies a community-based approach, anchored in participatory Social and Behavior Change (SBC ) and household counselling. Activities are integrated into existing health services (ANC, PNC, EPI and CMAM) and supported by community groups. CNWs and nutrition promoters lead household visits, and group sessions, while home gardening initiatives provide a practical pathway to improved dietary diversity.

Problem background

Undernutrition in Somaliland has remained a severe and persistent public health challenge for the past two decades, undermining progress on hunger reduction, child and maternal health, gender equality, and education. The burden is greatest among children, women of reproductive age, and adolescents in poor and marginalized communities. Key drivers include poverty, food insecurity, recurrent droughts, infectious diseases, micronutrient deficiencies, poor feeding and care practices, limited access to health and WASH services, and entrenched gender inequality. These factors have led to high levels of acute and chronic malnutrition, with devastating effects on survival, growth, cognitive development, and long-term health. Malnutrition perpetuates a vicious cycle across generations, weakening human capital and constraining Somaliland’s social and economic development.

- EVALUATION PURPOSE AND OBJECTIVES

Purpose
The overall purpose of this endline evaluation is to assess the effectiveness of the project in achieving its objectives. It is conducted at this stage because the project is approaching completion (2025) and timely evidence is needed to measure results, inform decisions on continuation or a successor phase, and strengthen accountability to stakeholders.

The evaluation will focus on both learning (to improve future programme design and implementation) and accountability (to report on outcomes to donors, partners, and communities), with learning taking precedence.

Objectives
To fulfill this purpose, the evaluation will:

- Assess the project’s performance against its logframe outcomes and outputs, focusing on MIYCN practices (MDD-W, MMF), women’s decision-making, SBC interventions, home gardening initiatives, and policy advocacy interventions, as these are all critical components of the project.

- Compare endline findings with baseline data to determine the extent of change achieved.

- Identify enabling and limiting factors that influenced project implementation and outcomes.

- Document best practices, lessons learned, challenges, and opportunities for improvement.

- Provide actionable recommendations to guide WHH, ACRIF, and stakeholders in designing future nutrition-sensitive and gender-transformative interventions, and inform advocacy efforts through SLCSN-SUN.

- SCOPE OF THE EVALUATION

The final evaluation will assess the effectiveness of the project in achieving its intended objectives and outcomes as per the project’s logical framework. It will cover all six project locations in Maroodi-Jex (Hargeisa and Gabiley) and Togdheer (Oodweyne) regions of Somaliland, and the full project duration.

The evaluation will:

- Assess the project’s relevance by examining whether the activities and support provided addressed the needs and priorities of women of reproductive age, caregivers, and local partners.

- Evaluate the achievement of the project’s outcome and results as defined in the logical framework, focusing on improvements in maternal, infant, and young child nutrition (MIYCN) practices (MDD-W, MMF), women’s participation in decision-making, home gardening, and policy advocacy support to nutrition-specific and nutrition-sensitive sectors.

- Examine the effectiveness, efficiency, and sustainability of the implementation model, particularly the use of Community Nutrition Workers, nutrition promoters, and participatory SBC approaches. The evaluation will also assess the strength of partnerships and coordination mechanisms (e.g., WHH–ACRIF collaboration, government engagement, and the SLCSN-SUN platform), as these were central to project delivery and sustainability.

- Document challenges, lessons learned, and best practices, including enabling and limiting factors affecting nutrition behaviors, gender equality, and household decision-making. This section will also explicitly capture both nutrition-specific and nutrition-sensitive approaches to provide a comprehensive understanding of the project’s contribution to improved nutrition outcomes.

- Provide key recommendations to inform WHH, ACRIF, and stakeholders for future programming, scale-up, or successor interventions.

Geographic scope: The evaluation will cover six project sites in Maroodi-Jex (Xunboweyne, Biyashiina, Geed-Deeble in Hargeisa, and Allaa Ibadaay in Gebiley) and Togdheer (Beerato and Abdi Farah in Oodweyne), and will include visits to the WHH Country Office, ACRIF headquarters, the SLCSN-SUN network, and relevant government ministries engaged in nutrition.

Participants and stakeholders: Women of reproductive age and caregivers, husbands, grandmothers, nutrition leaders, nutrition champions, CNWs and nutrition promoters, SLCSN-SUN members, policy-level stakeholders, WHH and ACRIF staff.

- USERS AND USES OF THE EVALUATION

## Primary users

Welthungerhilfe (WHH) Country Office staff: to guide decision-making on future program design, adaptation, and potential scale-up of nutrition-sensitive and gender-transformative interventions in Somaliland.

ACRIF (implementing partner): to strengthen organizational learning, improve technical and operational capacity, and refine future project implementation strategies.

Donors: to assess accountability for results and value for money, and to inform funding decisions on continuation or successor interventions.

## Secondary users

Project participants and communities: to gain feedback on how the project has addressed their needs and to strengthen ownership of nutrition and empowerment outcomes.

Government ministries: to inform nutrition policy development, program integration, and alignment with national strategies.

SLCSN-SUN and other civil society actors: to draw lessons for advocacy, coordination, and sector-wide learning.

WHH Regional and Global Units: to inform global programming strategies, evidence-based decision making, and internal learning across WHH’s portfolio.

## Intended uses of the findings

Decision-making and program adaptation: WHH and ACRIF will use findings to adjust approaches and design future interventions.

Learning and capacity development: All stakeholders will draw lessons on effective SBC, MIYCN, women’s empowerment, home gardening interventions, and policy advocacy support.

Accountability: Donors, government, and communities will use the results to validate outcomes and hold actors accountable.

Policy advocacy: Findings will inform the work of SLCSN-SUN and government ministries in scaling up nutrition-sensitive policies and actions.

Process uses of the evaluation

Capacity strengthening: WHH, ACRIF, and local stakeholders will build skills in evaluation, reflection, and evidence-based decision making.

Shared learning and dialogue: The evaluation process will create opportunities for joint reflection among WHH, ACRIF, government, and civil society, strengthening collaboration and mutual accountability.

- EVALUATION CRITERIA AND QUESTIONS

The evaluation will address the following questions based on the OECD DAC criteria of Relevance/Appropriateness, Effectiveness, Coherence, Sustainability/Connectedness, and Impact. The evaluation will focus on how well the project responded to the nutrition and empowerment needs of women of reproductive age, caregivers, and communities in Maroodi-Jex and Togdheer, how effective the measures were, and what impact they have had on participants’ lives.

## Relevance / Appropriateness

- To what extent did the project design and objectives respond to the nutritional requirements and empowerment of women of reproductive age, caregivers, and households in Maroodi-Jex and Togdheer?

- How well did the project align with national nutrition policies, strategies, and priorities of government and civil society actors (e.g., SLCSN-SUN), including efforts to promote nutrition-sensitive and gender-transformative approaches at community and national levels?

## Effectiveness

- To what extent were the planned outcomes achieved, particularly improvements in MDD-W, MMF, and women’s participation in household decision-making?

- How effective were SBC interventions (counselling, cooking demonstrations, group sessions) in improving nutrition knowledge and practices among target groups?

- How effectively did the project identify and reach the most vulnerable and marginalized groups, including children, women, the elderly, and people with disabilities?

## Sustainability / Connectedness

- To what extent are improved MIYCN practices, home gardening, women’s empowerment, and policy advocacy support likely to be sustained after the project ends?

- How effectively were CNWs, nutrition leaders/champions, and ACRIF capacitated to continue delivering nutrition services and advocacy?

## Impact

- What measurable changes in nutrition practices, dietary diversity, women’s empowerment, and policy advocacy support can be attributed to the project compared to baseline findings?

- How do the current conditions of participants and communities compare with the baseline data collected at the start of the project (or at the beginning of the year, in cases where participants have changed)?

- What broader or unintended effects (positive or negative) on households, gender relations, or community resilience emerged from the project?

## Relevance / Appropriateness

- To what extent was the project coherent and complementary with the interventions of government ministries (e.g., MoHD, Ministry of Agriculture), SLCSN-SUN, and other NGOs/INGOs active in the target regions?

- To what extent was the project aligned with national frameworks such as the Somaliland National Development Plan (NDP) and other government nutrition priorities?

## Efficiency

- To what extent were financial, human, and material resources used efficiently to achieve the intended project outcomes?

- What lessons can be drawn to improve cost-effectiveness and resource use in future interventions?

## Overarching Developmental Impact

- To what extent did the project contribute to broader development goals such as improved food and nutrition security, women’s empowerment, and policy influence?

- Has the project demonstrated a model approach that can be replicated, scaled up, or integrated into government or partner programmes?

## EVALUATION DESIGN AND METHODOLOGY

The evaluation will adopt a mixed-methods approach, combining quantitative and qualitative methods to ensure a comprehensive understanding of project performance, outcomes, and lessons learned. The design will be participatory and utilization-focused, engaging WHH, ACRIF, government, civil society, and community stakeholders throughout the process.

## Design

- Type: Final (endline) evaluation, non-experimental, using a before/after comparison with baseline data where available.

- Approach: Cross-sectional household survey, complemented by qualitative methods (FGDs, KIIs) and document review.

- Level of analysis: Project-level results, triangulated with community, household, and institutional perspectives.

## Quantitative methods

- Endline household survey covering WRA/caregivers in six project communities, representative of project Participants.

- Measurement of logframe indicators such as MDD-W and MMF to capture changes in dietary diversity and feeding practices, along capturing additional information on home gardening outcomes—including the proportion of households adopting kitchen gardens, types of produce grown and consumed, and their contribution to dietary diversity and household resilience.

- Structured participant questionnaires on knowledge, decision-making, SBC exposure, and expanded assessment of home gardening practices to capture their economic and resilience benefits, such as reduced household food expenditure, improved food availability, and coping capacity during lean seasons.

- Comparative analysis with baseline findings to assess progress and outcomes.

## Qualitative methods

- Focus Group Discussions (FGDs): with women, caregivers (segregated into male and female groups where appropriate), and community members to capture perceptions of nutrition practices, empowerment, and project relevance.

- Key Informant Interviews (KIIs): with CNWs, nutrition leaders/champions, WHH, ACRIF staff, government ministries, and SLCSN-SUN representatives to explore effectiveness, sustainability, and coherence.

- Case studies / stories of change: to document significant outcomes or unintended effects from the project.

## Secondary data review

- Review of project proposal, logframe, baseline survey, progress reports, training materials, and monitoring data.

- Reference to relevant external documents such as national nutrition policies, Somaliland NDP, and sector assessments.

## Triangulation

Findings from different sources will be cross validated (quantitative, qualitative, and documentary) to enhance credibility and reliability.

## Participation and inclusion

The methodology will ensure active involvement of women, men, adolescent girls, and vulnerable groups (including persons with disabilities) to capture diverse perspectives. Data will be sex-, age-, and disability-disaggregated (SADD) wherever possible.

## Ethical considerations

The evaluation will adhere to WHH’s Code of Conduct and safeguarding policies, ensuring informed consent, confidentiality, and do-no-harm principles during all data collection activities.

## RESOURCES AND AVAILABLE DATA/DOCUMENTS

The evaluation is a 45-day consultancy assignment. WHH will cover costs based on the consultant’s agreed financial proposal, while all direct expenses (enumerators, logistics, data collection, analysis, and reporting) will be fully managed by the consultant.

WHH and ACRIF will not provide human or logistical resources but will:

- Share project documents, monitoring data, and baseline reports.

- Facilitate introductions to communities, government, and stakeholders.

- Provide a venue for the validation workshop.

The consultant is responsible for mobilizing and supervising enumerators, ensuring quality data collection, and managing all logistical arrangements (transport, accommodation, translation, communication, etc.).

## MANAGERIAL ARRANGEMENTS / ROLES AND RESPONSIBILITIES

The WHH Area Office MEAL team will take overall coordination of this Final Evaluation, working closely with the successful consultant. The WHH Capacity Building Advisor (Project Focal Person), the ACRIF Project Manager, and the WHH MEAL focal person will jointly oversee the evaluation process and provide timely support as required.

## Roles and Responsibilities

Welthungerhilfe (WHH Area Office) and ACRIF
The WHH Area Office, in close coordination with ACRIF, will be responsible for:

- Sharing all necessary documents with the consultant to finalize the methodology and data collection tools.

- Supporting community mobilization and arranging appointments with key study participants.

- Providing input on the study methodology, tools, and report drafts.

- Offering guidance and coordination throughout all phases of the evaluation, maintaining continuous communication with the consultant.

- Reviewing the draft report and providing feedback.

- Approving and signing off on the final report.

The Consultant
The successful consultant will be responsible for designing and conducting the final evaluation and presenting findings to WHH and ACRIF. Specific tasks include:

- Reviewing key documents, including the ToR, proposal, and project logframe.

- Designing the evaluation, including an inception report with methodology, sampling frame, data sources, analysis plan, and draft data collection tools, to be submitted for review and approval.

- Developing an evaluation matrix aligned with the project logframe.

- Conducting training for enumerators and supervisors on tools, sampling, data protection, and research ethics.

- Overseeing field data collection, ensuring supervision and quality control.

- Preparing a draft report and discussing initial results with the project team.

- Conducting a validation workshop and final presentation of main findings with WHH and ACRIF.

- Producing the final evaluation report, including updated logframe values, datasets (raw and clean), tools, sampling strategy, fieldwork plan, and evaluation matrix.

WHH and ACRIF Staff

- Support in setting up interviews and meetings with stakeholders.

- Note: Transport and logistics must be organized by the consultant; WHH will not be liable for logistical support.

Steering / Reference Group
A steering group will be established to guide the evaluation, composed of representatives from:

- WHH MEAL and Programme teams

- WHH Capacity Building Advisor (Project Focal Person)

- ACRIF management

The steering group will validate the inception report, methodology, and draft findings, and support dissemination of the final results.

Contact Points

Overall coordination: WHH MEAL team

WHH Capacity Building Advisor (Project Focal Person)

ACRIF Project Manager

- ETHICAL CONSIDERATIONS

WHH is committed to upholding the Core Humanitarian Standard on Quality and Accountability, its Code of Conduct, and strong safeguarding principles, particularly the Protection from Sexual Exploitation, Abuse, and Harassment (PSEAH). These standards guide all activities carried out by internal and external stakeholders and require that all actions respect the dignity, rights, and safety of individuals, especially project participants and those in vulnerable situations.

The consultant must adhere to these principles throughout the evaluation. This includes:

- Treating all participants with dignity and respect, ensuring voluntary and culturally appropriate participation.

- Preventing and immediately reporting any suspected cases of Sexual Exploitation, Abuse, or Harassment (SEAH) via WHH’s reporting channel.

- Signing WHH’s Code of Conduct and safeguarding declarations before starting the assignment.

- Obtaining informed consent from all participants and ensuring their right to withdraw.

- Guaranteeing confidentiality of all data and documents, which remain the property of WHH.

- Following ethical research standards and securing any required ethical authorizations.

- DELIVERABLES AND REPORTING DEADLINES

All the Deliverables will be submitted to WHH soft copy (unless otherwise noted below).

- An inception report: The consultant will share the inception report that details the evaluation design (rationale, methodology), data collection tools, and a detailed work plan within 1-3 days of engagement, to be approved by WHH

- Data collection tools: Both Household Survey and qualitative data collection tools will be developed by the consultant. All tools must be revied and approved by WHH prior to the commencement of data collection, analysis, and interpretation.

- Validation meeting: A meeting, online, discussing the main findings of the draft report, including project staff, partner staff, WHH MEAL staff, once data collection has ended.

- Log Frame Alignment: Updated project log frame is required with endline indicator values.

- Raw and clean final datasets

- Draft Evaluation Report: The evaluator will prepare a draft evaluation report with details of findings, recommendations and lessons learnt for review by WHH and partners.

- Final Evaluation Report: The evaluator will share a final evaluation report after incorporating the comments from WHH and project partner.

- Photos of Evaluation Activities: The evaluator will provide photos documenting the evaluation activities, such as Focus Group Discussions (FGDs) and interviews (while being mindful of confidentiality concerns), as part of the report. Additionally, relevant photos of the project activities from the WHH archive should be used to illustrate the context and work conducted during the project. WHH signed consent form is needed for every photo taken.

- TIME FRAME / SCHEDULE

The evaluation will be conducted  over   45 calendar days following contract signing. An initial tentative timeline is presented below. Proposals should assess the feasibility of this timeline and include a detailed workplan. The final schedule will be agreed jointly between the evaluator(s) and WHH during the inception phase.

| Activity | Deliverable | Timing/Deadline |
| --- | --- | --- |
| Contracting and briefing | Kick-off meeting and briefing note | Day 1 |
| Inception phase. | Inception Report (methodology, tools, workplan) | By Day 7. |
| Enumerator training and piloting | Trained enumerators and pre-tested tools | By Day 14 |
| Field data collection | Completed household surveys, FGDs, and KIIs | Days 15–29 |
| Data cleaning and analysis | Clean dataset and preliminary analysis | Days 30–35 |
| Draft report preparation | Draft Evaluation Report | By Day 40 |
| Validation workshop & presentation | Stakeholder workshop and presentation slides | Days 41–43 |
| Final report (incorporating feedback) | Final Evaluation Report with annexes | By Day 45 |

## EXPERTISE OF THE EVALUATORS

This survey requires a consultant able to work in the study areas without limitations. The assignment is open to both individual consultants and consultancy firms with substantial experience in the services outlined.

Expected Profile of the Lead Consultant
The lead consultant (or team leader) must meet the following criteria:

- An Advanced  advanced degree in Nutrition, Dietetics, or Public Health Nutrition.

- Proven expertise in Monitoring and Evaluation, Epidemiology, Statistics, or a related field, with demonstrated experience in conducting evaluations of nutrition-related projects.

- At least 5 years of proven technical experience in nutrition programming, particularly Maternal, Infant and Young Child Nutrition (MIYCN), nutrition-sensitive interventions, and social and behaviour change (SBC) approaches.

- Demonstrated experience in the assessment of IYCF indicators according to the 2021 WHO IYCF Indicator Guide.

- Demonstrated experience with OECD DAC criteria and participatory evaluation methods (mixed-methods, FGDs, KIIs, surveys).

- Knowledge of Core Humanitarian Standard (CHS), safeguarding, and Protection from Sexual Exploitation, Abuse, and Harassment (PSEAH) principles.

- Experience with evaluations of BMZ/German-funded projects is a strong advantage.

- Demonstrated ability to design and manage endline evaluations, deliver agreed outputs on time and within budget, and maintain high professional standards.

- Excellent analytical, facilitation, and report writing skills in English.

Desired Competencies

- Previous experience working in Somaliland.

- Knowledge of Somali language is an asset.

- Ability to facilitate participatory validation workshops and communicate effectively with diverse stakeholders (government, civil society, donors, and communities).

Evaluation Team (if applicable)

- The Lead Evaluator must fulfill the above criteria.

- The consultancy firm may include technical specialists (nutrition/SBC) and local enumerators with Somali language skills.

- Gender balance in the team is highly desirable.

## TECHNICAL AND FINANCIAL OFFER

Applicants have to provide a technical and financial offer.

- A technical and financial offer.

- All insurances are the responsibility of the evaluator(s).

- The consultant has to quote costs for travel, accommodation, per diem, vehicle rental, and enumerator training in the financial offer.

- Soft copies of relevant documents will be provided by Welthungerhilfe.

- Welthungerhilfe/ACRIF staff will facilitate community entry and contacts with interviewees.

- Laptops need to be provided by the evaluator(s).

- Offers have to be signed or include the phrase “valid without signature”.

The technical part of the offer should include:

- Reflections on the feasibility of this ToR (including suggestions for refining evaluation questions, if required).

- A brief description of the proposed evaluation design and methodology, and a workplan/adaptations to the suggested schedule (maximum 10 pages).

The financial part of the offer should include:

- A budget for the complete evaluation, stating fees per working day (plus VAT, if applicable), the number of working days proposed, and other costs (e.g., visa, logistics, workshops).

- Proof of professional registration and taxation (e.g., a tax number).

Please note:

- All insurance is the responsibility of the consultant(s) or firm.

- Soft copies of relevant documents will be provided by WHH and ACRIF.

- The consultant will be responsible for paying any taxes required by the government.

- WHH/ACRIF will facilitate community entry and stakeholder contacts, but all transport and accommodation remain the responsibility of the consultant.

- Laptops must be provided by the consultant(s).

- WHH may invite shortlisted evaluators for an interview before final selection.

Proposal Assessment Criteria

Please note that the proposals received will be assessed according to the following key criteria:

| Criterion | Details | Weighting |
| --- | --- | --- |
| Technical Quality | Clarity, feasibility, and rigor of the proposed methodology; alignment with ToR objectives; appropriateness of tools and workplan. | 30% |
| Relevant Experience | Proven track record in nutrition evaluations, especially MIYCN, and SBC; experience in Somaliland; quality of previous evaluation reports. | 15% |
| Team Composition | Qualifications and expertise of proposed consultant(s) | 15% |
| Financial Offer | Cost-effectiveness, transparency of budget (fees per day, working days, other costs), and overall value for money. | 40% |

## SUBMISSION OF PROPOSALS AND COMMUNICATION

Offers must be signed or include the phrase “valid without signature.” Submissions will be accepted from individual consultants, consultancy firms, commercial companies, NGOs, and academics.

Proposals should be submitted in English by email to: procurement.somaliland@whh.de with the subject line: “Endline Evaluation Proposal – SOM1053 Project”. The deadline for submission is 26th October 2025 at 23:59 EAT.   Late submissions will not be considered.