# REQUEST FOR PROPOSAL

REVIEW AND DEVELOPMENT OF MIDWIFERY TRAINING CURRICULUM FOR SOS COLLEGE OF HEALTH SCIENCE, MOGADISHU-SOMALIA

# 1.0 CONTEXT AND RATIONALE

## 1.1 About SOS Children’s Villages

SOS Children’s Villages Somalia chapter was established in 1984 as a grassroots response to deficiencies in the provision of caring, secure, and supportive foster care system for children who have lost parental care or at risk of losing in Somalia. As members of a Global Federation, SOS CV Somalia is committed to applying the Federation's statutes, standards for quality childcare, and stringent financial and administrative practices. SOS CV Somalia is committed to the welfare of children who lost parental care or at risk of losing parental care – often ensuring that children grow up in a loving family environment and strengthening families and communities as a preventive measure in the fight against child abandonment and social negligence. In Ensuring child safeguarding is mainstreamed across SOS programming and interventions, SOS Children’s Villages Somalia created and maintained a caring and protective environment, which promoted its core values, and prevents and addresses child abuse and exploitation. this included human resources development actions such as training and counselling. In this effort, SOS CV Somalia established and trained certified safeguarding investigation team, Ensures safe recruitment in all program locations and enhanced skills and knowledge on PSHEA and CS for Program. Moreover, SOS Children’s Villages currently operates in five regions in Somalia — Banadir, Bay, Bakool, Lower Shabelle, and Middle Shabelle — delivering comprehensive, multisectoral programs in child care, health, nutrition, protection, WASH, and education.

## 1.2 Description of programme location and context

In partnership with the Federal Ministry of Health and the Ministry of Education, Culture, and Higher Education, the SOS College of Health Sciences (Kulliyadda Culuumta Caafimaadka SOS) has been a cornerstone of health education in Somalia for over 25 years. Committed to excellence in training, the college has graduated more than 600 health professionals, many of whom are now serving in key healthcare roles across the country — from frontline providers to leadership positions. Over the years, the college has emerged as a centre of excellence, renowned for its rigorous academic standards, skilled faculty, and its vital contribution to strengthening Somalia’s health workforce.

The college’s main campus is located in Heliwa District, Mogadishu, and offers a range of health science programs at diploma, bachelor’s, and postgraduate levels. Key areas of study include Nursing, Midwifery, and Public Health, among others, aimed at building a competent and responsive health workforce for Somalia.

## 1.3 Rationale and overall objective of curriculum review

The main purpose of the consultancy is to review and redesign the midwifery training curriculum of SOS College of Health Sciences, ensuring its alignment with national priorities, international standards, and the evolving healthcare needs of Somalia.

The specific objectives of the assignment are to:

- Formulate competency statements and expected learning outcomes in alignment with the standards of competency-based midwifery education, using the International Confederation of Midwives (ICM) Essential Competencies framework.

- Develop a theoretical instructional framework that outlines modules and module units, ensuring comprehensive coverage of relevant content within a structured format.

- Design innovative instructional approaches and media to support active teaching, learning, and assessment strategies suitable for adult and professional learners.

- Establish valid and reliable assessment and evaluation methods that effectively measure the achievement of competencies and learning outcomes.

- Compile a comprehensive, up-to-date list of reference and resource materials, presented in an appropriate scholarly format (e.g., Harvard or APA style), to support both theoretical and clinical learning.

## 1.4 Instruction to bidders

Bidders are invited to submit their proposals for the review and redesign of the Bachelor of Science in Midwifery curriculum at SOS College of Health Sciences, located in Heliwa District, Mogadishu, Somalia. This call for proposals is open to all eligible national and international suppliers, including independent consultants and legally registered firms, capable of delivering the required services.

All costs associated with the preparation and submission of the proposal shall be borne by the bidder. These costs are not reimbursable and cannot be included as a direct cost of the assignment.

Proposals, along with all supporting documents, must be submitted in English, and the financial proposal must be quoted in US dollars.

## 1.5 Process of Submission of Bids

To facilitate submission, proposals must be stamped, signed, and submitted electronically in PDF format to: procurement@sossomalia.org. Electronic submissions are preferred.

Document titles should clearly indicate:

- Technical Proposal for Midwifery Curriculum Review – SOS College of Health Science, Heliwa – [Consultant/Company Name]

- Financial Proposal for Midwifery Curriculum Review – SOS College of Health Science, Heliwa – [Consultant/Company Name]

Please ensure that the technical and financial proposals are submitted separately—either as a sealed envelope (for hard copy) or as separate PDF files (for electronic submission).

During evaluation, only technical proposals will be reviewed initially. Financial proposals will be opened only for those shortlisted based on the technical assessment.

## 1.6 Documents to submit

- Bid submission / identification form

- Previous experience format

- Price schedule form (to be sealed in a closed envelope or a separate PDF file)

- Technical proposal

- CVs of the Curriculum review team member(s) including current geographical location(s)

- Three references (at least two of them must be familiar with your work)

- An example of a recent/relevant evaluation report (if available for public use)

## 1.7 Deadline for submission

The proposal has to be received by latest on 30th September 2025 by the end of the day. Proposals received after the deadline will be considered.

## 1.8 Modification and withdrawal of bids

Proposals may be withdrawn on written request prior to the closing date of this invitation. Any corrections or changes must be received prior to the closing date. Changes must be clearly stated in comparison with the original proposal. Failure to do so will be at bidder’s own risk and disadvantage.

## 1.9 Signing of the contract

SOS Children’s Villages will inform the successful bidder electronically and will send the contract form within 3 weeks after closure of the bid submission deadline. The successful bidder shall sign and date the contract, and return it to SOS Children’s Villages Somalia within seven calendar days of receipt of the contract. After the contract is signed by two parties, the successful bidder shall deliver the services in accordance with the delivery schedule outlined in the bid.

## 1.10 Rights of SOS Children’s Villages

- Contact any or all references supplied by the bidder(s);

- Request additional supporting or supplementary data (from the bidder(s));

- Arrange interviews with the bidder(s);

- Reject any or all proposals submitted;

- Accept any proposals in whole or in part;

- Negotiate with the service provider(s) who has/have attained the best rating/ranking, i.e. The one(s) providing the overall best value proposal(s);

- Contract any number of candidates as required to achieve the overall evaluation objectives

## 1.11 Evaluation of proposals

After the opening, each proposal will be assessed first on its technical quality and compliance and subsequently on its price. The proposal with the best overall value, composed of technical merit and price, will be considered for approval. The technical proposal is evaluated on the basis of its responsiveness to the Terms of Reference (TOR). Bidders may additionally be requested to provide additional information (virtual presentation or phone interview) to SOS Children’s Villages on the proposed services.

The criteria for selection are:

- Method: The proposed method for evaluating the programme is suitable

- Timetable/work plan: The timetable/work plan is realistic and meet the needs of the programme

- Cost: The cost of the proposal is reasonable and feasible, given the other aspects of the proposal

- Experience: The training and experience of the consultants in evaluations and recommendations from organisations for which the consultant(s) has previously worked

# 2.0 TERMS OF REFERENCE

## 2.1 Overall objective

The consultancy is intended to review & redesign the college’s undergraduate midwifery program.

## 2.2 Specific objectives

The specific objectives of the assignment are to:

Specific Objectives of the Assignment:

- Formulate clear competency statements and expected learning outcomes based on the International Confederation of Midwives (ICM) Essential Competencies framework.

- Develop a theoretical instructional framework that includes structured modules and module units covering all core content areas.

- Design innovative instructional approaches and media to support competency-based teaching, learning, and assessment methods.

- Establish valid and reliable assessment strategies that effectively measure student performance and the achievement of learning outcomes.

- Provide a comprehensive and updated list of reference and resource materials aligned with current academic and professional standards (e.g., Harvard or APA format).

- Align the curriculum with national regulatory and accreditation requirements, including those of the Ministry of Health and Ministry of Education.

- Strengthen the clinical training component, ensuring adequate exposure to real-world midwifery practice in diverse healthcare settings.

- Recommend faculty development and capacity-building measures to support effective implementation of the revised curriculum.

- Develop a final curriculum package, including syllabi, practicum guides, evaluation tools, and implementation guidelines, ready for institutional adoption.

## 2.3 Scope

Specifically, the consultancy will cover the following areas:

- Review of Existing Curriculum:

  - Conduct a detailed assessment of the current MoH Diploma-level midwifery curriculum, including course content, structure, delivery methods, and assessment tools.

  - Identify strengths, gaps, and areas for improvement in alignment with current health priorities and workforce needs.

- Stakeholder Engagement and Consultation Workshops:

  - Organize and facilitate consultation workshops with key stakeholders including faculty, MoH, MoECHE, regulatory bodies, clinical partners, midwifery professionals, and students.

  - Ensure inclusive participation to gather input and build consensus on curriculum priorities and structure.

- Curriculum Redesign and Development:

  - Redesign the curriculum structure, including modules, credit hours, competencies, learning outcomes, and course outlines.

  - Integrate emerging topics such as respectful maternity care, ethics, gender, human rights, and emergency obstetric care.

- Development of Learning and Assessment Materials:

  - Develop or recommend instructional materials, clinical practice guidelines, teaching aids, and assessment tools suitable for both theoretical and practical training.

  - Propose appropriate assessment methods that align with competency-based education.

- Clinical Practice Enhancement:

  - Strengthen the clinical training component by ensuring appropriate alignment with health service delivery settings and student learning needs.

- Faculty Development Recommendations:

  - Assess faculty capacity and provide recommendations for training and professional development to support effective delivery of the revised curriculum.

- Finalization and Validation:

  - Produce a comprehensive final curriculum package, including syllabi, practicum guides, logbook and evaluation tools.

  - Present the curriculum for stakeholder review and facilitate a validation workshop.

- Support for Implementation and Accreditation:

  - Provide guidance on implementation planning and support the college in preparing for accreditation or regulatory approvals.

## 2.4 Work plan and expected deliverables

The evaluation will be carried out in three key stages, with all activities leading to deliverables clearly highlighted in bold.

Stage 1: Prepare
Undertake preparations for the curriculum review:

- Propose detailed methodology, including stakeholder mapping and document review.

- Conduct desk review of existing curriculum, policies, and global midwifery standards (e.g., ICM).

- Identify key informants (educators, students, clinical preceptors, policymakers).

- Plan data collection (e.g., surveys, interviews, workshops) and logistics.

- Submit an inception report outlining:

  - (i) Revised methodology and tools

  - (ii) Review framework aligned with ICM competencies

- Prepare interview guides, feedback forms, and schedules for curriculum review activities.

Stage 2: Conduct

- Facilitate participatory consultations with key stakeholders eg MoH, MoECHE, universities & other relevant institutions.

- Collect data from interviews, workshops, and curriculum mapping exercises.

- Analyse findings to identify gaps, strengths, and alignment with national and international standards.

Stage 3: Submit Findings

- Prepare a draft report summarizing findings and initial recommendations.

- Present findings to stakeholders (educators, regulatory bodies, partners) in a validation meeting.

- Finalize and submit the report, including a roadmap for curriculum redesign.

## 2.5 Deliverables:

- Inception report detailing the refined methodology for the curriculum review, stakeholder engagement plan, and adapted data collection tools.

- Mapping and gap analysis report comparing the existing curriculum against national standards, ICM competencies, and stakeholder inputs.

- Presentation of preliminary findings and proposed curriculum structure to SOS Children’s Villages Somalia and key stakeholders for validation.

- Revised competency-based midwifery bachelor's curriculum, including updated course outlines, teaching-learning strategies, student assessment tools, and a standardized clinical logbook.

- Curated list of updated reference materials and teaching aids aligned with the revised curriculum.

## 2.6 Report criteria

The evaluation will result in a revised, competency-based National Midwifery Training Curriculum in English. The final report should be submitted in both electronic and hard copy formats. Any sensitive or confidential information collected during the review process should be anonymized and, if necessary, presented in a separate annex to ensure the protection of participants.

The report must follow the structure below:

Cover Page

- Title/logos

- Country

- Programme

- Date of submission

Executive Summary

- Purpose and scope of the curriculum review

- Methodology used (including limitations and challenges)

- Summary of key findings, conclusions, and recommendations

Main Body

- Background and rationale for reviewing the national midwifery curriculum

- Methodology and review process, including stakeholder engagement, desk review, and standards comparison (e.g., ICM, national frameworks)

- Curriculum mapping and gap analysis findings

- Revised National Midwifery Training Curriculum, including:

  - Program learning outcomes and graduate profile

  - Detailed course/unit outlines with:

    - Learning objectives

    - Teaching and learning methods (theory, skills lab, clinical)

    - Core content

    - Assessment methods

    - Required/reference materials

- Recommendations for implementation, addressing:

  - Key conclusions must be accompanied by clear, practical, and actionable recommendations

Annexes

- Terms of Reference (ToR)

- List of stakeholders consulted and institutions visited

- Curriculum mapping matrix (e.g., against ICM Essential Competencies 2019)

- Sample tools: student logbooks, assessment checklists, evaluation forms

- Glossary of terms

- Maps or list of midwifery training institutions included in the review

## 2.7 Qualification of the curriculum review team

The consultants must possess the following qualifications:

- Advanced training in midwifery, preferably at postgraduate level

- Proven experience in curriculum design, review, and evaluation—particularly in midwifery and health education

- Strong knowledge of Somalia’s health system, including Human Resources for Health (HRH) and national development priorities

- Understanding of child rights and issues affecting vulnerable children and families

- Strong facilitation, organizational, and interpersonal skills

- Experience in participatory approaches and appropriate data collection methods, including child- and youth-sensitive tools

- Strong analytical and conceptual skills

- Excellent written communication skills, including report writing and presentation

- Ability to collaborate effectively with relevant institutions, including midwifery schools, professional councils, ministries, and development partners

## 2.8 Logistical arrangements

When at the programme location, accommodation and transport to the field will be organized by the member association, including the full coverage of costs during the entire stay of the consultant(s) (not to be included into price proposal).

National or location level staff (SOS) will be available to help organize the interviews including contacting SOS, announcement and local preparation of evaluation, linking to community duty bearers and national authorities if required.

## 2.9 Timetable

The curriculum review and evaluation will commence on 1st june 2025 and will be carried out over a period of 45 days. The final report is expected to be completed and submitted no later than 15th July 2025.

| Activities | Dates | Time frame | Location |
| --- | --- | --- | --- |
| Prepare evaluation plan and submit inception report (including methodology and proposed interviewees) | TBD | 4 days | Remote / Office-based |
| Conduct desk review of existing curriculum, national policies, and ICM standards | TBD | 6 days | Field |
| Conduct data collection (interviews, focus groups, institutional visits) | TBD | 6 days | Field |
| Analyze data and identify key findings and gaps | TBD | 5 days | Office/field |
| Hold stakeholder consultation/validation workshop | TBD | 3 days | Venue |
| Prepare draft report (including revised curriculum and annexes) | TBD | 9 days | Remote |
| Incorporate feedback and finalize report and presentation materials | TBD | 7 days | Remote |
| Final report submission | TBD | 5 | Remote |

## 2.10 Duration of the contract and terms of payment

Payment will be made only upon SOS Children’s Villages acceptance of the work performed in accordance with the above-described deliverables. Financial proposals should include proposed stage payments. Payment will be affected by bank transfer in the currency of billing and is due 30 days after receipt of invoice and acceptance of work.

Funding and Payment: The consultant will be paid by SOS Children’s Villages as follows:

- 25% on the submission and approval of inception report

- 25% on completion of the draft report

- 50% on completion of final report

Duration of contract: the contract is effective from the moment it is signed until the acceptance of work by the international project team.

## 2.11 Notice of Delay

Shall the successful bidder encounter delay in the performance of the contract which may be excusable under unavoidable circumstances; the contractor shall notify SOS Children’s Villages in writing about the causes of any such delays within one (1) week from the beginning of the delay.

After receipt of the Contractor's notice of delay, SOS Children’s Villages shall analyse the facts and extent of delay, and extend time for performance when in its judgment the facts justify such an extension.

## 2.12 Copyright and other proprietary rights

SOS Children’s Villages shall be entitled to all intellectual property and other proprietary rights including, but not limited to, copyrights, and trademarks, with regard to products, processes, inventions, ideas, know-how, or documents and other materials which the Contractor has developed for SOS Children’s Villages under the Contract and which bear a direct relation to or are produced or prepared or collected in consequence of, or during the course of, the performance of the Contract. The Contractor acknowledges and agrees that such products, documents and other materials constitute works made for hire for SOS Children’s Villages.

All materials: plans, reports, estimates, recommendations, documents, and all other data compiled by or received by the Contractor under the Contract shall be the property of SOS Children’s Villages and shall be treated as confidential and shall be delivered only to SOS Children’s Villages authorized officials on completion of work under the Contract. The external consultant is obliged to hand over all raw data collected during the assessment to SOS Children’s Villages.

## 2.13 Termination

SOS Children’s Villages reserves the right to terminate without cause this Contract at any time upon forty-five (45) days prior written notice to the Contractor, in which case SOS Children’s Villages shall reimburse the Contractor for all reasonable costs incurred by the Contractor prior to receipt of the notice of termination.  SOS Children’s Villages reserves the right to terminate the contract without any financial obligations in case if the contractor is not meeting its obligations without any prior notice:

- Agreed time schedule

- Withdrawal or replacement of key personal without obtaining written consent from sos children’s villages

- The deliverables do not comply with requirements of tor

# 3.0 ANNEX

## 3.1 SOS Children’s Villages child protection policy and code of conduct

SOS Children’s Villages International has a child protection policy and code of conduct that all consultants will be expected to comply with and will be required to sign a statement of commitment to the policy. This will happen upon signing of contract, together with an orientation of consultants on internal child safeguarding processes and data protection regulations.

Before the actual start of data collection, a police check is to be provided, in case any direct contact with programme participants and/or any sensitive data is planned.

In addition to the above mentioned, the following key areas for ethical consideration need to be taken into account: http://childethics.com/ethical%20guidance/

Graham, A., Powell, M., Taylor, N., Anderson, D. & Fitzgerald, R. (2013). Ethical Research Involving Children. Florence: UNICEF Office of Research - Innocenti.

The successful bidder is requested to obtain written consent from all participants of the evaluation process and/or their official guardians/representatives (when applicable).

## 3.2 Bid submission / identification form

This bid form must be completed, signed and returned to SOS Children’s Villages. Bids have to reflect the instructions described in the Request for Proposal and Terms of Reference.

Any requests for information regarding this Request for Proposal shall be send to [insert name and email address].

The Undersigned, having read the complete Request for Proposals including all attachments, hereby offers to supply the services specified in the schedule at the price indicated in the Price Schedule Form, in accordance with the Terms of Reference included in this document.

Offering service for: [insert organization and name].

Company/Institution Name/Individual’s Name___________________________________________

2. Address, Country: ________________________________________________________________

3. Telephone: __________________ Fax _________________ Website_______________________

4. Date of establishment (for companies): _________________________________

5. Name of Legal Representative (if applicable): _________________________________________

6. Contact Person: _____________________________________ Email: ______________________

7. Type of Company: Ltd. Other _________________________

8. Number of Staff: ______________________________________

9. Subsidiaries in the region:

Indicate name of subsidiaries and address

a)___________________________________________________________

b)___________________________________________________________

c)___________________________________________________________

Validity of Offer:	valid until:____________________________________

Date

Signature and stamp

## 3.3 Previous experience form

| Description (services and products provided to the clients relevant to the current RFP) | Client | Contact person/phone, e-mail address | Date of assignment (from/to) |
| --- | --- | --- | --- |

## 3.4 Price schedule form

The financial proposal needs to include all taxes.

|  | Activity | Staff involved (indicate profile) | Number of people | Number of days | Daily rate | Total price per row | % of total price |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | A | B | C | D=AxBxC | E=D/F |
| 1 | Preparation of data collection |  |  |  |  |  |  |
| 2 | Data collection |  |  |  |  |  |  |
| 4 | First draft of the final report |  |  |  |  |  |  |
| 5 | Final report |  |  |  |  |  |  |
|  | Total Price (F) |  |  |  |  |  | 100% |

Accommodation and local transportation to be covered by Member Association, not to be included into price proposal.

This proposal should be authorized, signed and stamped

________________

(Name of Organisation)

Name of representative

Address:

Telephone/Fax/Email:

## 3.5 Technical proposal (guideline)

| Name of Organisation/Firm/Independent Consultant |  |
| --- | --- |
| Name of contact person for this proposal (for organisation/firm) |  |
| Address: |  |
| Phone/Fax: |  |
| E-mail: |  |

The technical bid should be concisely presented and structured in the following order to include, but not necessarily be limited to the following information listed below.

1. Quality and Relevance of Technical Proposal

- Describe all actions related to defining data collection methodology and conducting the baseline study

- Realistic work plan with time lines in accordance with ToR

- Detailed quality assurance process for data collection and analysis

2. Qualification and expertise of or organisation/team of consultants/consultant submitting proposal

- Reputation of firm/organisation and staff and individual consultant/s (competence and reliability) in carrying out evaluations

- Relevance of:

- Specialized knowledge

- Proven expertise in carrying out formative evaluations

- CVs for key staff