TOR FOR PROSOPIS BASED ANIMAL FEED MILLING SERVICES

| Country: | Somaliland |
| --- | --- |
| Project title: | Lot 3: Reforestation, afforestation & land restoration in locations adjacent to Burao, Somaliland – SOM1068 |
| Project no: | SOM 1068 |
| Project holder: | Welthungerhilfe |
| Co-Finance (Line): | European Union |
| Project period: | 18.11.2023- 17.05.2026 |
| Location | Burao, Somaliland |
| Outcome | Outcome 2: Targeted vulnerable Somali communities apply climate smart agro-pastoral and pastoral production and water supply practices. |
| Output | 6.7 Output 2.3 related to Outcome 2: Increased control and use of invasive species for environmental protection and income generation. |
| Activity | Prosopis Animal feed Production |

## 1. ACTIVITY DESCRIPTION

Prosopis juliflora, though invasive, offers potential economic opportunities when its pods are utilized for livestock feed. In Togdheer, animal feed shortages are a persistent challenge specially this year where  the seasonal rain was very short. This activity aims to transform Prosopis pods into affordable, sustainable livestock feed while enhancing community livelihoods and promoting environmental management.

## 2. ACTIVITY PARPOSE

Overall Objective: Provide prosopis pod milling services with the right machines and capacity of milling.

Specific Objectives:

  - Produce balanced livestock feed by milling and mixing pods with local available hay.

  - Documentation of pod sack and recording the quantities, label with names of collectors and e.t.c

## 3. SCOPE OF WORK

Key activities include:

- Milling collected pods and mixing with local hay

- Packaging and labeling the sacks (sacks should be labeled with the phone number and the name of the collector for easy identification)

- Monitoring and documentation of the whole process (monitoring feed quality, documentation of processed quantities, recording the names of the collectors and quantities submitted each week)

## 4. EXPECTED OUTPUTS

- 48 Mt of milled pods mixed with 8 Mt of local hay (1000 sacks) of balanced animal feed produced (contained milled pods mixed with local available hay)

- Supported marketing of the final product at local market

- Return earnings to pod collectors

## 6. REQUIREMENTS

Required labor and proper milling machines

- Required labor: 3 labor per day at the milling site.

- Proper milling machines: At least two millers to be operated at a time cable of processing  0.5 to  1 Mt of milled prosopis per day.

WHH SUPPORT

- WHH will support providing Transportation services of biweekly transporting collected pods from pod collector to Aroori Center and will hire Vehicle for Transporting of milled Feed from Aroori center to Market.

- will provide packaging sack and pod drying plastics , and  labelling materials (Permanent Marker for labeling)

- Will purchase required hay for mixing the milled pod

- will support covering the cost of renting milling machines

- Will provide technical support

7. TENTATIVE TIMELINE

Activity will begin December 10, 2025, to February 10th, 2026

SUBMISSION

- Milling cost Per kg (including labor, fuel, the cost of milling, and labeling packaging)

- Capacity of Milling rate per day (in Metric tons (MT)

- Deadline: submit the required documents no later than 27th of November

10. APPROVAL

| Requested by: | Approved by: | Approved by: |
| --- | --- | --- |
| Prosopis Expert: Yusuf Yasin Abdirahman | Finance Officer: Roda Mahamoud | Head of Project: Dorcas Matundu |
| Signature. | Signature……………. | Signature……………. |