# REQUEST FOR PROPOSAL

FOR THE DEVELOPMENT OF STRATEGIC PLAN FOR SOS COLLEGE OF HEALTH SCIENCE, MOGADISHU-SOMALIA

Contents

1.0 CONTEXT AND RATIONALE	3

1.1 About SOS Children’s Villages	3

1.2 Description of programme location and context	4

1.3 Rationale and overall objective of strategic plan	4

1.4 Instruction to bidders	4

1.5 Process of Submission of Bids	4

1.6 Documents to submit	4

1.7 Deadline for submission	4

1.8 Modification and withdrawal of bids	4

1.9 Signing of the contract	4

1.10 Rights of SOS Children’s Villages	4

1.11 Evaluation of proposals	5

2.0 TERMS OF REFERENCE	5

2.1 Overall objective	5

2.2 Specific objectives	5

2.3 Scope	5

2.5 Deliverables:	6

2.6 Report criteria	6

2.7 Qualification of the strategic plan team	7

2.8 Logistical arrangements	7

2.9 Timetable	7

2.10 Duration of the contract and terms of payment	7

2.11 Notice of Delay	8

2.12 Copyright and other proprietary rights	8

2.13 Termination	8

3.0 ANNEX	8

3.1 SOS Children’s Villages child protection policy and code of conduct	8

3.2 Bid submission / identification form	9

3.3 Previous experience form	9

3.4 Price schedule form	10

3.5 Technical proposal (guideline)	10

# 1.0 CONTEXT AND RATIONALE

## 1.1 Introduction of SOS College of Health Science

SOS Children’s Villages Somalia chapter was established in 1984 as a grassroots response to deficiencies in the provision of caring, secure, and supportive foster care system for children who have lost parental care or at risk of losing in Somalia. As members of a Global Federation, SOS CV Somalia is committed to applying the Federation's statutes, standards for quality childcare, and stringent financial and administrative practices. SOS CV Somalia is committed to the welfare of children who lost parental care or at risk of losing parental care – often ensuring that children grow up in a loving family environment and strengthening families and communities as a preventive measure in the fight against child abandonment and social negligence. In Ensuring child safeguarding is mainstreamed across SOS programming and interventions, SOS Children’s Villages Somalia created and maintained a caring and protective environment, which promoted its core values, and prevents and addresses child abuse and exploitation. this included human resources development actions such as training and counselling. In this effort, SOS CV Somalia established and trained certified safeguarding investigation team, Ensures safe recruitment in all program locations and enhanced skills and knowledge on PSHEA and CS for Program.

## 1.2 Description of programme location and context

In partnership with the Federal Ministry of Health and the Ministry of Education, Culture, and Higher Education, the SOS College of Health Sciences (Kulliyadda Culuumta Caafimaadka SOS) has been a cornerstone of health education in Somalia for over 25 years. Committed to excellence in training, the college has graduated more than 600 health professionals, many of whom are now serving in key healthcare roles across the country — from frontline providers to leadership positions. Over the years, the college has emerged as a center of excellence, renowned for its rigorous academic standards, skilled faculty, and its vital contribution to strengthening Somalia’s health workforce.

The college’s main campus is located in Heliwa District, Mogadishu, and offers a range of health science programs at diploma, bachelor’s, and postgraduate levels. Key areas of study include Nursing, Midwifery, and Public Health, among others, aimed at building a competent and responsive health workforce for Somalia.

## 1.3 Rationale and overall objective of strategic plan

The development of a strategic plan for SOS College of Health Sciences is essential to guide its growth, academic excellence, institutional sustainability, and responsiveness to Somalia’s evolving health and education needs. As the college continues to expand its role in producing qualified health professionals, a comprehensive strategic plan will provide a clear roadmap to align its mission, vision, and core values with national priorities and global standards. The SP blueprint aims to steer infrastructure/equipment growth, academic growth for faculty and students, funding growth, research trajectory, governance and leadership, partnerships and regulatory frameworks. The consultant is expected to develop a ten (10) year SP that addresses:

- A comprehensive situational analysis (SWOT, PESTLE, and stakeholder mapping) to assess the internal and external environment of the college.

- Engage key stakeholders—including faculty, students, alumni, regulatory bodies, and development partners—through participatory consultations.

- Review and refine the college’s mission, vision, core values, and strategic identity.

- Assess the current academic programs and recommend improvements, expansion, or new program areas based on national health needs and labour market demand.

- Define key strategic pillars, goals, and outcomes aligned with the college’s mandate and the national health and education agenda.

- Develop a practical implementation framework, including timelines, responsible units, required resources, and key performance indicators (KPIs).

- Propose robust quality control strategies and academic assurance mechanisms, including internal audits, academic reviews, accreditation compliance, and continuous staff development.

- Design a Monitoring, Evaluation, and Learning (MEAL) framework to support accountability, performance tracking, and adaptive management.

- Deliver a complete, professionally formatted strategic plan document that is actionable, measurable, and institutionally owned.

- Propose partnerships and funding approaches that steer the College to financial self reliance

## 1.4 Instruction to bidders

Bidders are invited to submit their proposals for developing a 10 year Strategic Plan for SOS College of Health Sciences, located in Heliwa District, Mogadishu, Somalia. This call for proposals is open to all eligible national and international suppliers, including independent consultants and legally registered firms, capable of delivering the required services.

All costs associated with the preparation and submission of the proposal shall be borne by the bidder. These costs are not reimbursable and cannot be included as a direct cost of the assignment.

Proposals, along with all supporting documents, must be submitted in English, and the financial proposal must be quoted in US dollars.

## 1.5 Process of Submission of Bids

To facilitate submission, proposals must be stamped, signed, and submitted electronically in PDF format to: procurement@sossomalia.org. Electronic submissions are preferred.

Document titles should clearly indicate:

- Technical Proposal for Strategic Plan Development–SOS College of Health Science, Heliwa – [Consultant/Company Name]

- Financial Proposal for Strategic Plan Development – SOS College of Health Science, Heliwa – [Consultant/Company Name]

Please ensure that the technical and financial proposals are submitted separately—either as a sealed envelope (for hard copy) or as separate PDF files (for electronic submission).

During evaluation, only technical proposals will be reviewed initially. Financial proposals will be opened only for those shortlisted based on the technical assessment.

## 1.6 Documents to submit

- Bid submission / identification form

- Previous experience format

- Price schedule form (to be sealed in a closed envelope or a separate PDF file)

- Technical proposal

- CVs of the Strategic Plan Development team member(s) including current geographical location(s)

- Three references (at least two of them must be familiar with your work)

- An example of a recent/relevant evaluation report (if available for public use)

## 1.7 Deadline for submission

The proposal has to be received by latest on 20th June 2025. Proposals received after the deadline will be not considered.

## 1.8 Modification and withdrawal of bids

Proposals may be withdrawn on written request prior to the closing date of this invitation. Any corrections or changes must be received prior to the closing date. Changes must be clearly stated in comparison with the original proposal. Failure to do so will be at bidder’s own risk and disadvantage.

## 1.9 Signing of the contract

SOS Children’s Villages will inform the successful bidder electronically and will send the contract form within 3 weeks after closure of the bid submission deadline. The successful bidder shall sign and date the contract and return it to SOS Children’s Villages Somalia within seven calendar days of receipt of the contract. After the contract is signed by two parties, the successful bidder shall deliver the services in accordance with the delivery schedule outlined in the bid.

## 1.10 Rights of SOS Children’s Villages

- Contact any or all references supplied by the bidder(s);

- Request additional supporting or supplementary data (from the bidder(s));

- Arrange interviews with the bidder(s);

- Reject any or all proposals submitted;

- Accept any proposals in whole or in part;

- Negotiate with the service provider(s) who has/have attained the best rating/ranking, i.e. The one(s) providing the overall best value proposal(s);

- Contract any number of candidates as required to achieve the overall evaluation objectives

## 1.11 Evaluation of proposals

After the opening, each proposal will be assessed first on its technical quality and compliance and subsequently on its price. The proposal with the best overall value, composed of technical merit and price, will be considered for approval. The technical proposal is evaluated on the basis of its responsiveness to the Terms of Reference (TOR). Bidders may additionally be requested to provide additional information (virtual presentation or phone interview) to SOS Children’s Villages on the proposed services.

The criteria for selection are:

- Method: The proposed method for evaluating the programme is suitable

- Timetable/work plan: The timetable/work plan is realistic and meet the needs of the programme

- Cost: The cost of the proposal is reasonable and feasible, given the other aspects of the proposal

- Experience: The training and experience of the consultants in evaluations and recommendations from organisations for which the consultant(s) has previously worked

# 2.0 TERMS OF REFERENCE

## 2.1 Overall objective

The consultancy is intended to develop a comprehensive ten year Strategic Plan for SOS College of Health Sciences. The plan will provide a clear roadmap to guide the college’s growth, enhance academic and operational excellence, strengthen institutional governance, and align its programs and services with national health priorities and international standards. It will serve as a strategic framework to ensure sustainability, quality assurance, and responsiveness to the evolving needs of the health education sector in Somalia.

## 2.2 Specific objectives

The specific objectives of the assignment are to:

- Assess the college’s internal and external environment through SWOT and PESTLE analyses.

- Engage key stakeholders to ensure inclusive input and shared ownership of the plan.

- Review and update the college’s vision, mission, and core values to reflect its future direction.

- Evaluate academic and administrative programs for relevance, quality, and future expansion.

- Identify strategic priorities and goals for the next ten years across all functional areas.

- Develop a practical implementation plan with timelines, responsibilities, and resources.

- Establish quality assurance mechanisms to support academic excellence and accountability.

- Design a monitoring and evaluation framework to track progress and guide adjustments.

- Produce a complete, actionable strategic plan document aligned with national and global standards.

- Formulate partnerships and funding plan for the College

## 2.3 Scope

Specifically, the consultancy will cover the following areas:

- Institutional Analysis:

- Conduct a detailed assessment of the college’s internal strengths and weaknesses, and the external opportunities and threats, using tools such as SWOT and PESTLE.

- Stakeholder Engagement:

- Facilitate inclusive consultations with key stakeholders including college leadership, faculty, students, alumni, regulatory bodies, SOS CV senior management, partners, and relevant government institutions.

- Strategic Direction Review:

- Review and refine the college’s vision, mission, core values, and strategic identity to align with its mandate and future aspirations.

- Program Assessment:

- Evaluate the quality, relevance, and effectiveness of existing academic and administrative programs, and identify opportunities for improvement or expansion.

- Strategic Priorities and Goal Setting:

- Identify key thematic areas, strategic goals, and objectives to guide the college’s development over the next ten years.

- Implementation Planning:

- Develop a detailed action plan that includes activities, timelines, responsible units, resource needs, and performance indicators.

- Quality Assurance Framework:

- Recommend quality control strategies and institutional mechanisms to enhance academic standards, program accreditation, and internal accountability.

- Monitoring and Evaluation Framework:

- Design a practical Monitoring, Evaluation, and Learning (MEAL) framework to support tracking of progress, performance measurement, and adaptive management.

- Strategic Plan Documentation:

- Prepare and deliver a complete, user-friendly, and professionally formatted strategic plan document ready for endorsement and implementation.

- Partnerships and funding streams:

- Propose viable partnerships and propose funding mechanisms for sustainability and College self-reliance

## 2.5 Deliverables:

The consultant is expected to produce the following deliverables:

- Inception Report

- Outlining the consultant’s understanding of the assignment, proposed methodology, detailed work plan, and stakeholder engagement strategy.

- Situational Analysis Report

- A comprehensive report presenting the findings from the SWOT, PESTLE, and stakeholder consultations, including key insights and baseline data to inform the strategic plan.

- Draft Strategic Plan

- A well-structured draft document including revised mission, vision, core values, strategic priorities, goals, objectives, implementation framework, quality assurance strategies, and a monitoring and evaluation plan.

- Validation Workshop

- Facilitation of a stakeholder validation workshop to present the draft strategic plan, collect feedback, and ensure ownership and alignment.

- Final Strategic Plan Document

- A professionally formatted and actionable Ten-year strategic plan incorporating stakeholder feedback and aligned with national and institutional priorities.

- Presentation Materials

- PowerPoint slides summarizing the strategic plan for use in high-level meetings, donor engagement, and public communication.

## 2.6 Report criteria

All reports and deliverables must meet the following standards:

- Clarity and Structure:

- Reports should be well-organized, clearly written, and professionally formatted, with key sections such as executive summary, findings, and recommendations.

- Evidence-Based:

- Content must be supported by relevant data, stakeholder input, and aligned with national policies and global best practices.

- Language and Format:

- Deliverables should be in professional English, free of errors, and submitted in editable Word and PowerPoint formats. Visuals such as charts and tables should enhance clarity.

- Strategic Alignment:

- All content must align with the college’s mandate and national education and health sector priorities.

- Originality and Confidentiality:

- Reports must be original, properly cited, and all data treated as confidential and used solely for this assignment.

## 2.7 Qualification of the strategic plan team

The consultants must possess the following qualifications:

- The team must have 5-10 years experience in developing strategic plans for academic or health institutions.

- The lead consultant should hold a master’s or PhD in Public Health, Education Planning, or a related field.

- The team should have strong knowledge of institutional planning and the Somali education and health context.

- Proven skills in applying tools like SWOT, PESTLE, and stakeholder analysis are required.

- Experience in facilitating participatory planning and stakeholder workshops is essential.

- Excellent report writing and presentation skills in English are required; Somali language is an asset.

- The team should include a strategic planner, health/education expert, and M&E specialist.

## 2.8 Logistical arrangements

Accommodation and local transportation during the consultancy period in Mogadishu will be arranged and fully covered by SOS Children's Villages Member Association. These costs should not be included in the financial proposal.

SOS national and local staff will support logistical coordination, including scheduling and organizing stakeholder interviews, community consultations, and meetings with relevant authorities and duty bearers. The team will also assist with necessary announcements, venue arrangements, and engagement with local stakeholders to facilitate smooth implementation of the strategic planning process.

## 2.9 Timetable

The strategic plan development consultancy will commence on 5th July 2025 and will be carried out over a period of 28 days. The final report is expected to be completed and submitted no later than  Mid-August 2025

| Activities | Time frame | Location |
| --- | --- | --- |
| Inception meeting and work plan finalization | 2 days | SOS College, Mogadishu |
| Document review and desk-based assessment | 3 days | Consultant’s location |
| Stakeholder consultations and field visits | 6 days | Mogadishu |
| Data analysis and strategic framework drafting | 5 days | Consultant’s location |
| Presentation of draft strategic plan | 1 day | Mogadishu |
| Stakeholder validation workshop |  | Mogadishu |
| Final report writing and submission | 8 days | Consultant’s location |

## 2.10 Duration of the contract and terms of payment

Payment will be made only upon SOS Children’s Villages acceptance of the work performed in accordance with the above-described deliverables. Financial proposals should include proposed stage payments. Payment will be affected by bank transfer in the currency of billing and is due 30 days after receipt of invoice and acceptance of work.

Funding and Payment: The consultant will be paid by SOS Children’s Villages as follows:

- 25% on the submission and approval of inception report

- 25% on completion of the draft report

- 50% on completion of final report

Duration of contract: the contract is effective from the moment it is signed until the acceptance of work by the international project team.

## 2.11 Notice of Delay

Shall the successful bidder encounter delay in the performance of the contract which may be excusable under unavoidable circumstances; the contractor shall notify SOS Children’s Villages in writing about the causes of any such delays within one (1) week from the beginning of the delay.

After receipt of the Contractor's notice of delay, SOS Children’s Villages shall analyse the facts and extent of delay, and extend time for performance when in its judgment the facts justify such an extension.

## 2.12 Copyright and other proprietary rights

SOS Children’s Villages shall be entitled to all intellectual property and other proprietary rights including, but not limited to, copyrights, and trademarks, with regard to products, processes, inventions, ideas, know-how, or documents and other materials which the Contractor has developed for SOS Children’s Villages under the Contract and which bear a direct relation to or are produced or prepared or collected in consequence of, or during the course of, the performance of the Contract. The Contractor acknowledges and agrees that such products, documents and other materials constitute works made for hire for SOS Children’s Villages.

All materials: plans, reports, estimates, recommendations, documents, and all other data compiled by or received by the Contractor under the Contract shall be the property of SOS Children’s Villages and shall be treated as confidential, and shall be delivered only to SOS Children’s Villages authorized officials on completion of work under the Contract. The external consultant is obliged to hand over all raw data collected during the assessment to SOS Children’s Villages.

## 2.13 Termination

SOS Children’s Villages reserves the right to terminate without cause this Contract at any time upon forty-five (45) days prior written notice to the Contractor, in which case SOS Children’s Villages shall reimburse the Contractor for all reasonable costs incurred by the Contractor prior to receipt of the notice of termination.  SOS Children’s Villages reserves the right to terminate the contract without any financial obligations in case if the contractor is not meeting its obligations without any prior notice:

- Agreed time schedule

- Withdrawal or replacement of key personal without obtaining written consent from SOS children’s villages

- The deliverables do not comply with requirements of tor

# 3.0 ANNEX

## 3.1 SOS Children’s Villages child protection policy and code of conduct

SOS Children’s Villages International has a child protection policy and code of conduct that all consultants will be expected to comply with and will be required to sign a statement of commitment to the policy. This will happen upon signing of contract, together with an orientation of consultants on internal child safeguarding processes and data protection regulations.

Before the actual start of data collection, a police check is to be provided, in case any direct contact with programme participants and/or any sensitive data is planned.

In addition to the above mentioned, the following key areas for ethical consideration need to be taken into account: http://childethics.com/ethical%20guidance/

Graham, A., Powell, M., Taylor, N., Anderson, D. & Fitzgerald, R. (2013). Ethical Research Involving Children. Florence: UNICEF Office of Research - Innocenti.

The successful bidder is requested to obtain written consent from all participants of the evaluation process and/or their official guardians/representatives (when applicable).

## 3.2 Bid submission / identification form

This bid form must be completed, signed and returned to SOS Children’s Villages. Bids have to reflect the instructions described in the Request for Proposal and Terms of Reference.

Any requests for information regarding this Request for Proposal shall be send to [insert name and email address].

The Undersigned, having read the complete Request for Proposals including all attachments, hereby offers to supply the services specified in the schedule at the price indicated in the Price Schedule Form, in accordance with the Terms of Reference included in this document.

Offering service for: [insert organization and name].

Company/Institution Name/Individual’s Name___________________________________________

2. Address, Country: ________________________________________________________________

3. Telephone: __________________ Fax _________________ Website_______________________

4. Date of establishment (for companies): _________________________________

5. Name of Legal Representative (if applicable): _________________________________________

6. Contact Person: _____________________________________ Email: ______________________

7. Type of Company: Ltd. Other _________________________

8. Number of Staff: ______________________________________

9. Subsidiaries in the region:

Indicate name of subsidiaries and address

a)___________________________________________________________

b)___________________________________________________________

c)___________________________________________________________

Validity of Offer:	valid until:____________________________________

Date

Signature and stamp

## 3.3 Previous experience form

| Description (services and products provided to the clients relevant to the current RFP) | Client | Contact person/phone, e-mail address | Date of assignment (from/to) |
| --- | --- | --- | --- |

## 3.4 Price schedule form

The financial proposal needs to include all taxes.

|  | Activity | Staff involved (indicate profile) | Number of people | Number of days | Daily rate | Total price per row | % of total price |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | A | B | C | D=AxBxC | E=D/F |
| 1 | Preparation of data collection |  |  |  |  |  |  |
| 2 | Data collection |  |  |  |  |  |  |
| 4 | First draft of the final report |  |  |  |  |  |  |
| 5 | Final report |  |  |  |  |  |  |
|  | Total Price (F) |  |  |  |  |  | 100% |

Accommodation and local transportation to be covered by Member Association, not to be included into price proposal.

This proposal should be authorized, signed and stamped

________________

(Name of Organisation)

Name of representative

Address:

Telephone/Fax/Email:

## 3.5 Technical proposal (guideline)

| Name of Organisation/Firm/Independent Consultant |  |
| --- | --- |
| Name of contact person for this proposal (for organisation/firm) |  |
| Address: |  |
| Phone/Fax: |  |
| E-mail: |  |

The technical bid should be concisely presented and structured in the following order to include, but not necessarily be limited to the following information listed below.

1. Quality and Relevance of Technical Proposal

- Describe all actions related to defining data collection methodology and conducting the baseline study

- Realistic work plan with time lines in accordance with ToR

- Detailed quality assurance process for data collection and analysis

2. Qualification and expertise of or organisation/team of consultants/consultant submitting proposal

- Reputation of firm/organisation and staff and individual consultant/s (competence and reliability) in carrying out evaluations

- Relevance of:

- Specialized knowledge

- Proven expertise in carrying out formative evaluations

- CVs for key staff